## Test Case Templates (hidden)
INDEX
Test Scripts
TC_No | Test Scenario | Test Description | Test Steps | Expected Result | Actual Result | Priority | Status
TC_01 | To Verify the Attributes in MSTR ITSA_Incident_C Cube. | To verify and validate the Incident Attributes in ITSA_Incident_C Cube | Prerequisite | Login to Prod dev 5.1 Upgrade MSTR Web application | User should be able to login to the respective application. | 1-High | Completed. Complete Attribute validaiton screen shots are attached in below document.
|  |  | Step1 | Login to Gilead Tenant and Navigate to the ITSA_Incident_C Cube. | User should be able to navigate to the ITSA_Incident_C cube.
|  |  | Step2 | Verify the all the respective attribute are available. | All the Attributes should be available in Prod dev instance,compaired to Prod instance.
|  |  | Step3 | Verify the Values respective to DB
|  |  | Step4 | Verify the below aspects in the Incident cube: 1.Validate the format. 2.Validated the ascending and descending orders. 3.Validated the filter options. 4.Validated the Apps 5.0 Upgrade Changes both OOTB and Customization Changes. | All the below should be validated: 1.Validate the format. 2.Validated the ascending and descending orders. 3.Validated the filter options. 4.Validated the Apps 5.0 Upgrade Changes both OOTB and Customization Changes.
TC_02 | To Verify the Metrics in MSTR ITSA_Incident_C Cube. | To verify and validate the Incident Metrics in ITSA_Incident_C Cube | Prerequisite | Login to Prod dev 5.1 Upgrade MSTR Web application | User should be able to login to the respective application. | 1-High | Completed. Complete Metric validaiton screen shots are attached in below document.
|  |  | Step1 | Login to Gilead Tenant and Navigate to the ITSA_Incident_C Cube. | User should be able to navigate to the ITSA_Incident_C cube.
|  |  | Step2 | Verify the all the respective Metrics are available. | All the Metrics should be available in Prod dev instance,compaired to Prod instance.
|  |  | Step3 | Verify the Values respective to DB
|  |  | Step4 | Verify the below aspects in the Incident cube: 1.Validate the format. 2.Validated the ascending and descending orders. 3.Validated the filter options. 4.Validated the Apps 5.0 Upgrade Changes both OOTB and Customization Changes. | All the below should be validated: 1.Validate the format. 2.Validated the ascending and descending orders. 3.Validated the filter options. 4.Validated the Apps 5.0 Upgrade Changes both OOTB and Customization Changes.

## INDEX
SL No | INDEX
1 | Environment and Statistics
2 | Test Cases - Funtional
3 | Test Results - Functional
4 | Test Cases - ETL
5 | Test Results - ETL
6 | Test Cases - Cube Count
7 | Test Results - Cube Count
8 | Test Cases - MSTR
9 | Test Results - MSTR
10 | Regression Results
11 | References

## Cubes & DD Details (hidden)
INDEX
S no | CUBE | Cube | Place | path | Teant | Instance | QA Cube Query | Remark
1 | PUBLISH INTELLIGENT CUBE | ITSM_Incident_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
2 | PUBLISH INTELLIGENT CUBE | ITSM_Request Item | IN FOLDER | Public Objects\Reports\ITSA\iCubes | Numerify_BI_Gilead. | PROD | OOTB
3 | PUBLISH INTELLIGENT CUBE | ITSM_TASK FSS_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
4 | PUBLISH INTELLIGENT CUBE | ITSM_Request Task_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
5 | PUBLISH INTELLIGENT CUBE | ITSM_Survey C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
6 | PUBLISH INTELLIGENT CUBE | ITSM_Request Item_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | No Updates required | No count drops
7 | PUBLISH INTELLIGENT CUBE | ITSM_Request Task Keyword | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
8 | PUBLISH INTELLIGENT CUBE | ITSM_TASK_FSS_C Keyword | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
9 | PUBLISH INTELLIGENT CUBE | CMDB CI Weekly Trend_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
10 | PUBLISH INTELLIGENT CUBE | ITSM_Reassignment_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead | PROD | Updated | Count drops in ldb.d_incident and ldb.d_incident_state : Marking it has a known issues
S no | Customized Cube | Path | QA Status | Remark | Open JIRA
1 | ITSA_ Incident _C | Shared Insight-> ITSA->iCubes | Completed | Working fine | DELV-6582
2 | ITSA_ Request Task _C | Shared Insight-> ITSA->iCubes | Completed | Working fine
3 | CMDB CI Weekly Trend _C | Shared Insight-> ITSA->iCubes | Completed | Working fine
4 | ITSA_ Survey C | Shared Insight-> ITSA->iCubes | Completed | Working fine
5 | ITSA_Reassignment_C | Shared Insight-> ITSA->iCubes | Completed | Working fine
6 | ITSM_ Request Item _C | Shared Insight-> ITSA->iCubes | Completed | Working fine
7 | ITSM_ Request Task Keyword | Shared Insight-> ITSA->iCubes | Not Yet Started
8 | ITSM_TASK FSS_C | Shared Insight-> ITSA->iCubes | Not Yet Started
9 | ITSM_TASK_FSS_C Keyword | Shared Insight-> ITSA->iCubes | Not Yet Started
S no | Dashboard | Path | QA Status | Remark
1 | Request item Overview | Landing Page | Not Yet Started
2 | Opened Overview | Landing Page | Not Yet Started
3 | Backlog Trend Analysis | Landing Page | Not Yet Started
4 | Open Work by Assignee | Landing Page | Not Yet Started
5 | Resolved-Overview | Landing Page | Not Yet Started
6 | Incident Keyword Overview | Landing Page | Not Yet Started
7 | Incident Keyword Analysis | Landing Page | Not Yet Started
8 | CI Incident Analysis | Landing Page | Not Yet Started
9 | P1 & P2 Incident Analysis | Landing Page | Not Yet Started
10 | FSS Overview | Landing Page | Not Yet Started
11 | SLA Overivew | Landing Page | Not Yet Started
12 | Survey Overview | Landing Page | Not Yet Started
13 | Incident Analysis | Landing Page | Not Yet Started
14 | Request Item Analysis | Landing Page | Not Yet Started
15 | Catalog Task Analysis | Landing Page | Not Yet Started
16 | FSS Analysis | Landing Page | Not Yet Started
17 | SLA Analysis | Landing Page | Not Yet Started
18 | Survey Analysis | Landing Page | Not Yet Started
19 | Browse Dashbaorad | Landing Page | Not Yet Started
Sno | Dashboard Name | Dashboard Path | Total Job Count | QA Status | Remark
1 | Completeness | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevCMDBCompleteness | 8663 | Not Yet Started
2 | Customer Satisfaction Survey | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardCustomer Satisfaction Survey | 4569 | Not Yet Started
3 | OLDSPARC Ops FSS - TASK0243845 | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDecommissionedOLDSPARC Ops FSS - TASK0243845 | 3426 | Not Yet Started
4 | MisRouted Tickets | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASOMisRouted Tickets | 3207 | Not Yet Started
5 | New Dashboard | IS:\Numerify_BI_Gilead\Object Templates\Analysis | 2289 | Not Yet Started
6 | RITM0226543 - Customer Satisfaction Survey | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASORITM0226543 - Customer Satisfaction Survey | 1314 | Not Yet Started
7 | Vendor Management Dashboard | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevStandardVendor Management Dashboard | 1279 | Not Yet Started
8 | Standard SLA | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardStandard SLA | 1196 | Not Yet Started
9 | Customer Satisfaction Survey | IS:\Numerify_BI_Gilead\Public Objects\Reports\ITSA\Gilead\Production\Standard | 985 | Not Yet Started
10 | CMDB Application | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevCMDBCMDB Application | 872 | Not Yet Started
11 | Landing Page_Gilead_JB | Numerify_BI_GileadPublic ObjectsReportsCommonLanding Page_Gilead_JB | 812 | Not Yet Started
12 | Standard SLA | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardStandard SLA (Monthly) | 805 | Not Yet Started
13 | Backlog Trend Analysis | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardBacklog Trend Analysis | 798 | Not Yet Started
14 | Incident Reassignment | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardIncident Reassignment | 790 | Not Yet Started
15 | Ageing Incidents & Requests | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardAgeing Incidents & Requests | 782 | Not Yet Started
16 | RITM0149553 - Resource productivity | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDecommissionedRITM0149553 - Resource productivity | 713 | Not Yet Started
17 | SPARC Ops FSS - TASK0243845 | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevFSSSPARC Ops FSS - TASK0243845 | 660 | Not Yet Started
18 | MisRouted Incidents | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardMisRouted Incidents | 654 | Not Yet Started
19 | Weekly Open & Closed Trend Analysis | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASOWeekly Open & Closed Trend Analysis | 608 | Not Yet Started
20 | Landing Page_Gilead_JB | IS:\Numerify_BI_Gilead\Public Objects\Reports\Common | 554 | Not Yet Started
21 | SPARC Ops FSS - TASK0243845 | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionFSSSPARC Ops FSS - TASK0243845 | 532 | Not Yet Started
22 | RITM0149547 Ageing Incidents & Requests | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASORITM0149547 Ageing Incidents & Requests | 516 | Not Yet Started
23 | RITM0149549 - Monthly Open & Closed Trend Analysis | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASORITM0149549 - Monthly Open & Closed Trend Analysis | 485 | Not Yet Started
24 | Completeness – TESMify | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevTMICompleteness – TESMify | 482 | Not Yet Started
25 | RITM0149550 - Reopened and Reassigned | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASORITM0149550 - Reopened and Reassigned | 447 | Not Yet Started

## Environment and Statistics
INDEX
Environment Details
PROD DEV POD details
Prod Dev MSTR Link
PROD POD details
Prod MSTR Link
SL No | Date | Task details | Environment | Remarks
1 |  | Full load/data patch
2
3
Total Deployments/loads
Total QA Defects
Total Retests

## Test Cases - Funtional
INDEX
TC_No | Test Case | Test Description | Expected Result | Actual Result | Result | Defect JIRA # | Comments
1 | DELV-18473 | P&G: CMDB data to come from Snow instead of MEGA | All the Rita Appliction from the CSV file should be intergated to Service Now.

## RITA Application_C
S No | Attribute | Source | UAT Validation | VI Changes
1 | *# of 3rd Party Resources With Access | Mega | working fine | No Match Deviation
2 | *# of P&G Users With Access | Mega | working fine
3 | *Adverse Medical Event Information | Servicenow | working fine
4 | *Application Description | Servicenow | Working fine - Change in the Data from the PROD instance.
5 | *Application Lifecycle Status | Servicenow | working fine
6 | *Application Nature | Servicenow | working fine
7 | *Application Nature (Internal) | Servicenow | working fine
8 | *Automated Decision Making | Servicenow | working fine
9 | *Biometric Data | Servicenow | working fine
10 | *Consumer Account Username And Password | Servicenow | working fine
11 | *Credit Card Numbers | Servicenow | working fine
12 | *Criminal Or Judicial Records | Servicenow | working fine
13 | *Data About Children Under 13 | Servicenow | working fine
14 | *Data About Teens Between 13-15 Years Old | Servicenow | working fine
15 | *Data Category | Servicenow | working fine
16 | *Data Retention Period In Days | Servicenow | working fine
17 | *Digital Signature Data | Servicenow | working fine
18 | *Electronic Identification Data | Servicenow | working fine
19 | *Family Composition | Servicenow | working fine
20 | *Financial Account Number | Servicenow | working fine
21 | *Genetic Data | Servicenow | working fine
22 | *Government ID ,Government-issued ID | Servicenow | working fine
23 | *Identification Data | Servicenow | working fine
24 | *Image/Sound Recordings | Servicenow | working fine
25 | *Implementation Supplier Name | Servicenow | Now the Data is same in both attributes, and deviation form PROD instance
26 | *Implementation Supplier SAP Code | Servicenow
27 | *In Which Country Are You Collecting PII? | Mega | working fine
28 | *Is The PII Data Accessed, Processed, Viewed Outside Of The EU? | Mega | working fine
29 | *L3 Business Processes | Mega | working fine
30 | *LE(s) receiving the services? | Mega | working fine
31 | *Other Health Or Medical Data | Servicenow | working fine
32 | *Other Supplier Name | Servicenow | Displaying only UNSPECIFIED, Not Data in the Servicenow
33 | *Other Supplier SAP Code | Servicenow
34 | *Owning Org Level 1 Leader | Servicenow | working fine
35 | *Owning Organization | Servicenow | working fine
36 | *P&G Asset Owner | Servicenow | working fine
37 | *Personal Characteristics | Servicenow | working fine
38 | *PII Data Handled For Specific Business Process | Mega | working fine
39 | *Political Opinions, Political Party Affiliation | Servicenow | working fine
40 | *Precise Geo Location Data | Servicenow | working fine
41 | *Privacy Risk | Servicenow | In Servicenow we have Unspecified which is equivalently mapped to No Personal Data. Mostly MSTR Change.
42 | *Profession | Servicenow | working fine
43 | *Protected Health Information as Defined By HIPAA | Servicenow | Only N is populated and deviation from prod instance. And this is as expected from servicenow.
44 | *Racial Or Ethnic Origin | Servicenow | working fine
45 | *Reason For Data Collection | Servicenow | working fine
46 | *SAP Vendor(s) Name | Servicenow | working fine
47 | *SAP Vendor(s) Number | Servicenow | working fine
48 | *Service Operation Supplier Name | Servicenow | Now the Data is same in both attributes and deviation from PROD.
49 | *Service Operation Supplier SAP Code | Servicenow
50 | *Sex Life, Sexual Orientation Questions | Servicenow | working fine
51 | *Software Supplier Name | Servicenow | Now the Data is same in both attributes
52 | *Software Supplier SAP Code | Servicenow
53 | *Technology Supplier Name | Servicenow | Now the Data is same in both attributes
54 | *Technology Supplier SAP Code | Servicenow
55 | *Trade Union Membership | Servicenow | working fine
56 | *Vendor Qualification | Servicenow | Only UNKNOWN and UNSPECIFIED and deviation from PROD instance. This is populated as expected from Servicenow.
57 | *Volume Of Records - ALL countries | Servicenow | working fine
58 | *Volume of Records - EU countries | Servicenow | working fine
59 | App Mgr Email | Servicenow | working fine
60 | App Mgr Name | Servicenow | working fine
61 | Application ID | Servicenow | working fine
62 | Application Repository Sub Type | Servicenow | working fine
63 | Application Repository Type | Servicenow | Data is different between PROD and UAT instance and populated as per servicenow
64 | Behavioral Data | Servicenow | working fine
65 | Birthdate | Servicenow | working fine
66 | Browser Cookie Data | Servicenow | working fine
67 | Comments / Other Information About The Application | Servicenow | Not Working Fine - Numerify issues displaying only Blanks. Fixed and working fine
68 | Data About Teens 16-18 | Servicenow | working fine
69 | Data Asset Name | Mega | working fine
70 | Data Classification | Servicenow | working fine
71 | Data Elements Combined Flag | Servicenow | working fine
72 | Data Subject Rights Result | Mega | working fine
73 | DataRetentionDefImplemented | Mega | working fine- same as PROD
74 | DataRetentionEvidence | Mega | working fine- same as PROD
75 | DataRetentionStatus | Mega | working fine- same as PROD
76 | DataSubjRightsCentralTeam | Mega | working fine- same as PROD
77 | DataSubjRightsEvidence | Mega | working fine- same as PROD
78 | DPIA: Result | Mega | working fine- same as PROD
79 | DPIA: Status | Mega | working fine- same as PROD
80 | DpiaDonebyLegal | Mega | working fine- same as PROD
81 | DpiaEvidence | Mega | working fine- same as PROD
82 | Ease Hyperlink | Servicenow | Derived of the data from PROD instance and populated as per the Service now
83 | Email address | Servicenow | working fine
84 | Employee Account Username and Password | Servicenow | working fine
85 | Employee Band Level | Servicenow | working fine
86 | Employee T# | Servicenow | working fine
87 | Employee Work Location | Servicenow | working fine
88 | Gap and NoGap Applications | Servicenow | Derived Attributes based upon the Servicenow Attributes.
89 | GDPR Flagoverrode Flag | Servicenow | working fine
90 | GDPR Grouping | Servicenow | working fine
91 | GDPR Grouping Overrode Flag | Servicenow | working fine
92 | GDPR Relevant Flag | Servicenow | working fine
93 | GDPR Relevant Flag Calculated | Servicenow | working fine
94 | GDPR Sensitivity | Servicenow | Numerify Issues , Unspecified is not handeled. Fixed and working fine
95 | Gender | Servicenow | working fine
96 | Geographic Data, Imprecise (not within 3.2187KM) | Servicenow | working fine
97 | Grace Period | Servicenow | working fine
98 | Grace Period Flag | Servicenow | working fine
99 | Grace Period Start Date | Servicenow | working fine
100 | Hosting Type | Servicenow | Data is different between PROD and UAT instance and populated as per servicenow
101 | Information Which Contans Pseudonymized Data | Servicenow | working fine
102 | InfoSec Classification | Mega | Data is different between PROD and UAT instance and populated as per servicenow
103 | InventoryEvidence | Mega | working fine
104 | InventoryKeptUptoDate | Mega | working fine
105 | InventoryResult | Mega | working fine
106 | InventoryStatus | Mega | working fine
107 | IP Address | Servicenow | working fine
108 | IRisk Last Performed | Servicenow | working fine
109 | L0 Owning Organization | Servicenow | working fine
110 | L1 Owning Organization | Servicenow | working fine
111 | L2 Owning Organization | Servicenow | working fine
112 | L2 Owning Organization Leader (Dir) | Servicenow | working fine
113 | L3 Owning Organizaiton | Servicenow | working fine
114 | L3 Owning Organization Leader (AD) | Servicenow | working fine
115 | Last Reviewed Date | Servicenow | working fine
116 | Lawful BasisResult | Servicenow | working fine
117 | Lawful BasisStatus | Servicenow | working fine
118 | LawfulnessBasisEvidence | Servicenow | working fine
119 | LawfulnessBasisProcessing | Servicenow | working fine
120 | Mac Address | Servicenow | working fine
121 | Marital Status | Servicenow | working fine
122 | Mega Creation Date | Servicenow | working fine
123 | Mega ID | MEGA | working fine
124 | Mega Update Date | Servicenow | working fine
125 | Minimization | MEGA | working fine
126 | MinimizationEvidence | MEGA | working fine
127 | Mobile device Ids | Servicenow | working fine
128 | Mobile Phone Number | Servicenow | working fine
129 | Name | Servicenow | working fine
130 | NoticeEvidence | MEGA | working fine
131 | NoticeProcessing | MEGA | working fine
132 | NoticesResult | MEGA | working fine
133 | NoticesStatus | MEGA | working fine
134 | Other (e.g. customer) Account Username and Password | Servicenow | working fine
135 | Other demographic and behavioral data gathered online | Servicenow | working fine
136 | PG CSA Last Performed | MEGA | working fine
137 | Phone Numbers (not Mobile) | Servicenow | working fine
138 | PII for authentication/ authorization only | Servicenow | Data is different between UAT and PROD instance, Have Unspecifed in UAT instance.
139 | Postal address | Servicenow | working fine
140 | Reasonable InfoSec: Result | Servicenow | working fine
141 | Reasonable InfoSec: Status | Servicenow | working fine
142 | ReasonInfosecUctrl | Servicenow | working fine
143 | ReasonInfosecUctrlEvidence | Servicenow | working fine
144 | Retired Date(Decommission) | Servicenow | working fine
145 | Salary amount or level | Servicenow | working fine
146 | Salary or benefits data | Servicenow | working fine
147 | Scope Doc Name | MEGA | working fine
148 | Snow ID | Servicenow | Structure of the data has changed , PROD -sys-id format.
149 | Source Type | Mega | Did not change , as the data is coming from both service now?
150 | Vendor Manager | MEGA | working fine
151 | VendorsEvidence | MEGA | working fine
152 | VendorsPrivacyInfosecUpdated | MEGA | working fine
153 | VendorsResult | MEGA | working fine
154 | VendorsStatus | MEGA | working fine
155 | Zip codes | Servicenow | working fine
S No | Metrics | UAT instance
1 | # GDPR 1 Total Application | Populated as per the new logic
2 | # GDPR 2 Total Application | Populated as per the new logic
3 | # GDPR 3 Total Application | Populated as per the new logic
4 | # GDPR 4 Total Application | Populated as per the new logic
5 | # GDPR Ungrouped Application | Populated as per the new logic
6 | # Inventory Gaps | Populated as per the new logic
7 | # Of Complete Applications | Populated as per the new logic
8 | # Of Total Applications | Populated as per the new logic
9 | % Data Field Completeness | Populated as per the new logic
10 | % Inventory Gaps | Populated as per the new logic
11 | % Total Application Org Level 1 | Populated as per the new logic
12 | Row Count | Populated as per the new logic
13 | Total Application Org Level 1 | Populated as per the new logic

## RITA_Application_Governance_C
S No | Attribute | Source | UAT Validation | VI Changes
1 | Always On CBP | Servicenow | Data is differnet bwtween UAT and PROD instance. Prod is having Y or N. | Since cube has filer on the Application_Nature , the count of the Application is more in UAT instance which is a valid
2 | App Owner Employee Type | Servicenow | The Functionaly is not working as expected - Numerify issue. 'App Owner Validity (y/n)' should be 'Y' only for the employee type. As of now displaying for all types. Fixed and working fine
3 | App Owner Validity (y/n) | Servicenow
4 | Application Description | Servicenow | working fine
5 | Application ID | Servicenow | working fine
6 | Application Name | Servicenow | working fine
7 | Application Owner Email Address | Servicenow | working fine
8 | Application Owner Full Name | Servicenow | In ITSA we never popuate the Full Name, But these attributes is moved from Rita to Snow, hence username is displaying, hence data deviation
9 | Application/Technology Nature | Servicenow | working fine
10 | BIA Rating for Availability | Servicenow | The Data has changed to Interger, ex: 1,2 and 3 where as data in Prod is High,Medium and Low
11 | BIA Rating for Confidentiality | Servicenow | The Data has changed to Interger, ex: 1,2 and 3 where as data in Prod is High,Medium and Low
12 | BIA Rating for Integrity | Servicenow | The Data has changed to Interger, ex: 1,2 and 3 where as data in Prod is High,Medium and Low
13 | Business Process | Mega | working fine
14 | Commissioning Memo Date Approved | Servicenow | working fine
15 | Commissioning Memo Document Link | Servicenow | working fine
16 | CREATIONDATE | Servicenow | working fine
17 | CREATOR | Servicenow | Data is changed from PROD to UAT instance
18 | Critical Apps | Derived attirbutes | Changes as per the new data of BIA Rating for Availability,BIA Rating for Confidentiality and BIA Rating for Integrity
19 | Data Privacy | Servicenow | working fine
20 | Data Classification | Servicenow | working fine
21 | Data Correctness | Servicenow | Calcualtion based upon the App Owner Validity (y/n) logic
22 | Data Currentness | Servicenow | working fine
23 | Data Privacy | Servicenow | working fine
24 | Data Retention Period (Actual policy which is in place) | Servicenow | working fine
25 | Database | Servicenow | Displaying only UNSPECIFIED and working fine as per the Servicenow
26 | EA Data Compliance | Servicenow | working fine
27 | EA Missing Data | Servicenow | working fine
28 | Hex Ext ID (Internal) | Servicenow | working fine
29 | Hex ID (Internal) | Servicenow | working fine
30 | Hosting | Servicenow | Data is changed from PROD to UAT instance
31 | Implementation Supplier | Servicenow | working fine
32 | Instance | Servicenow | working fine as per the Service now
33 | iRisk Data Compliance | Servicenow | working fine as per the Service now
34 | iRisk Date | Servicenow | working fine
35 | Keyword-Subject Area | Servicenow | Not Working fine - Numerify issue , Displaying only Blank. Fixed and working fine
36 | L0 Owning Organization | Servicenow | working fine
37 | Last Reviewed Date | Servicenow | working fine
38 | Lead Solution Architect | Servicenow | working fine
39 | License | Servicenow | Not Working fine - Numerify issue , Displaying only UNSPECIFIED, We fixed it Dev instance,waiting for the DELV-18957, which is dependent.
40 | Life Cycle Status | Servicenow | working fine
41 | Link to EASE | Servicenow | working fine
42 | Owning Organization | Servicenow | working fine
43 | Owning Organization Level 1 | Servicenow | working fine
44 | Owning Organization Level 1 Leader | Servicenow | working fine
45 | Owning Organization Level 2 | Servicenow | working fine
46 | Owning Organization Level 2 Leader | Servicenow | working fine
47 | Owning Organization Level 3 | Servicenow | working fine
48 | Owning Organization Level 3 Leader | Servicenow | working fine
49 | P&G Application Owner | Servicenow | working fine
50 | RAMP Date | Servicenow | working fine
51 | RAMP Location | Servicenow | working fine
52 | Registration Data Compliance | Servicenow | working fine as per the new logic and populating only Non Complainces
53 | Registration Missing Data | Servicenow | working fine as per the new logic and populating only Non Complainces
54 | Registration Overall Compliance | Servicenow | working fine as per the new logic and populating only Non Complainces
55 | Regulated System | Servicenow | working fine
56 | Release | Servicenow | working fine
57 | Server | Servicenow | working fine
58 | Service Operations Supplier | Servicenow | working fine
59 | Site Name | Servicenow | working fine
60 | Snow ID | Servicenow | working fine
61 | Sox Classification | Servicenow | Displying only UnSpecified and working fine as Servicenow
62 | Standard | Servicenow | Data deviation from Prod instance and working fine as per the Servicenow
63 | Technology Supplier | Servicenow | working fine
64 | Validation Data Compliance | Servicenow | working fine
65 | Validation Missing Data | Servicenow | working fine
66 | Vendor Software Supplier | Servicenow | working fine
S No | Metrics | UAT instance
1 | # of Data Correct Applications | Working fine
2 | # of Data Current Applications | Working fine
3 | # of Data InCorrect Applications | Working fine
4 | # of EA Compliant Applications | Working fine
5 | # of EA Non Compliant Applications | Working fine
6 | # of IT Risk Assessment Complete Applications | Working fine
7 | # of IT Risk Assessment InComplete Applications | Working fine
8 | # of Non Current Applications | Working fine
9 | # of Registration Complete Applications | Working fine
10 | # of Registration Compliant Applications | Working fine
11 | # of Registration InComplete Applications | Working fine
12 | # of Registration Non Compliant Applications | Working fine
13 | # of Validation Compliant Applications | Working fine
14 | # of Validation Non Compliant Applications | Working fine
15 | % Data Complete | Working fine
16 | % Data Correct | Working fine
17 | % Data Current | Working fine
18 | % EA Compliance | Working fine
19 | % IT Risk Assessment | Working fine
20 | % Legal Validation Compliance | Working fine
21 | % of EA Compliance Apps | Working fine
22 | % of Registration Compliant Apps | Working fine
23 | % of Registration Data Complete Apps | Working fine
24 | % of Registration Data Correct Apps | Working fine
25 | % of Registration Data Current Apps | Working fine
26 | % of Validation Compliance Apps | Working fine
27 | % Registration Compliance | Working fine
28 | % Risk Completeness | Working fine
29 | Data Correct | Working fine
30 | Data Current | Working fine
31 | Row Count | Working fine
32 | Total # of Apps | Working fine
SELECT Count(distinct a.row_id) as cnt FROM ldb.f_rita_application_c_fact a JOIN ldb.d_rita_application_c b ON a.rita_application_c_key=b.row_key JOIN ldb.d_rita_application_ext_c c ON b.rita_application_ext_c_key=c.row_key JOIN ldb.d_lov_mega_data_currentness_c d ON c.data_currentness_c_key=d.row_key JOIN ldb.d_lov_mega_data_correct_c e ON c.data_correct_c_key=e.row_key JOIN ldb.d_processing_activities_managing_organization_c a12 ON a.managing_organization_c_key=a12.row_key JOIN ldb.d_lov_processing_activities_ot_life_cycle_status_c a13 ON b.application_lifecycle_status_c_key=a13.row_key JOIN ldb.d_lov_processing_activities_ot_repository_type_c a14 ON b.application_nature_c_key=a14.row_key Where (a14.cust_dimension_name_c IN ('Application','Application - Externally Owned','Application Platform','Application Platform - Externally Owned') AND a13.source_dimension_name IN ('Design/Build', 'Launch/Deploy', 'Discovery/Requ.','UNSPECIFIED','Leverage/Optimize', 'Qualify/Deliver', 'Retired', 'Sunset','Exception') ) AND a.soft_deleted_flag='N'

## Rita_Application_Infosec_C
S no | Attribute | Source | UAT Validation | VI Changes
1 | Application ID | Servicenow | Working fine | No much Deviation except below issues
2 | Application Lifecycle Status | Servicenow | Working fine
3 | Application Nature | Servicenow | Working fine
4 | Application Repository Type | Servicenow | Working fine
5 | BIA Availability | Servicenow | Working fine
6 | BIA Confidentiality | Servicenow | Working fine
7 | BIA Integrity | Servicenow | Working fine
8 | Compliance Factor | Mega | Working fine
9 | Data Asset Name | Servicenow | Working fine
10 | Exclude in InfoSec Flag | Mega | Working fine
11 | Exclusion Date | Mega | Working fine
12 | Exists in iRisk | Mega | Working fine
13 | Exists in Legacy G1 | Mega | Working fine
14 | Exists in Legacy G234 | Mega | Working fine
15 | GDPR Grouping | Servicenow | Working fine
16 | Grace Period | Servicenow | Working fine
17 | Infosec In Scope | Mega | Working fine
18 | Infosec Not Applicable | Mega | Working fine
19 | iRisk Assessment Status | Mega | Working fine
20 | iRisk Category (Internal) | Mega | Working fine
21 | iRisk Category Name | Mega | Working fine
22 | iRisk ID | Mega | Working fine
23 | iRisk Open Issues | Mega | Working fine
24 | iRisk Status | Mega | Working fine
25 | L0 Owning Organization | Servicenow | Working fine
26 | L1 Owning Organization | Servicenow | Working fine
27 | L2 Owning Organization | Servicenow | Working fine
28 | L3 Owning Organization | Servicenow | Working fine
29 | Mega Hex | Servicenow | Working fine
30 | Owning Organization | Servicenow | Working fine
31 | P&G Asset Owner | Servicenow | Working fine
32 | Privacy Risk | Servicenow | Working fine
33 | Project Team GDPR Relevant OverWrittenFlag | Servicenow | Working fine
34 | Reason for Exclusion | Mega | Working fine
35 | SL SPOC | Mega | Working fine
iRisk Open issues metric is not working fine

## Sheet7
Total Application Count has been reduced from 60 K to 20 K
GDPR Validation
v
Infosec_privacy_c cube
ITAM_Application Governance_c

## RITAApplicationPrivacyCompli
S no | Attribute | Source | UAT Validation | VI Changes
1 | Application ID | Servicenow | Working fine | No Much Deviations
2 | Application LifeCycle Status | Servicenow | Working fine
3 | Application Nature | Servicenow | Working fine
4 | Application Repository Type | Servicenow | Working fine
5 | Assessment Status | Mega | Working fine
6 | BIA Availability | Servicenow | Working fine
7 | BIA Confidentiality | Servicenow | Working fine
8 | BIA Integrity | Servicenow | Working fine
9 | Created Date | Servicenow | Working fine
10 | Data Asset Name | Mega | Working fine
11 | Due Date | Mega | Working fine
12 | Exclude in Privacy Flag | Mega | Working fine
13 | GDPR Grouping | Servicenow | Working fine
14 | Grace Period | Servicenow | Working fine
15 | L0 Owning Organization | Servicenow | Working fine
16 | L1 Owning Organization | Servicenow | Working fine
17 | L2 Owning Organization | Servicenow | Working fine
18 | L3 Owning Organization | Servicenow | Working fine
19 | Mega Hex | Mega | Working fine
20 | Owning Organization | Servicenow | Working fine
21 | PG Asset Owner | Servicenow | Working fine
22 | PIA/DPIA Status | Mega | Working fine
23 | Privacy Category Name | Mega | Working fine
24 | Privacy Category(Internal) | Mega | Working fine
25 | Privacy Compliance Factor | Mega | Working fine
26 | Privacy Dashboard Flag | Mega | Working fine
27 | Privacy Exclusion Date | Mega | Working fine
28 | Privacy Exists in iRisk | Mega | Working fine
29 | Privacy Exists in iRisk Legacy Flag | Mega | Working fine
30 | Privacy Exists in Legacy Flag | Mega | Working fine
31 | Privacy In Scope | Mega | Working fine
32 | Privacy iRisk Status | Mega | Working fine
33 | Privacy Not Applicable | Mega | Working fine
34 | Privacy Reason for Exclusion | Mega | Working fine
35 | Privacy Risk | Mega | Working fine
36 | Privacy Submission Date | Mega | Working fine
37 | Privacy Submitter | Mega | Working fine
38 | PRV-0018 | Mega | Working fine
39 | SL SPOC | Mega | Working fine

## Test Cases - Cube Count
INDEX
Pre Requisite: | Cube query has to be updated for latest changes
TC_No | Test Case | Expected Result | Actual Result | Result | Cube query name | Defect JIRA # | Comments
S No | Cube | VI | Issues | Observations
1 | RITA_Application_ Cube | Application Tracker VI | Vendor Qualification attribute is only Unknown and Unspecified | Other Supplier Name and Other Supplier SAP Code : Compelted UNSPECIFIED
|  |  | DataSubject Right Result attribute is UNKNOWN | Source Type : This is still displying Mega, Should it change to Service Now and Mega
GDPR Sensitivity - Need to Handle Unspecified
Comments/otherInformation About the Application attributes is only Blank
2 | RITA_Application_Governance_c cube | ITAM_Application_Governance VI | Database Attirbute is compeltely UNSPECIFIED | Confirmation on Data Privacy ( UNSPECIFIED and No Personal Data)
Keyword-Subject Area is compeletey UNSPECIFIED
License attribute is compeletey UNSPECIFIED
Sox Classification attirbue is compeletey UNSPECIFIED
3 | RITA_Application_Infosec_c cube. RITA_Application_privacy_c cube. | GDPR Application Infosec_privacy_VI | iRisk Open Issues Count Metric is displyaing 0
Unspecified is not handled for IRisk_ID

## References
INDEX
References - Design document, Unit test document, data lineage, Data profiling document (if any)

## QA_Efforts Estimations (hidden)
Home
| Pre Upgrade |  | Prod 003CJ_ 3.2 | prod dev006J_ 3.2
Post Upgrade
| Gilead 5.1 Upgrade |  |  |  |  | Parent Ticket: DELV-6251
S no | Task | Start Date | End Date | Time in hrs | Remark | Task Jirra's
1 | 3.2 Prod Base line |  | 2017-05-29 | 5 mins | Triggered the Delivery Test | DELV-6266
2 | 3.2 Prod Base line_QA Failure Analysis_Cuts |  | 2017-05-29 | 1 hrs | 3 Failures | DELV-6266
3 | 3.2 Prod Base line_QA Failure Analysis_Mats |  | 2017-05-29
4 | 100 % Mats Coverage |  | 2017-05-29 | 3 hrs | Worked for Incident;Reassignment;CMDB Ci Weekly treand-c cube updated and count drop validation. | DELV-6259
|  |  | 2017-05-30 | 3 Hrs | Worked on Request_task,Task_Fss_Keyword,Request_item, Survey_c.
5 | 100 % cust coverage (Datamapper provided on 09_May_2017)
6 | Actual Baseline Report |  | 2017-06-07 | 5 mins |  | DELV-6424
7 | Usage Report |  | 2017-06-07 | 5 mins |  | DELV-6423
8 | Gilead_5.1 Upgrade_ Data mapper_QA_Cust Coverage |  | 2017-06-07 | 1 hrs | Cust Coverage anlaysis and writing the required test scripts. | DELV-6429
|  |  | 2017-06-08 | 4 Hrs
9 | Gilead_5.1_Upgrade_Prod dev_QA Test Scripts and User Document |  | 2017-06-07 | 1 hrs |  | DELV-6430
10 | Cust and Mats ETL Run in Prod dev |  | 2017-06-10 | 5 mins | Tiggered the Delivery Test | DELV-6508
11 | 5.1 ETL_QA Analysis in Prod dev (ETL Issues) |  | 2017-06-12 | 2hrs | QA Failure in Prod dev instance. | DELV-6505,6506,6507
12 | 5.1 Mats_Cube Query Validations in Prod dev |  | 2017-06-12 | 4 Hrs | Validated the Cust Queries in Prod dev instance. | DELV-6509-Task Ticket.
12.1 | 5.1 Mats_Cube Query QA Analysis_Prod dev(Redshift issues) |  | 2017-06-12 |  | Cust Failure in prod dev instance. | DELV-6514,DELV-6513,DELV-6535
13 | MSTR Cube Validation |  | 2017-06-13 |  |  | DELV-6514,DELV-6513,DELV-6535
13.1 | Incident Cube |  | 13-Jun-2017 14-Jun-2017 15-Jun-2017 (Retest Incident issues). | 7 :30 Hrs |  | DELV-6593
13.2 | ITSA_Request Task_ |  | 2017-06-16 | 3:00 Hrs |  | DELV-6594
13.3 | CMDB CI Weekly Trend_C |  | 2017-06-16 | 3:00 Hrs |  | DELV-6608
13.4 | ITSA_Survey_C |  | 2017-06-19 | 3:00 Hrs |  | DELV-6625
13.5 | ITSA_Reassignment_C |  | 2017-06-19 | 3:00 Hrs |  | DELV-6626
13.6 | ITSA_Request_Item_C |  | 2017-06-19 | 3:00 Hrs |  | DELV-6637
13.7 | ITSA_Request_Task_Keyword_C
13.7 | ITSA_TASK FSS_C
13.9 | ITSA_TASK_FSS_C Keyword
14 | Dashboard
14.1