## QA Validation status
|  |  | QA Validation Status Prod Dev instance |  |  | Pord Move Ticket
S No | Jira | Description | Status | Date | Issues | DELV-18134
1 | DELV-17463 | P&G: Executive Operational Dashboard Changes for FY 19/20 | Completed in Dev instance
2 | DELV-17594 | Exec Ops: Changes to Met All SLAs Flag and Resolved Incidents Met All SLAs % | Completed in Dev instance | 2019-07-26 | Noticed Data issues in PROD Dev instance , will retest the same in PROD QA or prod Dev.
3 | DELV-16934 | P&G: Enhance RITM Cubes & Create New RITM SLA Dashboard | Completed in Dev instance | 25-JULY-2019 26-JULY-2019 | DELV-18321 DELV-18313 Fixed and Working fine
4 | DELV-17566 | P&G: Add AG Parent Attribute to Multiple ITSM Cubes | Completed in Dev instance | 2019-07-26 | DELV-18332 Fixed and working fine on 29_JULY-2019
5 | DELV-18292 | Add new field to ITSA_Incident_C: Quantitative Impact | Completed in UAT instance | 2019-08-01 | This attribute is already avaialble in PROD instance, but filtering is not working fine
6 | DELV-18291 | Add new field to ITSA_Incident_C: Unit of Measure | Completed in UAT instance | 2019-08-01

## ITSA & Upgrade
| JIRA Details |  |  | Resources |  |  | Expected
Due Date | Sno | JIRA | Summary | ETL | QA | MSTR | ETL - Completion | MSTR - completion | QA - completion | Delivery Date
2019-07-22 | 1 | DELV-17833 | PNG: Upgrade 6.00.001 HF2 Ellora Hf16 to 6.4 & MSTR 10.11 to MSTR2019( to track the upgrade related issues) | Sandeep/Harsha | Kishore/Bhavani | Param/Pooja | 2019-06-27 | 2019-03-07 | 2019-05-07 | 2019-07-22
| 2 | DELV-18045 | Service Now : Madrid Upgrade - Project communication - UAT Closure - 5th July, Sys_user Extraction Test from SNOW UAT to Numerify PROD DEV | Harsha | NA | NA | 2019-07-16 | NA | NA | 2019-07-22
2019-09-08 | 1 | DELV-17463 | P&G: Executive Operational Dashboard Changes for FY 19/20 | Harsha | Kishore | Pooja | 2019-07-24
| 2 | DELV-17594 | Exec Ops: Changes to Met All SLAs Flag and Resolved Incidents Met All SLAs % | Harsha | Kishore | Param | 2019-07-16
| 3 | DELV-16934 | P&G: Enhance RITM Cubes & Create New RITM SLA Dashboard | Harsha | Kishore | Param | NA
| 4 | DELV-17566 | P&G: Add AG Parent Attribute to Multiple ITSM Cubes | Harsha | Kishore | Param | 2019-07-16
| 5 | DELV-17750 | P&G: Creation Request for Problem SLM Dashboard | Harsha | Kishore | Param | 2019-07-26
| 1 | DELV-14430 | P&G: Lineage for P&G Cubes
| 2 | DELV-17894 | P&G: Retrofit dashboards to new visual standards

## QA Estimates
S No | Jira | Description | Steps | Complexity | App. QA Estimates in hours | Activity Date | Status
1 | DELV-17463 | P&G: Executive Operational Dashboard Changes for FY 19/20 | Requirement Analysis | EOD Dashboard-Aggregated Fact, PNG Custome Filter and VI validation | 2 |  | Not Started
|  |  | ETL Validation |  | 3 |  | Not Started
|  |  | MSTR Validation |  | 3 |  | Not Started
2 | DELV-17594 | Exec Ops: Changes to Met All SLAs Flag and Resolved Incidents Met All SLAs % | Requirement Analysis | Met SLA Flag logic includes the Task_sla_final | 1 | 2019-07-10 | Completed
|  |  | ETL Validation |  | 6 |  | In progress
|  |  | MSTR Validation |  | 1
3 | DELV-16934 | P&G: Enhance RITM Cubes & Create New RITM SLA Dashboard | Requirement Analysis | DELV-16964,DELV-16965- Two Dossier Should be created | 2 | 2019-07-15 | Completed
|  |  | ETL Validation |  | NA |  | Not Started
|  |  | MSTR Validation |  | 4 |  | Not Started
4 | DELV-17566 | P&G: Add AG Parent Attribute to Multiple ITSM Cubes | Requirement Analysis |  | 0.5 | 2019-07-17 | Completed
|  |  | ETL Validation |  | 2 |  | Not Started
|  |  | MSTR Validation |  | 0.5 |  | Not Started
5 | DELV-17750 | P&G: Creation Request for Problem SLM Dashboard | Requirement Analysis | New SLA Problem Cube should be build | 2 |  | Not Started
|  |  | ETL Validation | DELV-17751- Met SLA Logic should be implemented and other attirbutes | 13 |  | Not Started
|  |  | MSTR Validation |  | 5 |  | Not Started
|  |  |  | Total | 45

## RITA
| JIRA Details |  |  | Resources |  |  | Expected
Due Date | Sno | JIRA | Summary | ETL | QA | MSTR | ETL - Completion | MSTR - completion | QA - completion | Delivery Date
2019-08-28 | 1 | DELV-18072 | P&G: CR-308-Apply Visual Design Standards to all GDPR Dashboards | Sriharsha | Kishore | Pooja
| 2 | DELV-18061 | P&G: CR-345- fix irisk id data feed for info sec & privacy compliance report | Sriharsha | Kishore | Pooja
| 3 | DELV-18069 | P&G:CR-343- GDPR Application info sec & Privacy compliance report - L2 organization | Sriharsha | Kishore | Pooja
| 4 | DELV-18064 | P&G:CR-335 - Application tracker: fix grace period calculation | Sriharsha | Kishore | Pooja
| 5 | DELV-18068 | ITAM Application Governance and GDPR Application Tracker: Data Privacy Level and Field level changes | Sriharsha | Kishore | Pooja
2019-08-28 | 1 | DELV-18081 | CR-339-EASE Data Privacy Elements DATA_MODEL DB view change | Sriharsha | Kishore | Pooja
| 2 | DELV-18080 | P&G: CR-346- GDPR - L0 instead of L1 filtering fixes | Sriharsha | Kishore | Pooja
| 3 | DELV-18079 | P&G-CR-332-App Governance Dashboard: Legal Validation link attributes | Sriharsha | Kishore | Pooja
| 4 | DELV-18078 | P&G:CR-348- Remove Unregistered Devices column in Overall view | Sriharsha | Kishore | Pooja
| 5 | DELV-18077 | P&G:CR-349-Rename Security Leader Header Label in Overall view | Sriharsha | Kishore | Pooja
| 6 | DELV-18076 | P&G:CR-341- Application Governance Report: fix compliance chart | Sriharsha | Kishore | Pooja
| 7 | DELV-18075 | P&G:CR-342-GDPR Application Tracker - add L2 org to filters | Sriharsha | Kishore | Pooja
| 8 | DELV-18073 | P&G: CR-334-Fix color coding in Numerify for last review date | Sriharsha | Kishore | Pooja

## Dynatrace & DP
| JIRA Details |  |  | Resources |  |  | Expected
Due Date | Sno | JIRA | Summary | ETL | QA | MSTR | ETL - Completion | MSTR - completion | QA - completion | Delivery Date
| 1 | DELV-17046 | Digital Presence Historical data load | Prathyusha |  | Bhavesh
| 2 | DELV-17207 | Digital Presence: Include Calibre Data in Digital Presence | Prathyusha |  | Bhavesh
| 3 | DELV-17206 | Digital Presence: Get Response Time data from Dynatrace API application | Prathyusha |  | Bhavesh
Sep | 4 | DELV-17874 | P&G: Digital Presence: Create a DP Website_C Snapshot Table and use it to filter dashboard data. | Prathyusha |  | Bhavesh
| 5 | DELV-17653 | P&G: Digital Presence: Ingest PSAT results from ServiceNow Scanning table. | Prathyusha |  | Bhavesh
| 6 | DELV-17205 | Digital Presence: Include SEO Data in Digital Presence | Prathyusha |  | Bhavesh
ITOT

## Advance Analytics
| JIRA Details |  |  | Resources |  |  | Expected
Due Date | Sno | JIRA | Summary | ETL | QA | MSTR | ETL - Completion | MSTR - completion | QA - completion | Delivery Date
2019-08-26 | 1 | DELV-18084 | P&G: Incident Clustering Production Implementation