## legend (hidden)
10 - New (Draft)
11 - On-hold
20 - Submitted (for Review)
30 - Planned for Release
40 - Assigned to Tech Team
45 - Requirements Reviewed
50 - Work In Progress
55 - Design Approved
60 - Build Complete (for Unit Testing)
70 - Unit Tested (for UAT)
80 - UAT Sign-off (for Deployment)
90 - Released (for Closure)
95 - Closed (Cancelled)
99 - Closed (Complete)

## General
Item # | Category | Requirement | Details | Upd Date | Release | Status | Comment
Asset-1 | Operations | Track unique asset report customer visitors per month | Provide a counter (better: trend) which allows us to track the number of unique visitors (excluding ITAM/Infosec Stakeholders, Developers and Ops) on a monthly basis. Do this for the Hardware Asset Dashboard and separately for the Application Asset Dashboard. |  |  | 20 - Submitted (for Review) | Agree. But this is not particularly high priority for me.
Asset-2 | Opportunity | Optimize access request management process |  |  |  | 10 - New | Agree. Preference to automate.
Asset-3 | Opportunity | Clearly distinguish ITAM from InfoSec (Vulnerabilities) requirements - also in UI? |  |  |  |  | Agree. Tagging the reports/widgets
Asset-4 | Opportunity | AGF 3.0 simplification |  |  | Initial | 20 - Submitted (for Review)
Asset-5 | Opportunity | Hardware Dashboard in Numerify instead of Excel distribution |  |  |  |  | Agree.
Asset-6 | Opportunity | Hardware Tab table content alignment | HW-96 |  |  | 20 - Submitted (for Review) | Agree.
Asset-7 | Security | Provide View per roles defined | RITA Security slides |  |  | 20 - Submitted (for Review) | Agree.
Asset-8 | Device Details Download | Offer the capability to download or access a workbook containing all attributes of devices within the site. | All reports |  | Initial | 20 - Submitted (for Review) | Agree. Would be best if the user can choose the attributes to be downloaded. As a device can have a lot of attributes, showing everything on the screen will be difficult.
Asset-9 | IT Health | Compliance % and details linked to/ Drilldown from IT Health |  |  | Initial | 30 - Planned for Release | Agree.
Asset-10
Asset-11
Asset-12
Asset-13
Asset-14
App-16 | View: tbc | Configuration Management | Link Application Assets to Hardware/ Software Assets (separate report) so that User can drill down/ up | 2018-12-27 | Initial, Prio 2 | 10 - New (Draft) | [TW 12/27] To be designed: how will this capabilities be offered to stakeholders

## Persona Use Cases upd
| PERSONA | Asset Category
Persona: AD, Director, VP, BU IT leader - leader of an organization of Application Owners OR organizations Governance delegate! | Organizational Leader | Applications
Use Case: drive organization compliance to 100% for all org. owned application objects in scope.
(Scope differs per compliance metric, e.g. Foundational compliance - all applications and platforms that are not decommissioned; IT Risk compliance - all foundational scope with PG AlwaysOn CBP = yes; etc.)
Need: |  |  | Transparency on organization compliance for all Application Governance aspects today.
Visibility on compliance gaps - per sub-organization* so that they can be addressed.
*More specific:
A BU IT Leader or VP should be able to see the metrics for his entire organization, and should be able to see for each of his VPs or directors. Etc.
For GBS IT the service hierarchy we use for the org nodes -> A Director should be able to see the metrics for his entire organization, and should be able to see for each of his Associate Directors. An AD should be able to see the metrics for his entire organization, and should be able to see for each Application Owner.
Non GBS/ IT: general concept that an nodes org leader is a target. These would come from the app spocs outside the gbs/it nodes. Tbc. - still comming from Mega Service Hierarchy.
It should be possible to drill down from the top to the Application Owner.
Once you are at the Application Owner level, the details table should list the owned applications each with metrics and attribute details.
Ability to download into Excel.
Persona: Functional Stakeholder (ITAM, IT Security, Enterprise Architecture, Validation Owner) | Global Stakeholder | Applications
Use Case: drive P&G compliance to 100% for all application objects in scope and for functional area.
(Scope differs per compliance metric, e.g. Foundational compliance - all applications and platforms that are not decommissioned; IT Risk compliance - all foundational scope with PG AlwaysOn CBP = yes; etc.)
Use Case: drive P&G asset compliance (registration/ documentation) to 100% for all devices
Need: |  |  | Transparency on overall P&G and and organization compliance for all Application Governance aspects today.
Transparency on overall P&G, site-by-site and integrator-managed compliance for all Device Governance aspects today
Visibility on application compliance gaps - per sub-organization* so that they can be addressed.
*More specific:
A Functional Stakeholder should be able to see the metrics for the entire P&G organization, and should be able to see for each BU IT Leader and for the GBS/IT VPs.
A Vice President should be able to see the metrics for his entire organization, and should be able to see for each of his directors.
A Director should be able to see the metrics for his entire organization, and should be able to see for each of his Associate Directors.
An AD should be able to see the metrics for his entire organization, and should be able to see for each Application Owner.
It should be possible to drill down from the top to the Application Owner.
Once you are at the Application Owner level, the details table should list the owned applications each with metrics and attribute details.
Visibility on % unregistered deivces - per site so that they can be addressed.
Visibility on centrally managed device compliance gaps - per type/ integrator, so that they can be addressed.
Visibility on top compliance gaps so that they can be addressed. E.g. BIA Availability missing for 90% if the applications, Hosting missing for 87% of the applications, etc.
Ability to create charts and tables for specific analysis needs, ability to download into Excel.
Persona: Functional Stakeholder (ITAM, IT Security, Enterprise Architecture, Validation Owner) | Global Stakeholder | Hardware | to be added
Use Case: drive P&G compliance to 100% for all hardware objects in scope and for functional area.
Use Case: drive P&G asset compliance (registration/ documentation) to 100% for all devices
Need:
Persona: Application Asset Owner | Asset (App) Owner | Application
Use Case: drive owned application compliance to 100%
(Scope differs per compliance metric, e.g. Foundational compliance - all applications and platforms that are not decommissioned; Validation – FDA regulated flagged apps only, etc)
Need: |  |  | Transparency on compliance for list of owned applications for all Application Governance aspects today.
Visibility on compliance gaps so that they can be addressed.
The details table should list the owned applications each with metrics and attribute details.
Ability to download into Excel.
Persona: Integrator | Integrator | Hardware
Use Case: drive centrally managed list of devices (certain types, per supplier/ integrator) compliance to 100%
Need: |  |  | Transparency on compliance for specific device type, for all registered devices.
Visibility on compliance gaps so that they can be addressed.
Transparency on vulnerabilities and EVP enrollment for all centrally managed devices per integrator
Visibility on critical and high vulnerabilties and guide to close the gap
The details table should list the respective devices each with metrics and attribute details.
Ability to download into Excel.
Tbc. List of GBS/IT organization members to be mapped as Integrators for visibility and governance
Persona: Site Security Leader (and Security Lead Teams) | Site Security Leader | Hardware
Use Case: drive site-managed list of devices (e.g. SMO site, plant, R&D centre) compliance to 100%
Out of scope tbc: applications by site (will be managed by organization)
Need: |  |  | Transparency on compliance for all registered devices, plus transparency on not-registered devices with IP address mapped to site
Visibility on compliance gaps so that they can be addressed.
The details table should list the respective devices each with metrics and attribute details.
Ability to download into Excel.

## Group Genies
Persona | Workspace Name | PowerBI Prod link | Group Genie Group
Asset Categories
Global Stakeholder | Asset Gov Overall | RITA - Asset Gov Overall | GDSG-RITA-AssetAdmin | Application and Hardware
Integrator | Asset Gov for Asset Types | RITA - Asset Gov for Asset Types | GDSG-RITA-Integrator | Hardware
Organizational Leader | Asset Gov for Organizational Leaders | RITA - Asset Gov for Organizational Leaders | GDSG-RITA-OrgLeaders | Application
Site Security Leader | Asset Gov for Sites | RITA - Asset Gov for Sites | GDSG-RITA-SSL | Hardware
Security Lead | Asset Gov across Sites | RITA - Asset Gov across Sites | GDSG-RITA-SecLeadTeam | Hardware - group of SSLs, tbc. Whether needed!
Asset (App) Owner | n/a (web page) | https://myrita.pg.com | n/a | Application

## Vulnerabilities (hidden)
Item # | Category | Requirement | Details | Upd Date | Release | Status | Comment
V-1 | Entry Page | Infosec Metrics to be displayed (metrics and trends) | #Registered Devices, #Active Devices, % Ownership Accuracy, % Site Accuracy |  | Initial | 20 - Submitted (for Review)
V-2 | Metric | EVP Compliance % Chart/ Metric | https://pgone.sharepoint.com/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx |  | Initial | 20 - Submitted (for Review)
V-3 | Metric | # not-compliant EVP Devices Chart/ Metric | https://pgone.sharepoint.com/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx |  | Initial | 20 - Submitted (for Review)
V-4 | Metric | # Devices with Critical Vulnerabilities Metric | https://pgone.sharepoint.com/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx |  | Initial | 20 - Submitted (for Review)
V-5 | Metric | Devices with Vulnerabilities by Criticality Chart/ Metric | https://pgone.sharepoint.com/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx |  | Initial | 20 - Submitted (for Review)
V-6 | Metric | # Vulnerabilities by Criticality Chart/ Metric | https://pgone.sharepoint.com/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx |  | Initial | 20 - Submitted (for Review)
V-7 | Metric | # Obsolete OS Devices Metric | https://pgone.sharepoint.com/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx |  | Initial | 20 - Submitted (for Review)
V-8 | Metric | Vulnerabilities Ratings | CVSS v3.0 Ratings Severity Base Score Range None 0.0 Low 0.1-3.9 Medium 4.0-6.9 High 7.0-8.9 Critical 9.0-10.0 |  | Initial | 20 - Submitted (for Review)
V-9 | Metric -> Details | Chart - # Devices with Vulnerability | Devices with Vulnerabilities Report |  | Initial | 20 - Submitted (for Review)
V-10 | Metric -> Details | # Vulnerabilities by Criticality | Vulnerability Report: Table should contain the following Columns: Device Name, Primary Device Owner, Site Code, Vulnerability Severity, Vulnerability Associated to Device, Vulnerability Proposed Fix, Temporal Score, Last Scan Date, etc.: From Qualys Data provided, use Column U for Vulnerability Description and Column V for Fix Recommendation. |  | Initial | 20 - Submitted (for Review)
V-12 | Metric -> Details | EVP Compliance | Non-EVP compliant Devices Report: Shows table containing list of windows online devices that are non-compliant. Table should contain the following columns. Device Name, Primary Device Owner, Site Code, Non-compliance reason, Integrator, OS information, Patch information, Anti-virus information. |  | Initial | 20 - Submitted (for Review)
V-13 | Metric -> Details | # Devices with Critical Vulnerabilities | Devices with Critical Vulnerabilities Report: Shows table containing list of devices with critical vulnerabilities. Table should contain the following columns. Device Name, Primary Device Owner, Site Code, Temporal Score, Associated Critical Vulnerabilities, Proposed fix to Critical Vulnerabilities, Integrator, OS information, Patch information, Anti-virus information. |  | Initial | 20 - Submitted (for Review)
V-14 | Metric -> Details | # Obsolete OS Devices | Offline Devices with Obsolete OS report: Shows table containing list of offline devices with obsolete OS. Table should contain the following columns. Device Name, Primary Device Owner, Site Code, Integrator, OS information, Patch information, Anti-virus information, Last Seen Date. |  | Initial | 20 - Submitted (for Review)
V-15 | Reports | Drill-down capabilities | Drill down to devices - that are non-compliant and their reasons. - with Critical Vulnerabilities. - with Obsolete OS. |  | Initial | 20 - Submitted (for Review)
V-17 | Report: All | Non-EVP Compliant Devices - Filters | Hardware Status, Device Type, Device Owner, Discovery Source |  | Initial | 20 - Submitted (for Review)
V-18 | Report: All | Non-EVP Compliant Devices - Details | Device Name, Site Name, Site Code, Device Owner, Device Type, IP Address, Non-Compliant Reason, Assignment Group, Hardware Status, Last Patch Scan, Last Seen Online, Signature Age, EPTM Full Scan Age, EPTM Full Can Date, Critical Crisis Patches not installed, Patch Cycle, Patch Scan Age, Discovery Source, OS Description, OS Service Pack, OS Edition, MAC Address, EPTM Version, Tapp Vulnerability, Snow ID, PG Asset ID, Malware Virus Protection Version, Compliance STatus |  | Initial | 20 - Submitted (for Review)
V-19 | Report: All | Devices with Critical Vulnerability - Content | devices with discovered "critical" vulnerabilities , sourcing from SNOW and scanning solution, per authorized assignment groups, potential additional page-level preset filter to be specified, per code: End Date top 1 by Latest End Date 'vw_BridgeDevice'[Criticality] is Critical Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 20 - Submitted (for Review) | to be specified
V-20 | Report: All | Devices with Critical Vulnerability - Filters | Site, Hardware Status, Device Type, Severity Level, Criticality, Discovery Source |  | Initial | 20 - Submitted (for Review)
V-21 | Report: All | Devices with Critical Vulnerability - Details | Snow ID, PG Asset ID, Device Name, Title, Device Type, Site Name, Vulnerability Type, Average of CVSS Temporal Score, OS Information, Discovery Source, Hardware Status, Description, Recommendation, Anti-Virus Information, Device Owner, Criticality |  | Initial | 20 - Submitted (for Review)
V-22 | Report: All | Devices with Vulnerability - Content | devices with discovered vulnerabilities , sourcing from SNOW and scanning solution, per authorized assignment groups, potential additional page-level preset filter to be specified, per code: End Date top 1 by Latest End Date Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 20 - Submitted (for Review) | to be specified
V-23 | Report: All | Devices with Vulnerability - Filters | Site, Hardware Status, Device Type, Severity Level, Criticality, Discovery Source |  | Initial | 20 - Submitted (for Review)
V-24 | Report: All | Devices with Vulnerability - Details | Snow ID, PG Asset ID, Device Name, Title, Device Type, Site Name, Site Code, Vulnerability Type, Average of CVSS Temporal Score, OS Information, Discovery Source, Hardware Status, Anti-Virus Information, Description, Recommendation, Device Owner, Criticality |  | Initial | 20 - Submitted (for Review)
V-25 | Report: All | Vulnerability - Content | vulnerabilities with identified devices (to be specified) per authorized assignment groups?, potential additional page-level preset filter to be specified, per code: End Date top 1 by Latest End Date Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 20 - Submitted (for Review) | to be specified
V-26 | Report: All | Vulnerability - Filters | Site, Hardware Status, Device Type, Severity Level, Criticality, Discovery Source |  | Initial | 20 - Submitted (for Review)
V-27 | Report: All | Vulnerability - Details | Criticality, Title, SNOW ID, PG Asset ID, Device Name, Device Owner, Site Name, Site Code, Device Type, Vulnerability Type, Temporal Score, OS Information, Integrator, Lifecycle Status, Anti-Virus Information, Recommendation, Description |  | Initial | 20 - Submitted (for Review)
V-28 | Report: All | Vulnerability - Link | downloadable CSV (for IT Asset Admins onyl with large content)
V-29 | Report: All | Offline Devices with Obsolete OS - Content | "offline" (to be specified) devices with obsolete OS (to be specified - per EVP), per authorized assignment groups?, potential additional page-level preset filter to be specified, per code: End Date top 1 by Latest End Date IsRegistered is 1 Network Connected is no Obsolete Flag is True Assignment Group is not (Blank) Is Accountable is True Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 20 - Submitted (for Review) | to be specified
V-30 | Report: All | Offline Devices with Obsolete OS - Filters | Site, Hardware Status, Device Type, Device Owner, Assignment Group |  | Initial | 20 - Submitted (for Review)
V-31 | Report: All | Offline Devices with Obsolete OS - Details | Device Name, Snow ID, PG Asset ID, Assignment Group, Site Name, Site Code, Discovery Source, last seen, Hardware Status, Antivirus Information, OS Service Pack, Device Owner, Device Type, OS Description |  | Initial | 20 - Submitted (for Review)
V-32 | Report: All | KPI Trends - Content | page-level filters to be specified |  | Initial | 20 - Submitted (for Review)
V-33 | Report: All | KPI Trends - Filters | Site, Assignment Group, Country, Region, Area, Lifecycle status |  | Initial | 20 - Submitted (for Review)
V-34 | Report: All | KPI Trends - Details | % Compliant Devices, # EVP Enrolled Devices, # devices with critical vulnerabilities,#AC/WL Locked Devices, #Obsolete OS Devices, #Server 2008 Devices, #Windows XP Devices, # Other Obsolete OS, |  | Initial | 20 - Submitted (for Review)
V-35 | Dashboard | Vulnerability Report for BU Leaders | CR 243 Formula is =if(AND([Employee Type]="Employee",related(rAssignGrp[Org Derivation rule])="Employee") ,[Employee Organization],related(rAssignGrp[Org])) And I have a mapping table relating Assignment Group to Org Derviation Rule, and Org AND([Employee Type]="Employee" --> means that there is an employee tagged as the owner of the device. |  | Initial | 20 - Submitted (for Review)
V-36 | Integration | Device data Export | Regular data transfer to Infosec Core Alerting system ( DOMO/ Cybrics/ Kenna....) from Numerify needs to be enabled |  | Initial | 20 - Submitted (for Review)
V-37 | Report: All | Additional slicers | Add Exploit Available Add Vulnerability Status (new, fixed, resurfaced) |  | Initial | 10 - New (Draft) | more details from Richard?
V-38 | Integration | EVP | EVP data to be loaded to Numerify. Update calculation logic of existing KPIs? |  | Initial | 20 - Submitted (for Review) | more details tbc - DG?
V-39 | Integration | Scanning data (Tenable) | Scanning data to be sourced from Tenable. Update calculation logic of existing KPIs? |  | Initial | 20 - Submitted (for Review) | more details tbc - DG?
V-40 | Integration | BDNA | Integrate BDNA data and make use of Obsolete OS and Vulnerability information to augment Discovery, EVP, and Vulnerability reports. |  | Later Release | 10 - New (Draft) | to be confirmed if still desired and priority, and whether BDNA is strategic
V-41 | Report: SSL | Patch management | Similar to Vulnerability Management, we want to update the patches in devices - Site Security Leaders |  | Later Release | 10 - New (Draft) | to be confirmed if still desired and priority
V-42 | Metric | Put age threshold on vulnerability reporting | RITA CR 247 |  | Later Release | 10 - New (Draft) | to be confirmed if still desired and priority
V-43 | Field addition | Add "Obsolete OS remediation plan" as a field on cmdb_ci_computer - R&D request | RITA CR 239 |  | Later Release | 10 - New (Draft) | to be confirmed if still desired and priority
removed from NumeRITA scope

## Application
Item # | Category | Requirement | Details | Upd Date | Release | Status | Comment
App-1 | Usability | Intro Page | Each workspace shall come with an Intro page to provide perspective on scope and purpose, and instructions, contact names for inquiries | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | OK. [DG 1/21] Agree to keep [TW 12/27] Keep (BW 12/19) Obsolete unless HW does this-my impression was that users don't look for the high level info in the application itself based on FAQs we got.
App-10 | Report: Individual | Individual Asset Owner - Registration and Compliance | see sheet App-10 | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | With the new secuirty setup. This will be provided through filtering/ save as local copy. OK. [TW 12/27] still valid (BW 12/19) most likely obsolete-clarifying with iRisk governance owners.
App-11 | Metric | Enterprise Architecture Assessment Metric | % of completed architecture relevant documentation see sheet App-1ff AGF 3.0 | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | OK for now. [DG 1/21] Per discussion with Barbara, I wonder if this is really needed. Or maybe, compress everything into 1 view. Like the Infosec.
App-12 | Metric | irisk Compliance Metric | % of completed iRisk assessment see sheet App-1ff AGF 3.0 | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | OK for now. [DG 1/21] Per discussion with Barbara, I wonder if this is really needed. Or maybe, compress everything into 1 view. Like the Infosec.
App-13 | Report: All? | Trendline Reporting within Dashboard | 3 trendlines: 0) Show trendlines for every Owning Org Level 1. I have to manually adjust the PowerBI reports to get this done. 1) number of application assets and 2) % compliance over time. Consolidate all available data - include historic data from Azure/ PowerBI! Have dynamic trendlines? So that we can chose to see last three years or last 3 days Create the trendlines separately per regisration/ target metrics | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | OK - but please see adjustment [DG 1/21] To adjust the trendline, would like to see dynamic attributes on Trendline. Right now, I need to manually adjust the PowerBI reports to see what I want. See right for what I mean.
App-14 | Usability | Report Drill Down | Capability to drill down from compliance outage (charts) to application/ field level gap (missing data field) | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | OK. DG 1/21 Agree
App-15 | Report: Org | Org Dashboard for Governance | A dashboard view is requred for Org Leaders to see all compliance outages in one place -> owning org in Mega | 2018-12-27 |  | 11 - On-hold | Moved to on hold. DG 1/21 - I wonder if this is really needed, because the mass upload template is what people really need. [TW 12/27] Confirmation in week of Jan 15 with IT Asset Governance Owners (BW 12/19: tracking by site SSL view will go away)
App-17 | Security | Delegation | Allow for each Organization to assign a person (on top of the Organization Leader) who has full visibility to all organizations application assets. Setup delegate per Organization (not per organizatuíon leader; allow one delegate to be setup as delegate for multiple organizations) See App-17 for config table design | 2019-02-21 | Initial | 95 - Closed (Cancelled) | no longer relevant due to secuirty release to all. tbc which UAT will have this functionality [TW 2/18] Propose to maintain in Excel file on SP, manual sent through SFTP by Tanja (BW 12/19) changed vs. Previous implemenation: modified to remove the Organization Leader assignment as a requirement for assigning a delegate
App-18 | Security | Owning Org View Restriction | L0, L1, L2, L3 Org Leaders can see all applications mapped to owning organizations in their hierarchy | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | OK.
App-19 | Report: Org | Registration Compliance - Org Views | Compliance reports across all metrics shall exist for management to see major outages and overall compliance per site (required for PS, R&D) - following Hardware Model | 2018-12-27 |  | 95 - Closed (Cancelled) | OK. (BW 12/19: tracking by site SSL view will go away)
App-21 | Security | Security | Only ITAM members and defined functional Stakeholders (per group genie "IT Asset Admin") can see everything for P&G. Only members of Org Leader (= org leaders and delegates) group genie can see scopes of applications by owning organization. | 2018-12-27 | Initial | 95 - Closed (Cancelled) | no longer relevant due to security release to all.
App-22 | Usability | Table visuals column sort order for all views | The tables should be sorted by application name, and should list all columns in the sequence defined in AGF 3.0 metric -> App-49 | 2019-02-19 | Initial | 70 - Unit Tested (for UAT) | Agree.
App-23 | Report: All | Filters/slicers | Allow to use L0,L1,L2, L3 Org Leaders and Org Names as filters or for drill down in all compliance reports. | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | DG 1/21 - I think this makes sense even for SPOCs. tbc. - only needed for IT Asset Admin and Owning org
App-24 | Report: IT Asset Admin | Top Compliance Gaps | Provide perspective to the functional Stakeholders on key gap areas (per attribute, sorted by % of outages top down) | 2018-12-27 | Initial, Prio 2 | 11 - On-hold | DG 1/21 - Agree. This makes sense if in tabular view for IT Asset Admin (BW 12/19) we have not used this to drive compliance per field; low priority
App-25 | Usability | Column Naming Consistency in all views | Name columns as per AGF 3.0 | 2018-12-27 | Initial | 70 - Unit Tested (for UAT)
App-26 | Metric | Validation Metric listing Instances | need to add comma separated list of Instances - tbc how to measure | 2018-12-27 |  | 11 - On-hold | to be confirmed - with Validation Owner
App-27 | Metric | Validation filter for Instances | Although we need an easy to use filter to remove/add the Applications of Type Instance from the scorecard, default is that Instances are not shown. When instances are not shows they also don't contribute to the measure. Each of the 4 measured attributes contribute 25% to the score per application | 2018-12-27 |  | 11 - On-hold | to be confirmed - with Validation Owner
App-28 | Usability | Table visuals percentage content | Show all percentage numbers as numbers with one decimal place (within table column and also in the metric.) | 2019-02-19 | Initial | 70 - Unit Tested (for UAT)
App-29 | Report: Individual | Individual Asset Owner View Design | Add a link/Help button How do I review my applications for compliance with URL https://pgone.sharepoint.com/sites/PG-ITAM/Shared%20Documents/ITAM/Apps/Trainings/How%20do%20I%20review%20my%20applications%20for%20compliance%20-%20Job%20Aid%20-%20Application%20Governance.pptx | 2018-12-27 | Intial-UAT2 | 70 - Unit Tested (for UAT) | Tanja to incorporate this into the Application Governance Help Page - accessible through the one info button
App-3 | Metric | Registration & Classification (Base) Metric | % of completed registrations see sheet App-1ff AGF 3.0 | 2019-02-19 | Initial | 70 - Unit Tested (for UAT)
App-30 | Report: All | Registered vs Targeted metrics/ UX | Initial view should show Registration (base) application compliance metric. Create separate "content" for targeted metrics to allow to navigate to EA, Validation, ... (tbc.) targeted metrics. | 2018-12-27 | Initial | 70 - Unit Tested (for UAT)
App-33 | Report: IT Asset Admin | Chart display of Registration Compliance Metric for Overall Stakeholder | Number of Applications and Registration Compliance % by Lifecycle status, potentially also by App nature | 2018-12-27 | Initial | 70 - Unit Tested (for UAT)
App-34 | Report: OwningOrg | Chart display of Registration Compliance Metric for Owning Og | Number of Applications and Registration Compliance % by owning organization - potentially consolidating "last" 10% into one "Others" group | 2018-12-27 | Initial | 11 - On-hold | stakeholder not convinced this is useful
App-36 | Report: IT Asset Admin? | Trend view | Trend of number of apps total, number of apps "removed", number of app new (removed is every app that is no longer meeting the filter criteria; so this can be deleted apps, or status changed to decommissioned or to not used, or tech nature changed) | 2018-12-27 | Release X | 20 - Submitted (for Review)
App-4 | Usability | EASE link | Provide link to EASE as a hyperlink URL (should be clickable!) composed of https://ease.pg.com/app.php?id=HEXID; example:https://ease.pg.com/app.php?id=C0D3C18747C20011 | 2018-12-27 | Initial | 70 - Unit Tested (for UAT)
App-5 | View | Registration and Target content separation | Use "Contents" to separate into multiple views | 2018-12-27 | Initial | 70 - Unit Tested (for UAT)
App-37 | Usability | Color Coding of Compliance Gaps in table visuals | all mandatory but missing documentation items (or with issues) must be marked in red | 2018-12-27 | Initial | 70 - Unit Tested (for UAT) | Yes.
App-6 | Metric | "Currentness" metric as part of Registration Metric - Last Reviewed Date | Last Reviewed Date: Details per sheet App-6 | 2019-02-19 | Initial | 70 - Unit Tested (for UAT)
App-38 | Report: Individual | Individual Asset Owner - Registration and Compliance - Content | see tabs App-1ff AGF 3.0 metric and App-10 - Asset Owner name | 2018-12-27 | Initial | 70 - Unit Tested (for UAT)
App-39 | Report: Individual | Individual Asset Owner - Registration and Compliance - Filters | see tabs App-1ff AGF 3.0 metric and App-10 - no slicers needed | 2018-12-27 | Initial | 70 - Unit Tested (for UAT)
App-40 | Report: Individual | Individual Asset Owner - Registration and Compliance - Details | see tabs App-1ff AGF 3.0 metric and App-10 - all mentioned columns | 2018-12-27 | Initial | 70 - Unit Tested (for UAT)
App-41 | Metric | Registration & Classification | distinguish by nature and lifecycle status | 2019-02-11 | Release X | 10 - New (Draft) | to be defined/ confirmed
App-42 | Report: all | App Owner Site slicer | For R&D and PS: Allow to filter base on Application Owners site | 2019-02-13 | Intial-UAT2 | 40 - Assigned to Tech Team | OK. get Person - Site relationship from SNOW!
App-43 | Integration | App Owner additional information | All data for app governance will be obtained from Mega, except the two: App Owner validity status as well as App Owner - Site mapping | 2019-02-13 | Intial | 70 - Unit Tested (for UAT)
App-45 | Report: PS | PS Applications Content | tbc | 2019-02-13 | Release X | 10 - New (Draft) | App Governance add-on for PS specific (tbc. Mike) - small enhancement in order to make use of the large capacity released for Vulnerabilities out of scope
App-46 | Report: PS | PS Applications Filters/ Slicers | tbc | 2019-02-13 | Release X | 10 - New (Draft) | App Governance add-on for PS specific (tbc. Mike) - small enhancement in order to make use of the large capacity released for Vulnerabilities out of scope
App-47 | Report: PS | PS Applications Metrics | tbc | 2019-02-13 | Release X | 10 - New (Draft) | App Governance add-on for PS specific (tbc. Mike) - small enhancement in order to make use of the large capacity released for Vulnerabilities out of scope
App-48 | Report: PS | PS Appliations Details | tbc | 2019-02-13 | Release X | 10 - New (Draft) | App Governance add-on for PS specific (tbc. Mike) - small enhancement in order to make use of the large capacity released for Vulnerabilities out of scope
App-49 | Report: All | Application Table Column Order | Most attributes of the old RITA report (App Governance Overall) should be followed, plus new attributes included in the metric (for details also in other views, see App-49 tab): Application Name Hex ID Average of Overall Registration Score Data Complete Data Correct Data Current P&G Application Owner Application Owner IntranedID App Owner Validity Missing Data Owning Organization Level 1 Owning Organization Level 1 Leader Owning Organization Level 2 Owning Organization Level 2 Leader Owning Organization Level 3 Owning Organization Level 3 Leader Last Reviewed Date Application/Technology Nature Life Cycle Status Application Description Data Classification Sox Classification Data Privacy Regulated System BIA Rating for Confidentiality BIA Rating for Integrity BIA Rating for Availibility Owning Organization Hosting Vendor Software Supplier Technology Supplier Service Operations Supplier Implementation Supplier Instance Link to EASE CREATOR CREATIONDATE | 2019-02-18 | Initial | 70 - Unit Tested (for UAT) | Requirement given by Donelle. We don't have the following which are desired as well (coming from Enterprise Directory): HR Function Org Type Employee Org (LDAP) the following attributes should come from SNOW, potentially from user table: App Owner Validity. See App-49 tab
App-6 | Metric | "Completeness" metric as part of Registration Metric - all mandatory fields | App-1ff tab | 2019-02-19 | Initial | 70 - Unit Tested (for UAT)
App-6 | Metric | "Correctness" metric as part of Registration Metric - App Owner Validity | App-1ff tab | 2019-02-19 | Initial | 70 - Unit Tested (for UAT)
App-50 | tbc | multiple Application Onwers case - how to handle | Tbc: what happens to Site if there is more than one App Owner assigned to an application | 2019-02-19 |  | 95 - Closed (Cancelled) | we will only get one distinct App Owner
App-51 | Report: All | new attribute in application details tables | "Application ID" which is the (new) unique ServiceNOw ID, will need to be displayed as part of the detials | 2019-03-06 | Intial-UAT2 | 40 - Assigned to Tech Team
App-52 | Security | Open Application Governance Reporting up for all P&Gers | Use employee status (P&G) as documented in SNOW sys_user tablE and SNOW role ecmdb_admin or cmdb_light for vendor resources, I to determine whether user is allowed to see application governance reports. Allow to see all application entries. affecting/ overwriting App-17,App-18, App-21 | 2019-03-13 | Intial-UAT2 | 40 - Assigned to Tech Team
App-54 | Default Filters | Filtering option for individual Application Owner | Easy to use and performant option to filter based on Application Owner name (required if we open all Application Governance up) | 2019-03-13 | Initial | 70 - Unit Tested (for UAT)
App-55 | Report: All | iRisk Multi BIA selection | see tab "App-12 iRisk calculation" | 2019-03-25 | Intial-UAT2 | 40 - Assigned to Tech Team
App-56 | Report: All | iRisk lifecycle status changes | see tab "App-12 iRisk calculation" | 2019-03-25 | Intial-UAT2 | 40 - Assigned to Tech Team

## App-1ff AGF 3.0 metric upd
https://pgone.sharepoint.com/:w:/r/sites/PG-ITAM/_layouts/15/Doc.aspx?sourcedoc=%7B787B7052-5D16-46ED-9136-FC21F98C2798%7D&file=AGF%203.0.docx&action=default&mobileredirect=true |  | Please take columns for details table from App-49 tab!
Registration --> Registration Completeness | Currentness | Data Ownership | Registration | iRisk | Legal-PII (REMOVE TAB NOT USED!) | IT Continuity (remove tab, not used, IT Continuity is already using Numerify) | Validation | Enterprise Architecture
Up to 15 Data Points are collected for each application; if a data point is a gap (failed the condition, it reduces the score by 1/15) | Last Reviewed Date (NO gap if newer than 12 months or NO gap if create date is newer than 12 months only one of these conditions needs to be true to PASS; Applies only to apps in Levergae/Optimize; in case of a gap show Last Modified Date in Missing Data; see also App-3) | Application owner is valid (SNOW flag) | =(1/3*Registration Completeness score) + (1/3*Currentness score) + (1/3*Data Ownership score)
filter: App/ Tech nature = [XOApp, App, XO Platf, Platf] AND Lifecycle status != Decommissioned !=not_used | filter: App/ Tech nature = [XOApp, App, XO Platf, Platf] AND Lifecycle status != Decommissioned !=not_used | filter: App/ Tech nature = [XOApp, App, XO Platf, Platf] AND Lifecycle status != Decommissioned !=not_used | filter: App/ Tech nature = [XOApp, App, XO Platf, Platf] AND Lifecycle status != Decommissioned !=not_used | filter: App/ Tech nature = [XOApp, App, XO Platf, Platf] AND Lifecycle status != Decommissioned !=not_used |  |  | filter: App/ Tech nature = [XOApp, App, XO Platf, Platf] AND and Regulated System=Yes AND Lifecycle status != Decommissioned !=not_used | filter: App/ Tech nature = [XOApp, App, XO Platf, Platf] AND Lifecycle status != Decommissioned !=not_used
PG Application owner
PG last Reviewed Date
Application Name |  |  |  | Application Name (show but don't measure) |  |  | Application Name (show but don't measure) | Application Name (show but don't measure)
Registration & Classification Score (number without decimal) |  |  |  | IT Risk Assessment Complete (eithe 0% or 100%) |  |  | Validation Data Complete (in percent, no decimal places) | Enterprise Architecture Data Complete (in percent, no decimal places)
Missing Data Registration & Classification (list of comma separated fields that have a gap) |  |  |  | iRisk Date (gap if blank for all applications where BIA Confidentiality OR BIA Availability OR BIA Integrity is High OR Very High OR blank OR Not Performed AND Lifecycle status not Discovery OR Retired; if gap score 0%; if iRisk date not blank always 100%; if blank but not a gap as per conditions put no score; see sheet App-iRisk calculation) |  |  | Missing Data Validation | Missing Data Enterprise Architecture
Owning Org level 0 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page |  |  |  | Owning Org level 0 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page |  |  | Owning Org level 0 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page | Owning Org level 0 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page
Owning Org level 1 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page |  |  |  | Owning Org level 1 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page |  |  | Owning Org level 1 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page | Owning Org level 1 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page
Owning Org level 2 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page |  |  |  | Owning Org level 2 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page |  |  | Owning Org level 2 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page | Owning Org level 2 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page
Owning Org level 3 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page |  |  |  | Owning Org level 3 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page |  |  | Owning Org level 3 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page | Owning Org level 3 (show only, derived from ITAM hierarch database view); add as a multi select slicer(filter) to the page
Owning Org level 1 leader (show only, derived from ITAM hierarch database view) |  |  |  | Owning Org level 1 leader (show only, derived from ITAM hierarch database view) |  |  | Owning Org level 1 leader (show only, derived from ITAM hierarch database view) | Owning Org level 1 leader (show only, derived from ITAM hierarch database view)
Owning Org level 2 leader (show only, derived from ITAM hierarch database view) |  |  |  | Owning Org level 2 leader (show only, derived from ITAM hierarch database view) |  |  | Owning Org level 2 leader (show only, derived from ITAM hierarch database view) | Owning Org level 2 leader (show only, derived from ITAM hierarch database view)
Owning Org level 3 (show only, derived from ITAM hierarch database view) |  |  |  | Owning Org level 3 (show only, derived from ITAM hierarch database view) |  |  | Owning Org level 3 (show only, derived from ITAM hierarch database view) | Owning Org level 3 (show only, derived from ITAM hierarch database view)
Owning Organization (gap if blank or multiple value or value not in list of valid applications (ITAM hierarchy database view; show comma separated list if more than one is connected as Owning Organization; if a gap show Owning Organization in Missing Data column) |  |  |  | Owning Organization |  |  | Owning Organization | Owning Organization
P&G Application Owner (gap if blank, or if SNow flag "invalid owner" is yes, if gap then show "P&G Application Owner" in column Missing Data) |  |  |  | P&G Application Owner |  |  | P&G Application Owner | P&G Application Owner
Application Owner intranet ID (e.g. wiechers.b); not measured; comma separated list of app owners if more than one app owner assigned |  |  |  | Application Owner intranet ID (e.g. wiechers.b); not measured; comma separated list of app owners if more than one app owner assigned |  |  | Application Owner intranet ID (e.g. wiechers.b); not measured; comma separated list of app owners if more than one app owner assigned | Application Owner intranet ID (e.g. wiechers.b); not measured; comma separated list of app owners if more than one app owner assigned
Site name is sderived from App Owner site name (display only, not part of metric; Site from SNOW) |  |  |  | SIte name is sderived from App Owner site name (display only, not part of metric; Site from Enterprise Directory of the linked Application Owner; if multiple app owners blank); add as a multi select slicer(filter) to the page | SIte name is sderived from App Owner site name (display only, not part of metric; Site from Enterprise Directory of the linked Application Owner; if multiple app owners blank); add as a multi select slicer(filter) to the page | SIte name is sderived from App Owner site name (display only, not part of metric; Site from Enterprise Directory of the linked Application Owner; if multiple app owners blank); add as a multi select slicer(filter) to the page | SIte name is sderived from App Owner site name (display only, not part of metric; Site from Enterprise Directory of the linked Application Owner; if multiple app owners blank); add as a multi select slicer(filter) to the page | SIte name is sderived from App Owner site name (display only, not part of metric; Site from Enterprise Directory of the linked Application Owner; if multiple app owners blank); add as a multi select slicer(filter) to the page
Last Reviewed Date (NO gap if newer than 12 months or NO gap if create date is newer than 12 months only one of these conditions needs to be true to PASS; Applies only to apps in Levergae/Optimize; in case of a gap show Last Modified Date in Missing Data; see also App-3) --> remove from Completeness. Part of Currentness score.
Application/Technology Nature |  |  |  | Application/Technology Nature (not measured, view only) |  |  | Application/Technology Nature (not measured, view only) | Application/Technology Nature (not measured, view only)
Life Cycle Status (gap if Undecided or blank; if Undecided or blank show "Life Cycle Status" in Missing Data column) |  |  |  | Life Cycle Status |  |  | Life Cycle Status | Life Cycle Status
Application Description (gap if blank; if blank show Application Description in Missing Data column) |  |  |  | Application Description |  |  | Application Description | Application Description
Data Classification (gap if blank; if blank show Data Classification in Missing Data Column) | [6 empty] | RAMP Date (not blank, if blank show RAMP Date in Missing Data column) | Business Process (not blank, if blank show Business Process in column Enterprise Architecture Data Complete, if more than one Business Process is assigned show a comma separated list)
Sox Classification (gap if blank; if blank show Sox Classification in Missing Data column) | [6 empty] | RAMP Location (not blank, if blank show RAMP Location in Missing Data column) | Standard (not blank)
Data Privacy (gap if blank with exception: blank is not gap if blank and Hosting = No Cloud: Locally Installed (Desktop) or No Cloud: Locally Installed (Mobile); also not a gap is nature is XOPlatform or Platform; not a gap if status is discovery; if a gap show Data Privacy in Missing Data column). Note: valid values are Low, Medium, High, No PII Data. |  |  |  | Data Privacy |  |  | Commissionning Memo Date Approved (not blank) if blank show Commissionning Memo Date Approved in missing data column) | License (not blank)
Regulated System (gap if blank with exception; blank is not a gap if status is Discovery; if blank show Regulated System in Missing Data column) | [6 empty] | Commissionning Memo Document Link (not blank, if blank show Commissionning Memo Document Link in missing data column) | Lead Solution Architect (not blank, if blank show Lead Solution Architect in column Enterprise Architecture Data Complete, if more than one Solution Architect is assigned show a comma separated list)
BIA Score for Confidentiality (gap if blank or Not Performed with exception: if status is discovery then blank or not performed is not a gap; if gap show BIA Rating for Confidentiality in Missing Data column) |  |  |  | BIA Score for Confidentiality |  |  |  | Data Retention Period (Actual policy which is in place)
BIA Score for Integrity (gap if blank or Not Performed with exception: if status is discovery then blank or not performed is not a gap; if gap show BIA Rating for Integrity in Missing Data column) |  |  |  | BIA Score for Integrity
BIA Score for Availability (gap if blank or Not Performed with exception: if status is discovery then blank or not performed is not a gap; if gap show BIA Rating for Availability in Missing Data column) |  |  |  | BIA Score for Availability
Hosting (gap if blank or None with exception: if status is discovery then blank or None is not a gap; if gap show; if blank show Hosting in Missing Data column)
Vendor Software Supplier (gap if blank, add as comma separated list if more than one; if gap show Vendor Software Supplier in Missing Data column) |  |  |  | Vendor Software Supplier
Release (comma separated list if more than one Release; not required in AGF 3.0)
Instance (gap if blank with exceptions; not a gap if Hosting contain SaaS or PaaS or No cloud: Locally Installed (Desktop) or No Cloud: Locally Installed (Mobile) or if Life Cycle Status is not Discovery/Requ. or Design/Build comma separated list if more than one Instance; if it is a gap show Instance in Missing Data column) Instance should be connected to the Release, which is connected to the Application. Or Instance should be connected directly to the Application.
Server (comma separated list if more than one Server; governance on server application connectivity moves to HW governance ad is not measured in App Governance)
Database (comma separated list if more than one Server; governance on server application connectivity moves to HW governance ad is not measured in App Governance) | [7 empty] | Hex ID (display only; not part of measure)
Hex ID (display only; not part of measure) |  |  |  | Hex ID (display only; not part of measure) |  |  | Hex ID (display only; not part of measure) | link to ease
link to ease |  |  |  | link to ease |  |  | link to ease | Created by (display only, shortname of person who created the object)
Created by (display only, shortname of person who created the object) |  |  |  | Created by (display only, shortname of person who created the object) |  |  | Created by (display only, shortname of person who created the object) | Created on (display only, date format)
Created on (display only, date format) |  |  |  | Created on (display only, date format) |  |  | Created on (display only, date format)
Technology Supplier - this will only be included in future completeness metric once this data requirement is deployed to all organizations
Service Operations Supplier - this will only be included in future completeness metric once this data requirement is deployed to all organizations
Implementation Supplier - this will only be included in future completeness metric once this data requirement is deployed to all organizations
Subject Area Keyword? Whenever a keyword starts with "SA:"
Note on F11: wiechers.b: 100% if not blank 0% if blank

## App-12 iRisk calculation
Filter/ metric update 03/26:
YES (compliant) - if iRisk date column is populated
NO (non-compliant) - if iRisk date column is blank and lifecycle status !=[decom, not-used, retired, Sunset] | note that discovery is in and sunset is out!
n/a - if iRisk date column is blank and lifecycle status is one of [decom, not-used, retired, Sunset] | note that discovery is in and sunset is out!
Filter/ selection update 03/26:
Need a combined BIA function to see application BIA level across all three(Confidentiality/Integrity/ Availability) BIA categories.
For example, if an application has a high or very high for the C or the I or the A, it should be selectable with one filter click.
The excel logic below allows me to see this information for applications that have a “High” or “Very High” across the C or the I or the A:
= IF(OR([@[BIA Rating for Confidentiality]]="high",[@[BIA Rating for Confidentiality]]="very high",[@[BIA Rating for Integrity]]="high",[@[BIA Rating for Integrity]]="very high",[@[BIA Rating for Availibility]]="high",[@[BIA Rating for Availibility]]="very high"), "Yes", "No")
This is the flexibility that is needed for reviewing compliance for applications that are classified as critical.
Critical applications = Applications that have a “High” or “Very High” in the BIA for C or I or A.

## App-17 Delegate
Group Genie "orgleader" defines whether I am generally allowed to see application "scope"
what data I can see, depends on where I am assigned as organization leader.
(Mega: organization leader -> ownng organization ->application)
PGV_APP_RESPONSIBLE_ORG_PERSON
PGV_ORG_ITAM_GBS
alternatively - what data I can see, depends on which owning org I am mapped to as a delegate (config table)
Config Table will look like this
L1 Org | Delegate Name
Consumer Services | kremer.s
FSS | onguc.h
will most likely be L1 - but be prepared for later changes to also add L0 , L2, L3 organization delegates | needs to be unique, so might use IntranetID instead of Full Name

## App-49 table details
List of Attributes for Reigstration View | Source | List of Attribute For Enterprise Architecture View | List of Attribute For Validation View | List of Attribute For iRisk View
Application Name | Mega | Application Name | Application Name | Application Name
Application ID | Mega (new column!) | Application ID | Application ID | Application ID
Hex ID | Mega | Hex ID | Hex ID | Hex ID
Average of Overall Registration Score | calculated, see tab App-1ff | Average of EA Data Complete | Average of LV Data Complete | IT Risk Assessment Completeness
Data Complete | calculated, see tab App-1ff | P&G Application Owner | P&G Application Owner | P&G Application Owner
Data Ownership | calculated, see tab App-1ff | Application Owner IntranedID | Application Owner IntranedID | Application Owner IntranedID
Data Current | calculated, see tab App-1ff | EA Missing Data | Validation Missing Data | iRisk Date
P&G Application Owner | Mega | License | RAMP Date | Owning Organization
Application Owner IntranedID | Mega | Lead Solution Architect | RAMP Location | Organization Level 1
App Owner Validity (y/n) | derived from SNOW sys_user attributes u_employee_type and active | Business Process | Commissionning Memo Date Approved | Owning Organization Level 1 Leader
Missing Data | consolidated (gaps), see tab App-1ff [of the 19 attributes, only those which have a gap] | Application/Technology Nature | Commissionning Memo Document Link | Owning Organization Level 2
Owning Organization Level 1 | Mega | Life Cycle Status | Instance | Owning Organization Level 2 Leader
Owning Organization Level 1 Leader | Mega | Owning Organization | Owning Organization | Owning Organization Level 3
Owning Organization Level 2 | Mega | Owning Organization Level 1 | Owning Organization Level 1 | Owning Organization Level 3 Leader
Owning Organization Level 2 Leader | Mega | Owning Organization Level 1 Leader | Owning Organization Level 1 Leader | BIA Rating for Confidentiality
Owning Organization Level 3 | Mega | Owning Organization Level 2 | Owning Organization Level 2 | BIA Rating for Integrity
Owning Organization Level 3 Leader | Mega | Owning Organization Level 2 Leader | Owning Organization Level 2 Leader | BIA Rating for Availibility
Last Reviewed Date | Mega | Owning Organization Level 3 | Owning Organization Level 3 | Vendor Software Supplier
Application/Technology Nature | Mega | Owning Organization Level 3 Leader | Owning Organization Level 3 Leader | Data Privacy
Life Cycle Status | Mega | Standard | Application/Technology Nature | Application/Technology Nature
Application Description | Mega | Data Retention Period (Actual policy which is in place) | Life Cycle Status | Life Cycle Status
Data Classification | Mega | Data Classification | Link to EASE | Link to EASE
Sox Classification | Mega | Data Privacy | CREATOR | CREATOR
Data Privacy |  | iRisk Date | CREATIONDATE | CREATIONDATE
Regulated System |  | Keyword-Subject Area
BIA Rating for Confidentiality |  | Link to EASE
BIA Rating for Integrity |  | CREATOR
BIA Rating for Availibility |  | CREATIONDATE
Owning Organization
Hosting
Vendor Software Supplier
Technology Supplier
Service Operations Supplier
Implementation Supplier
Instance
Link to EASE
CREATOR
CREATIONDATE
Note on D9: Pinaki: KPI To be shown in Dashboard
Note on D10: Pinaki: KPI To be shown in Dashboard
Note on E10: Pinaki: KPI To be shown in Dashboard
Note on E11: Pinaki: KPI To be shown in Dashboard
Note on E12: Pinaki: KPI To be shown in Dashboard
Note on D21: Pinaki: KPI To be shown in Dashboard

## App-6 Last Reviewed Date
create date | last reviewed date | what to write to Gap column | score in % current
not older 12 months | older than 12 months | not a gap - show neither Last Reviewed nor Create Date in Gap column | 100
not older 12 months | not older 12 months | not a gap - show neither Last Reviewed nor Create Date in Gap column | 100
not older 12 months | blank | not a gap - show neither Last Reviewed nor Create Date in Gap column | 100
older than 12 months | older than 12 months | is a gap - show in Gap column: Last Reviewed date | 0
older than 12 months | blank | is a gap - show in Gap column: Last Reviewed date | 0
older than 12 months | not older 12 months | not a gap - show neither Last Reviewed nor Create Date in Gap column | 100

## App-10
Applied filter/ slicer: Asset Owner Name! |  |  | show in 4 tabs instead of one, one tab per metric
Metrics % Compliance (consolidate across all owned applications for this perso)n: | Registration Compliance | iRisk Compliance | Validation Compliance | Enterprise Architecture Compliance
Details Table: |  |  | % compl/ color coded | % compl/ color coded | % compl/ color coded | % compl/ color coded | gaps highlighted (registration in red, others in yellow?)
| Application Name | HexID | Registration | iRisk | Validation | Enterprise Architecture | ... List of attributes...
old content below as inspiration but no longer valid
This requrement is not 100% valid anymore-updates to this requrement have been documented in sheet Req
| Persona: Application Owner | [10 empty] | latest Azure implementation to checked -> myRITA.pg.com!
Use Case:
have visibility on compliance of all owned items
-> see list of owned applications and for each of them what items are missing to get compliant
| Ideas (initial July 2018): | For application managers only applications assigned to them can be visible for compliance position
Per application they own, show score per applicable compliance and color code; compliance which is not applicable show N/A
Show all columns which are black in sheet AGF 3.0 metric per application and the respective value
Release column is a comma separated list of values, in case there is more than one value per application
Instance column is a comma separated list of values, in case there is more than one instance (Viha is already working on such a field for one of the governance scorecards)
Physical Database (Instance) is a comma separated list of values, in case there is more than one ...
Server (Instance) is a comma separated list of values, ....
+comma separated lists for all 1:m attributes
column Request data updates (via free text) with link to https://ease.pg.com/app.php?id=<hex id>, for example https://ease.pg.com/app.php?id=C0D3C18747C20011
Since thee are many attributes (columns) per application allow to hide / unhide the attribute details
Assume that an Application Owner usually own more than one Application
Filter is all applications where logged in person is Application Owner and App/ Tech nature = [XOApp, App, xO Platf, Platf] (don't remove decommissioned); but decomissioned applications ONLY require a decomission date (to be compliant, see Enterprise Architecture Documentation)
Sort alphabetically but 1st !=Decommissioned the the Decommissioned
Titel of columns with naming convention <scorecard><measure>; only Registration and Classification has 4 columns
Allow to hide the columns which are marked in blue; when page is opened the deault is that all 3 columns are hidden (like a group in excel)
Allow to hide the columns which are marked in orange; when page is opened the deault is that all attribute columns are hidden (like a group in excel), we expect 50+ columns, some with a comma separated value list, see definition of measured attributes per compliance scorecard; don't color the values
Sort attributes (orange columns per compliance area)
All scores without decimal places
Example
|  | Registration&Classification Compliance (in %) | Registration&Classification Complete (in %) | Registration&Classification Current (in %) | Registration&Classification Correct (in %) | Risk AssessmentComplete (in %) | Regulated Complete (in %) | Architecture Complete (in %) | Gaps for Registration&Classification | Gaps for Risk Assessment | Gaps for Regulated | Gaps for Architecture | Request data updates (via free text) | Request data updates (via appupdates.pg.com) | <name of attribute 1> | <name of attribute 2> | <name of attribute 3> | <name of attribute x>
|  | 66 | 100 | 0 | 100 | 100 | N/A | 100 | comma separated list of measured attributes | comma separated list of measured attributes, only show if the app is in scope of the RISK assessment, else show N/A | comma separated list of measured attributes, only show if the app is in scope of the Reglated Doumentation, else show N/A | comma separated list of measured attributes, only show if the app is in scope of the Enterprize Architecture assessment, else show N/A | Request data updated (via button in EASE) (hyperlink)https://ease.pg.com/app.php?id=<hex id> | Request updates via App Update (hyperlink http://appupdates.pg.com) | actual attribute value 1, or comma separated list of values if 1:m | actual attribute value 2, or comma separated list of values if 1:m | actual attribute value 3, or comma separated list of values if 1:m | actual attribute value x, or comma separated list of values if 1:m
Application Name
MEGA

## Hardware
Item # | Category | Requirement | Details | Upd Date | Release | Status | Comment
HW-1 | Entry Page | HW Compliance Metrics to be displayed (metrics and trends) | #Registered Devices, #Active Devices, % Ownership Accuracy, % Site Accuracy |  | Initial | 40 - Assigned to Tech Team
HW-2 | Metric | Total Active Devices (Lifecycle Status = Active) | https://pgone.sharepoint.com/:u:/r/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx?csf=1&e=jS4V9h |  | Initial | 40 - Assigned to Tech Team
HW-3 | Metric | Total Registered Devices (Lifecycle Status is NOT duplicate/invalid not used/reference) | https://pgone.sharepoint.com/:u:/r/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx?csf=1&e=jS4V9h |  | Initial | 40 - Assigned to Tech Team
HW-4 | Metric | % Lifecycle Status availability (Lifecycle Status = NOT empty) | https://pgone.sharepoint.com/:u:/r/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx?csf=1&e=jS4V9h |  | Initial | 40 - Assigned to Tech Team
HW-5 | Metric | % Lifecycle Status accuracy (One in link is still accurate) | https://pgone.sharepoint.com/:u:/r/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx?csf=1&e=jS4V9h |  | Initial | 40 - Assigned to Tech Team
HW-6 | Metric | % Ownership Accuracy: % of devices where Owner = active P&G employee [owned by.active = TRUE and owned by.employee type = employee] | https://pgone.sharepoint.com/:u:/r/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx?csf=1&e=jS4V9h |  | Initial | 40 - Assigned to Tech Team
HW-7 | Metric | % Site Accuracy. Refer to D | https://pgone.sharepoint.com/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx. Count as "bad" also location = ALL LOCATIONS |  | Initial | 40 - Assigned to Tech Team
HW-8 | Metric -> Details | Unregistered Devices (# unr/ % reg) | Shows table containing list of unregistered devices with values in any of the following columns: Device Name, NetBIOS Name, DNS Name, Mac Addess, Serial Number. Table should also contain the following columns. Site Code, OS information, IP Address. |  | Initial | 40 - Assigned to Tech Team
HW-9 | Metric -> Details | Unregistered Devices on Disposal watchlist (# unr/ % reg) | Shows table containing list of unregistered devices, with values in any of the following columns: Device Name, NetBIOS Name, DNS Name, Mac Addess, Serial Number. Table should also contain the following columns. Site Code, OS information, IP Address. [Add filter Where Last Seen > 90 days.] |  | Initial | 40 - Assigned to Tech Team
HW-10 | Metric -> Details | Unregistered Devices: Scanning data to be sourced from Tenable. Update calculation logic of existing KPIs. | Site Security Leaders 1. Derived Manufacturer from MAC address 2. Tenable estimated device_type 3. Determine if the device is wired or wireless. If wired, derive switch and port |  | Later Release | 11 - On-hold | To be reviewed.
HW-11 | Metric -> Details | Registered Devices. Show table... | KPI Trends |  | Initial | 40 - Assigned to Tech Team
HW-12 | Metric -> Details | Active Devices. Show table... | Active Devices |  | Initial | 40 - Assigned to Tech Team
HW-13 | Metric -> Details | #Devices with Vulnerabilities by Criticality. Show table... | Devices with Vulnerabilities |  | Initial | 40 - Assigned to Tech Team
HW-14 | Metric -> Details | % Ownership. Show table where the ownership score is 0. | Shows table containing list of devices with blank Primary Device Owners. Table columns consist of Device Name, Primary Device Owner, Site Code, Device Type, Lifecycle Status. |  | Initial | 40 - Assigned to Tech Team
HW-15 | Metric -> Details | % Site Accuracy. Show table where the site accuracy score is 0. | Shows table containing list of devices with blank Site Code. Table columns consist of Device Name, Primary Device Owner, Site Code, Device Type, Lifecycle Status. (Applicable for reports to Integrators only) |  | Initial | 40 - Assigned to Tech Team
HW-16 | Metric -> Details | % Lifecycle Status Accuracy | Shows table containing list of devices with incorrect Lifecycle Status. Table columns consist of Device Name, Lifecycle Status, Last Seen on Network, Primary Device Owner, Site Code, Device Type. https://pgone.sharepoint.com/sites/PG-ITAM/Pages/RITA-ReportHelp/HW-compliance.aspx |  | Initial | 40 - Assigned to Tech Team
HW-17 | Reports | Views for specific user groups | Notes: some of the views (Pages) are visbile for all parties, some are visible only for some! |  | Initial | 40 - Assigned to Tech Team
HW-18 | Reports | Table containing list of all devices and all the attributes associated to them.: Can be downloadable Excel or Workbook. | Can the download allow the user to choose the fields for download, even beyond what is immediately visible on the report. |  | Initial | 40 - Assigned to Tech Team
HW-19 | Reports | Drill-down capabilities | Drill down to devices - with gaps on Site Code and Ownership. - with gaps on Lifecycle Accuracy. - that are unregistered. - that are not "managed" |  | Initial | 40 - Assigned to Tech Team
HW-20 | Report: IT Asset Admin | Overall View - Content | summary # devices by assignment group, page-level preset filter to be specified, per code: Is Member is True Current Record is Y End Date top 1 by Latest End Date IsRegistered is 1 Is Accountable is True Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 40 - Assigned to Tech Team
HW-21 | Report: IT Asset Admin | Overall View - Filters | Site, Assignment Group, Region, Area, Country, Lifecycle Status |  | Initial | 40 - Assigned to Tech Team
HW-22 | Report: IT Asset Admin | Overall View - Displayed Metrics | # Active Devices, % Site Accuracy, % Lifecycle Status Accuracy, % Ownership Accuracy, % Unregistered Devices |  | Initial | 40 - Assigned to Tech Team
HW-23 | Report: IT Asset Admin | Overall View - Details | Assignment Group Site Name Security Lead Total Active Devices % Site Accuracy % Ownership % Lifecycle Status Accuracy # Unregistered Devices, # Registered Devices, # Total Active Devices, # Managed Devices, # Non-Managed Devices |  | Initial | 40 - Assigned to Tech Team
HW-24 | Report: SSL | SSL Global View - Content - reapply the preset filters in PowerBI | summary # devices per authorized assignment groups, by site/ region, page-level preset filter to be specified |  | Initial | 40 - Assigned to Tech Team
HW-25 | Report: SSL | SSL Global View - Filters | Current Record is Y Calendar Date top 1 by Latest Calendar Date Region is not (Blank) Is Accountable is True Lifecycle Status is Installed |  | Initial | 40 - Assigned to Tech Team
HW-26 | Report: SSL | SSL Global View - Details Chart | Chart - clickable map |  | Initial | 40 - Assigned to Tech Team | can be dropped if not available
HW-27 | Report: SSL | SSL Global View - Details | Parent Location, # Total Active Devices, % Registered Devices, % Managed, % Ownership, # devices with critical vulnerabilities |  | Initial | 40 - Assigned to Tech Team
HW-28 | Report: All | Device Details - Content | device details per authorized assignment groups, page-level preset filter to be specified, per code: End Date top 1 by Latest End Date Is Registered is 1 Assignment Group is not (Blank) Is Accountable is True Hardware Status is not duplicate_invalid or decommissioned |  | Initial | 40 - Assigned to Tech Team
HW-29 | Report: All | Device Details - Filters | Site, Hardware Status, Device Type, Department, Assignment Group |  | Initial | 40 - Assigned to Tech Team
HW-30 | Report: All | Device Details - Link | downloadable CSV (for IT Asset Admins onyl with large content) |  | Initial | 40 - Assigned to Tech Team
HW-31 | Report: All | Device Details - Details - allow users to choose what fields to show in the table | Device Name, Site Name, Site Code, Device Owner, Device Type, DNS Name, MAC Address, Hardware Status, Last Seen, Assignment Group, Discovery Source, ACWL Status, Snow ID, PG Asset ID, Operating System, Service Pack |  | Initial | 40 - Assigned to Tech Team
HW-32 | Report: All | All Devices on Site - Content | devices details (for Sites - not only per authorized assignment groups but including asset-type specific assignment group devices linked to SSL Site scope), potential additional page-level preset filter to be specified, per code: End Date top 1 by Latest End Date Is Registered is 1 Assignment Group is not (Blank) Is ITAM Assignment Group is True Hardware Status is not duplicate_invalid or decommissioned |  | Initial | 40 - Assigned to Tech Team
HW-33 | Report: All | All Devices on Site - Filters | Site, Hardware Status, Device Type, Department, Assignment Group |  | Initial | 40 - Assigned to Tech Team
HW-34 | Report: All | All Devices on Site - Details - allow users to choose what fields to show in the table | Device Name, Site Name, Site Code, Device Owner, Device Type, DNS Name, MAC Address, Hardware Status, Last Seen, Assignment Group, Discovery Source, ACWL Status, Snow ID, PG Asset ID, Managed? |  | Initial | 40 - Assigned to Tech Team
HW-35 | Report: All | All Devices on Site - Link | downloadable CSV (for IT Asset Admins onyl with large content) |  | Initial | 40 - Assigned to Tech Team
HW-36 | Report: All | Active Devices - Content | devices details per authorized assignment groups, potential additional page-level preset filter to be specified, per code: Hardware Status is installed End Date top 1 by Latest End Date Is Registered is 1 Assignment Group is not (Blank) Is Accountable is True Hardware Status is not duplicate_invalid or decommissioned |  | Initial | 40 - Assigned to Tech Team
HW-37 | Report: All | Active Devices - Filters | Site, Hardware Status, Device Type, Department, Assignment Group, Country, Region, Area |  | Initial | 40 - Assigned to Tech Team
HW-38 | Report: All | Active Devices - Details | Device Name, Site Name, Site Code, Device Owner, Device Type, DNS Name, MAC Address, Hardware Status, Last Seen, Assignment Group, Discovery Source, ACWL Status, Snow ID, PG Asset ID, Serial Number, Managed? |  | Initial | 40 - Assigned to Tech Team
HW-39 | Report: All | Ownership Gaps - Content | devices without valid assigned owner (=Active P&G Employee) per authorized assignment groups, potential additioanl page-level preset filter to be specified, per code: Owner Accuracy Score is 0 Current Record is Y IsRegistered is 1 Assignment Group is not (Blank) Is Accountable is True Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 40 - Assigned to Tech Team
HW-40 | Report: All | Ownership Gaps - Filters | Site, Hardware Status, Device Type, Department, Assignment Group, Country, Region, Area |  | Initial | 40 - Assigned to Tech Team
HW-41 | Report: All | Ownership Gaps - Details | Device Name, Device Type, Discovery Source, Assignment Group, Device Owner, Employee Type, HR Status ID, Site Name, Site Code, Hardware Status, last seen, Snow ID, PG Asset ID, Serial Number |  | Initial | 40 - Assigned to Tech Team
HW-42 | Report: All | Site Code Gaps - Content | devices without valid assigned site (see HW-7) per authorized assignment groups, potential additioanl page-level preset filter to be specified, per code: Site Accuracy Score is 0 Current Record is Y IsRegistered is 1 Assignment Group is not (Blank) Is Accountable is True Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 40 - Assigned to Tech Team
HW-43 | Report: All | Site Code Gaps - Filters | Site, Hardware Status, Device Type, Department, Assignment Group, Country, Region, Area |  | Initial | 40 - Assigned to Tech Team
HW-44 | Report: All | Site Code Gaps - Details | Device Name, Device Owner, Assingment Group, Discovery Source, Site Name, Site Code, Site Type, Status, Device Type, Hardware Status, last seen, Snow ID, PG Asset ID, Serial Number |  | Initial | 40 - Assigned to Tech Team
HW-45 | Report: All | Inaccurate Lifecycle Status - Content | devices without valid assigned Hardware Status? (Based on Row 5) per authorized assignment groups, potential additioanl page-level preset filter to be specified, per code: Lifecycle Status Score is 0 Current Record is Y IsRegistered is 1 Network Connected is not no Assignment Group is not (Blank) Is Accountable is True Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 40 - Assigned to Tech Team
HW-46 | Report: All | Inaccurate Lifecycle Status - Filters | Site, Hardware Status, Device Type, Department, Assignment Group, Country, Region, Area |  | Initial | 40 - Assigned to Tech Team
HW-47 | Report: All | Inaccurate Lifecycle Status - Details | Device Name, Device Type, Assignment Group, Discovery Source, Device Owner, Site Name, Site Code, Hardware Status, last seen, Snow ID, PG Asset ID, Serial Number |  | Initial | 40 - Assigned to Tech Team
HW-48 | Report: All | Lifecycle Status not available - Content | devices without any assigned Hardware Status (status = blank) per authorized assignment groups, potential additioanl page-level preset filter to be specified, per code: Hardware Status is (Blank) Current Record is Y IsRegistered is 1 Assignment Group is not (Blank) Is Accountable is True Lifecycle Status is not duplicate_invalid or decommissioned |  | Initial | 40 - Assigned to Tech Team
HW-49 | Report: All | Lifecycle Status not available - Filters | Site, Hardware Status, Device Type, Department, Assignment Group, Country, Region, Area |  | Initial | 40 - Assigned to Tech Team
HW-50 | Report: All | Lifecycle Status not available - Details | Device Name, Device Type, Assignment Group, Discovery Source, Device Owner, Site Name, Site Code, Hardware Status, last seen, Snow ID, PG Asset ID, Serial Number |  | Initial | 40 - Assigned to Tech Team
HW-51 | Report: All | Unregistered Devices - Content | devices that can't be mapped to CMDB (sourced from scanning solution), potential additional page-level preset filter to be specified, per code: Is Registered is 0 End Date top 1 by Latest End Date Lifecycle Status is not duplicate_invalid or decommissioned Last Seen < 90 days DNS name or MAC address available Need to have logic that prevents mapping of empty dscovered DNS names to a CI with blank name in SNOW. |  | Initial | 40 - Assigned to Tech Team
HW-52 | Report: All | Unregistered Devices - Filters | Site, Country, Region, Area |  | Initial | 40 - Assigned to Tech Team
HW-53 | Report: All | Unregistered Devices - Details | DNS Name, Site Name, Site Code, MAC Address, IP Address, OS Description, Tenable Discovery ID, Last Scan Date |  | Initial | 40 - Assigned to Tech Team
HW-54 | Report: All | KPI Trends - Content | n/a - filtes applied to each chart |  | Initial | 40 - Assigned to Tech Team
HW-55 | Report: All | KPI Trends - Filters | Site, Assignment Group, Country, Region, Area, Lifecycle status |  | Initial | 40 - Assigned to Tech Team
HW-56 | Report: All | KPI Trends - Details | trendline charts for #/%Unregistered Devices, %Registered Devices, % site accuracy, % ownership accuracy, % Lifecycle status accuracy, # non- managed, %Managed, #Active Devices |  | Initial | 40 - Assigned to Tech Team
HW-57 | Report: All | Managed Devices - Content | Devices falling into the following classes which cannot be found in the following Discovery Sources: Classes: - Windows Server - Computer - Laptop PC - Desktop PC - Smartphone - Tablet Discovery Source: - AUCMDB - Interstates - MARIMBA - Airwatch End Date top 1 by Latest End Date Assignment Group is not (Blank) Network connected is not NO Hardware Status is Installed | 2019-03-05 | Initial | 40 - Assigned to Tech Team | adjusted based on alignment with Mike
HW-58 | Report: All | Managed Devices - Filters | Site, Hardware Status, Device Type, Device Owner, Discovery Source |  | Initial | 40 - Assigned to Tech Team
HW-59 | Report: All | Managed Devices - Details | Device Name, Site Name, Site Code, Device Owner, Discovery Source, Device Type, OS Description, Hardware Status, Snow ID, PG Asset ID, Assignment Group |  | Initial | 40 - Assigned to Tech Team | Show Assignment group as well.
HW-60 | Report: All | Unregistered Devices Disposal watchlist - Content | devices without assignment group (sourced from scanning solution), potential additional page-level preset filter to be specified, per code: Is Registered is 0 End Date top 1 by Latest End Date Lifecycle Status is not duplicate_invalid or decommissioned Last Seen > 90 days DNS name or MAC address available |  | Initial | 40 - Assigned to Tech Team
HW-61 | Report: All | Unregistered Devices Disposal watchlist - Filters | Site, Country, Region, Area |  | Initial | 40 - Assigned to Tech Team
HW-62 | Report: All | Unregistered Devices Disposal watchlist - Details | DNS Name, Site Name, Site Code, MAC Address, IP Address, OS Description, Tenable Discovery ID, Last Scan Date |  | Initial | 40 - Assigned to Tech Team
HW-63 | Report: SSL | Global View with Site and Integrators as Filter. Follow the one existing in PowerBI. | Table view with all KPIs at a Global level, and Site and Integrators as Filter. |  | Initial | 40 - Assigned to Tech Team | The map can be dropped if not available
HW-64 | Report: SSL | Site View with Assignment Group as Filter. All Devices on Site report. | Table view with all KPIs at a Site level, and Integrators as Filter. |  | Initial | 40 - Assigned to Tech Team
HW-65 | Security | Delete removed SNOW Assignment Group managers/ members from RITA | RITA CR 217 |  | Initial | 40 - Assigned to Tech Team
HW-66 | Pre-defined filter | Ignore deleted SNOW CI records in ALL calculations | RITA CR 204 |  | Initial | 40 - Assigned to Tech Team
HW-67 | Pre-defined filter | Exclude unregistered devices where OS = "HP ILO" | RITA CR 203 |  | Initial | 40 - Assigned to Tech Team
HW-68 | Report: SSL | Change in device visibility for sites: do not include asset-type specific assignment group devices in metrics, but display them in "all devices on site" report | RITA CR 188 |  | Initial | 40 - Assigned to Tech Team | tbc: how to distinguish accountable vs visible
HW-69 | Report Content | Redesign of the unregistered device | RITA CR 195 |  | Initial | 40 - Assigned to Tech Team
HW-70 | Report: SSL | Global View: Red/Yellow/Green color coding | RITA CR 229 |  | Initial | 40 - Assigned to Tech Team
HW-71 | Security | Process change to map R&D/PS Security Lead Team Members to individual Assignment Groups instead of using RITA-Admin | RITA CR 224 |  | Initial | 95 - Closed (Cancelled) | no longer relevant with security release
HW-72 | Report Content | Add Adapt asset tag to report page table details | RITA CR 141 |  | Initial | 40 - Assigned to Tech Team
HW-73 | Report Content | Add Operating System, OS Version, Service Pack in Device Details table view of the SSL App | RITA CR 245 |  | Initial | 40 - Assigned to Tech Team
HW-74 | Report: SSL | Registered Devices - Content | remove -> content in KPI trends |  |  | 95 - Closed (Cancelled)
HW-75 | Report: SSL | Registered Devices - Filters | remove -> content in KPI trends |  |  | 95 - Closed (Cancelled)
HW-76 | Report: SSL | Registered Devices - Displayed Metrics | remove -> content in KPI trends |  |  | 95 - Closed (Cancelled)
HW-77 | Report: SSL | Registered Devices - Details | remove -> content in KPI trends |  |  | 95 - Closed (Cancelled)
HW-78 | Report: All | Unregistered Devices/ U.D. Disposal watchlist - Device Type Calculated | add "Calculated Device Type" column, calculated from DNS Name or MAC Address |  | Release X | 10 - New (Draft) | to be specified how - DG
HW-79 | Report Content | Align HW status values with LC status values | RITA CR 252 |  | Release X | 10 - New (Draft) | Change in SNOW first
HW-80 | Report Content | Missing Site Code in Infoblox report - reflect in Report | RITA CR 223 |  | Release X | 10 - New (Draft) | Infoblox dependency
HW-81 | Dashboard | Overal BU Leader Dashboard (currently manual) integrated in NumeRITA | tbc |  | Release X | 10 - New (Draft) | waiting for requirements
HW-82 | Report Content | How to make the UnRegistered Devices Report more useful - Utilize IP range description in BT IP file to provide more clues in unregistered device identification | RITA CR 165 |  | Later Release | 11 - On-hold | other pre-requisites to be met
HW-83 | Report Content | For devices with Static IP, use IP address as an identification method. | RITA CR 148 |  | Later Release | 11 - On-hold | On hold due to infoblox migraiton
HW-84 | Report Content | Merge EPO data into unregistered device report | RITA CR 144 |  | Later Release | 11 - On-hold | We dont pull EPO data
HW-85 | Report Content | How to treat inconsistent Tenable Data for Devices? | RITA CR 208 |  | Later Release | 11 - On-hold | Tenable change in the first place
HW-86 | Integration | Registered Device source | SNOW |  | Initial | 40 - Assigned to Tech Team
HW-87 | Integration | Asset Owner Validity Status | SNOW |  | Initial | 40 - Assigned to Tech Team
HW-88 | Integration | EVP source | EVP report |  | Initial | 95 - Closed (Cancelled)
HW-89 | Integration | Site Mapping | Infoblox report |  | Initial | 40 - Assigned to Tech Team
HW-90 | Metric -> Details | Managed | Non-Managed Devices Report: Shows table containing list of windows online devices not managaed: Table should contain the following columns. Device Name, Primary Device Owner, Site Code, Integrator, OS information., Assignment Group |  | Initial | 40 - Assigned to Tech Team
HW-91 | Device Details -> Content | Registered Device details | Add the 2 fields to the registered device table, to the right most part of the table: 1. FDA status / Regulated 2. IQ/OQ |  | Release X | 10 - New (Draft)
HW-92 | Report Logic | Remove IP address from unregistered device matching logic | Currently, we use IP address as a mechanism to match unregistered device. But since some sites are registering devices like laptops with IP address, this causes poor matches. |  | Release X | 10 - New (Draft)
HW-93 | Report Filters | Assignment Group - ITAM only | not valid | 2019-03-06 | Initial | 95 - Closed (Cancelled)
HW-94 | Report: Integrator | Show all unregistered devices to Integrators | Integrators should not only see devices from their Assignment group, but also devices which are not registered (scanned from Tenable) | 2019-03-13 | Initial | 95 - Closed (Cancelled) | Integrators will see all devices anyhow - security released. Filtering needs to be explained

## Report and Page Level Filters
For explanation on existing report and page level filters (PowerBI)
| Is Member is True | used to check whether a person can use the data in the report. It is checked if the person is in the given sites and assignment group. If they are, both filters are set to True. | that field Is Member checks whether a person is a manager for a given site and assignment group, or a member.
Is Accountable is True
| Current Record is Y | used to filter for the latest/ most recent documentation for a device (vs historic states) and that a device is counted only for its latest state, not multiple times - used to identify current records in the database for a specific device, sites and employee. [In PowerBI-RITA, we store the history of changes in the tables in the database using the time periods (Start Date and End Date). For current records, that is, those whose End Date equals today, we assign Current Record = 'Y'. For all other records that are not current Current Record = 'N'.]
End Date...
| Is Registered is 1 | used to filter for devices which are already registered in SNOW (exlcuding those which are only scanned and found in Tenable)
| Lifecycle Status is not duplicate_invalid or decommissioned | used to filter for active devices only
| Hardware Status is not duplicate_invalid or decommissioned | used to filter for active devices only
| AssignmentGroup is not (Blank) | used to filter only for devices which are assigned to an Assignment Group
| Is ITAM Assignment Group is True | used to filter only for devices which are assigned to an Assignment Group with "ITAM" in its name

## hw attributes data dict
Context | Attribute | Source System | Reference Table | Reference Attribute | Source Table | Source Attribute | Calculated/ Derived (how?)
Overall View | Assignment Group | SNow | sys_user_group | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | assignment_group | Assigned in SNOW based on discovery source
Overall View | Site Name | SNow | cmn_location | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | location | Complete list of values comes form cmn_location table
Overall View | Security Lead | SNow | sys_user_group | manager | sys_user_group | manager | Derived from the manager of the assignment group of the device
Overall View | Total Active Devices | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | N/A | Calculated as total # of devices with hardware_status = installed and lifecycle status <> decommissioned or duplicate_invalid
Global View | Parent Location | N/A | N/A | N/A | N/A | N/A | Field is not used. No values right now.
Device Details | Device Name | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | name
Device Details | Site Name | SNow | cmn_location | name | cmn_location | name
Device Details | Site Code | SNow | cmn_location | u_pg_site_code_002 | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | location
Device Details | Device Owner | SNow | sys_user | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | owned_by
Device Details | Device Type | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | sys_class_name
Device Details | DNS Name | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | fqdn
Device Details | MAC Address | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | mac_address
Device Details | Hardware Status | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | hardware_status
Device Details | Last Seen | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | last_discovered
Device Details | Assignment Group | SNow | sys_user_group | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | assignment_group
Device Details | Discovery Source | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | discovery_source
Device Details | ACWL Status | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | u_pg_ac_wl_status
Device Details | Is EPO Managed? | N/A | N/A | N/A | N/A | N/A | Not needed anymore
Device Details | Standard Patches Not Installed | N/A | N/A | N/A | N/A | N/A | Not needed anymore
Device Details | Snow ID | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | u_number
Device Details | PG Asset ID | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | asset_tag
Device Details | Managed? | N/A | N/A | N/A | N/A | N/A | Not needed anymore
Device Details | Operating System | SNow | N/A | N/A | cmdb_ci_win_server cmdb_ci_linux_server cmdb_ci_unix_server cmdb_ci_esx_server cmdb_ci_server cmdb_ci_desktop_pc cmdb_ci_laptop_pc cmdb_ci_smartphone | os
Device Details | Service Pack | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | os_service_pack
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Device Name | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | name
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Primary Device Owner | SNow | sys_user | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | owned_by
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Site Code | SNow | cmn_location | u_pg_site_code_002 | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | location
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Device Type | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | sys_class_name
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Lifecycle Status | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | install_status
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Last Seen on Network | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | last_discovered
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Discovery Source | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | discovery_source
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Assignment Group | SNow | sys_user_group | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | assignment_group
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Device Owner | SNow | sys_user+D9 | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | owned_by
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Employee Type | SNow | sys_user | u_employee_type | sys_user | u_employee_type
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | HR Status ID | SNow | sys_user | active (will show True or False. Active employees have an active value of True) | sys_user | active
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Site Name | SNow | cmn_location | name | cmn_location | name
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Site Code | SNow | cmn_location | u_pg_site_code_002 | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | location
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Hardware Status | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | hardware_status
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | last seen | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | last_discovered
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Snow ID | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | u_number
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | PG Asset ID | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | asset_tag
% Ownership/ % Site Code/ % Lifecycle Status Accuracy gaps | Serial Number | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | serial_number
Unregistered Devices | DNS Name | Tenable | N/A | N/A | Assets API | fqdns | Question: Could there be multiple values for fqdns?
Unregistered Devices | Site Name | Tenable | N/A | N/A | N/A | N/A | Calculated based on ipv4s or ipv6s value from Tenable, which will be used to look for the matching site in the Infoblox file. The link of device to site is inferred from the IP Address range that is defined in the Infoblox file.
Unregistered Devices | Site Code | Tenable | N/A | N/A | N/A | N/A | Calculated based on ipv4s or ipv6s value from Tenable, which will be used to look for the matching site in the Infoblox file. The link of device to site is inferred from the IP Address range that is defined in the Infoblox file.
Unregistered Devices | MAC Address | Tenable | N/A | N/A | Assets API | mac_addresses
Unregistered Devices | IP Address | Tenable | N/A | N/A | Assets API | ipv4s
Unregistered Devices | OS Description | Tenable | N/A | N/A | Assets API | operating_systems
Unregistered Devices | Tenable Discovery ID | Tenable | N/A | N/A | Assets API | bios_uuid
Unregistered Devices | Last Seen | Tenable | N/A | N/A | Assets API | last_authenticated results or last_unauthenticated_results last_authenticated_scan_date OR last_seen? | Question: Does the Assets API have a last unauthenticated scan date field? If the last_authenticated results is blank, then the value from last_authenticated_results is taken
Managed Devices | Device Name | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | name
Managed Devices | Site Name | SNow | cmn_location | name | cmn_location | name
Managed Devices | Site Code | SNow | cmn_location | u_pg_site_code_002 | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | location
Managed Devices | Device Owner | SNow | sys_user | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | owned_by
Managed Devices | Discovery Source | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | discovery_source
Managed Devices | Device Type | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | sys_class_name
Managed Devices | OS Description | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | os + os_version (concatenated with a space in between)
Managed Devices | Hardware Status | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | hardware_status
Managed Devices | Snow ID | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | u_number
Managed Devices | PG Asset ID | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | asset_tag
Managed Devices | EPTM Full Scan Date | No field in SNOW | N/A | N/A | N/A | N/A | Not needed anymore
Managed Devices | Primary Device Owner | SNow | sys_user | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | owned_by
Managed Devices | Integrator | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | discovery_source
All Devices On Site | Device Name | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | name
All Devices On Site | Site Name | SNow | cmn_location | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | location
All Devices On Site | Device Owner | SNow | sys_user | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | owned_by
All Devices On Site | Device Type | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | sys_class_name
All Devices On Site | DNS Name | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | fqdn
All Devices On Site | MAC Address | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | mac_address
All Devices On Site | Hardware Status | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | hardware_status
All Devices On Site | Last Seen | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | last_discovered
All Devices On Site | ACWL Status | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | u_pg_ac_wl_status
All Devices On Site | Assignment Group | SNow | sys_user_group | name | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | assignment_group
All Devices On Site | Discovery Source | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | discovery_source
All Devices On Site | Is EPO Managed? | SNow | N/A | N/A | N/A | N/A | Not needed anymore
All Devices On Site | Standard Patches Not Installed | SNow | N/A | N/A | N/A | N/A | Not needed anymore
All Devices On Site | Snow ID | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | u_number
All Devices On Site | PG Asset ID | SNow | N/A | N/A | cmdb_ci_hardware cmdb_ci_storage_device cmdb_ci_voice_hardware | asset_tag
All Devices On Site | Managed? | SNow | N/A | N/A | N/A | N/A | Not needed anymore
| IPAM Description | Infoblox

## Tenable qu
% LifeCycle Status Accuracy Logic:
SNOW and Tenable data will be joined via the hostname (Tenable) and either the DNS Name (SNOW) or the NetBIOSName (SNOW).
If hardware status of the device is either of the following: Decommissioned, Defective, Stolen, Missing, In Disposition, In Maintenance, In Stock, On Order, Retired and the Last Seen date is 1900-01-01 then the score is 100 for the device
If hardware status of the device is either of the following: Decommissioned, Defective, Stolen, Missing, In Disposition, In Maintenance, In Stock, On Order, Retired and the Last Seen date is <=60 from the current date, then the score is 0 for the device
If hardware status of the device is either of the following: Decommissioned, Defective, Stolen, Missing, In Disposition, In Maintenance, In Stock, On Order, Retired and the Last Seen date is NULL, then the score is 100 for the device
If hardware status of the device is NULL then the score is 0 for the device
If hardware status of the device is Installed and the Last Seen date is more than 60 days already the Last Seen date is Null then the score is 0 for the device
The score for all the devices will be averaged to get the % LifeCycle Status Accuracy score.
Active Devices formula
DAX Formula: Total Active Devices:=(CALCULATE(DISTINCTCOUNT('Discovery'[DeviceKey]),'Device Details'[Lifecycle Status]="installed",FILTER('Discovery',COUNTROWS(FILTER(VALUES('Date'[Calendar Date]),'Discovery'[Start Date]<='Date'[Calendar Date]&&'Discovery'[End Date]>='Date'[Calendar Date]))))+0)
In the Discovery table we have all device IDs that have been added to our base with Tenable and SNOW. We store there information about when we started researching (storing) the given device in our database (Start Date) and when was the last update of this device (End Date).
This table is combined with a second table (Device Details) that stores the details of the device, including status.
How do we calculate Total Active devices?
For example. With only the 11 devices shown in the picture, we take into account those that have EndDate = 2019-04-10, which is today. (in this case, we will take 6 devices). Then we check the status for them and take only those that have the status = 'Installed'. And then we take only distinct on deviceKey. Assuming that each of these 6 devices has an 'Installed' status, the final result will be 6 (rows 1,2,3, 6, 8 and 10).
Initial Load
What is the "last seen" date which we should be the basis for the loading (timeframe)?
We will only load devices that were last seen for the past 3 months/90 days.
Incremental Loads
Confirm "last seen" as defining attribute (today to 90 days before)?
Yes. We should also think about full loads if the incremental load fails.
What is the timeline we need to show (rolling 12 months)?
Rolling 12 months. To build the trends, either we keep a snapshot of the previous days because that will be overwritten or there’s a full load for every 1st of the month and keep that as basis.
At what point in time/ frequency (e.g. Last day of month)?
This is updated on a daily basis - > once a month is ok
What number (current list of Tenable Ids? Has nothing to do with last_seen!)
Unregistered is all devices loaded from Tenable and are not in SNOW. Registered is all devices from SNOW. Open item: There looks to be an additional filter called IsValid that I’m still asking from Lukasz.
Invalid flag -> most likely not relevant, this was used to eliminate duplicate Tenable Ids - but we only have distinct ones
Confirm we do not need functionality to drill down to history?
No need to drill down
1. Per the metric definition below for Unregistered devices. Either DNS or NetBIOS should not be blank.
a. Can we ignore the asset extraction if both values are empty or NULL?
b. Also HP ILO device types should be excluded. Can we filter these records also from source?
c. # Unregistered Devices - the count of Unregistered Devices is taken from Tenable discovery data. Only devices with DNS or NetBIOS names are considered as valid Unregistered Devices. The IP addresses of these devices are mapped with the BT IP Diamond report to determine the sites where they belong. The denominator for Registered Devices is the sum of Registered Devices in Service Now and the count of valid Unregistered Devices in Tenable. As Site Security Leader, you are expected to investigate on the Unregistered devices in your site and register them if they are valid company assets.
Site Security Leaders should see registered devices which have an assignment group assigned and also unregistered devices captured by the scanning solution in the respective sites. You should not see registered "orphan" devices. Also "HP ILO" device types (peripherals added on to DXC servers to allow remote access/control) should be excluded.
Yes, disregard devices with no DNS or NetBIOS names. HP ILO devices should be excluded from the registered devices only.
1. Whether we need to use the below given url for getting asset data? If yes, please shed some light on the same.
https://cloud.tenable.com/scan/export/" + exportid + "/ chunks /" + item.Key
Currently we are using the below urls for fetching data. | https://cloud.tenable.com/assets/export
Provide export_id for required assets | https://cloud.tenable.com/assets/export/ed59fdf2-acfa-4318-bb60-cc79d2861cc7/status
Provide export status and chunks details | https://cloud.tenable.com/assets/export/ed59fdf2-acfa-4318-bb60-cc79d2861cc7/chunks/9
Provide asset details for specific chunk
Steve/ Tenable:
As mentioned before, The documentation is quite clear here.
https://developer.tenable.com/tenableio/reference#exports-assets-request-export
https://developer.tenable.com/tenableio/reference#exports-assets-export-status
https://developer.tenable.com/tenableio/reference#exports-assets-download-chunk
API URL – that’s already in the documentation and it’s the same URL you’re using
1. Many fields are not present in the JSON extracted from Tenable API. In those columns, last_authenticated_results/last_unauthenticated_results,Device_type and description are important for metric calculations.
Availability
Required Cols | YES
agent_uuid | YES
bios_uuid | NO
completed_at | NO
description | NO
device_type | NO
family | NO
family_id | YES
first_found (first_seen) | YES
fqdn(fqdns) | YES
has_patch(has_plugin_results) | YES
hostname(hostnames) | YES
id | YES
ipv4(ipv4s) | NO
last_authenticated_results | YES
last_found(last_seen) | NO
modification_date | NO
name | YES
operating_system(operating_systems) | NO
output | NO
port | NO
protocol | NO
publication_date | NO
risk_factor | NO
schedule_uuid | NO
see_also | NO
severity | NO
severity_default_id | NO
severity_id | NO
severity_modification_type | NO
solution | NO
started_at | NO
state | NO
synopsis | NO
tracked | NO
type | NO
uuid | NO
version
* The column names in bracket are the fields whose data is being used to populate the nearby CSV column.
Steve/ Tenable:
As you're talking about ASSET data and not VULNERABILITY data here, it would be logical to assume that vulnerability-centric fields wouldn’t be in the asset export? Further some of the fields are different, but will convey similar context as the context is to the ASSET and not a VULNERABILITY.
I’d recommend taking a look at the fields in the export to shed some light here. For example:
last_authenticated_scan_date ~ last_authenticated_results
system_types ~ device_type
(Errol) Missing fields
a. I have updated the data dictionary with the field names coming from the latest API. For some fields, they are returned as an array in the latest API. Can you check with Lukasz if we have the same cases for the API responses read by Azure, and if so, what do we do with it? Pinaki will check for those which are coming back as array.
b. There are some missing fields, which we’ll ask if there’s any corresponding field in the new API: Last Unauthenticated Results, Device Type and Description. [Device Type already answered; Description -> Operating System]
c. You’ve shared a table in the email below containing some more missing fields. If we’re not using it anyway, like the vulnerability fields, then let’s not map it anymore with the fields from the latest API.
1. Which will be the primary key field for tenable Asset data? question
ID
Source has 3 different device types Assets/Vulnerabilities and Relationships.
1. Since scope is only for Assets, How to extract only asset details from Json?
Hopefully Steves earlier reply and reference answered this? Yes
1. Please update the source mappings for below attributes.
Please provide a sample file with above fields to start extraction and development.
Are we sure these woudl be coming from Tenable/ asset API?
IPAM Descriptioin solved, Updated Date - Pinaki to check where needed
| column used | Present in Json?
Attribute | fqdn | Yes
DNS Name | ipv4 | Yes
Site Name | ipv4 | yes
Site Code | mac_address | No
MAC Address | ipv4 | Yes
IP Address | operating_system | Yes
OS Description | bios_uuid | Yes
Tenable Discovery ID | COMING FROM INFOBLOX | No
IPAM Description | not used | No
Updated Date | last_authenticated results or last_unauthenticated_results | No
Last Seen | device_type | No
Device Type | uuid | No
Host ID

## device and IP related clarif
Answers from Lukasz
1. Site code / Site mapping
We have site code and site names in the Infoblox report and also in SNOW, not always it’s consistent or unique.
a. Can you explain whether we maintain one table with all site code/ site name mappings in our PowerBI implementation? If yes, how do we decide which takes precedence? E.g. Site name from IPAM or one of the site names from SNOW (sometimes there are more than one per site code)?
Or do we decide based on where the device information is coming from e.g. if it is registered in SNOW, then take site code/ name from SNOW directly from the device record in device_details table, and if it is coming from Tenable only then take the site code -> site name (EA-Level3) from the Infoblox data?
b. In cases where the site code/ site name mapping in cmn_location is not unique e.g.
, OTHER, 1656, 1656, GREEN BAY, NORTH AMERICA, NORTH AMER AREA, UNITED STATES, SERVICES PLUS - GREEN BAY WI, 1
, OTHER, 1656, 1656, , NORTH AMERICA, NORTH AMER AREA, UNITED STATES, SERVICES PLUS - GREEN BAY WI, 1
Do we just take any one of them, or what is the rule?
For 1. For this procedure, we use the procedure that I send in the attachment.
2. How many Tenable device records do we have in our database? Is this round about a million? Or do we apply a filter (which!?) before loading the data into our tables?
For 2. We download data from Tenable from json files and then separate into several staging tables (Devices, Vulnerabilities and Relationships). The next step is to update these data in the dimension tables and the SNOW connection. In the SnowDimDeviceTenable table, we have all devices and there are about half a million of them.
When loading this to the PowerBI application, we use all data and then filter it before showing it.
3. Can you please also check and confirm the primary key of the Tenable data – we assume it’s “agent_uuid”
For 3. In the json files there is an "asset: uuid" field and it is later mapped to the Tenable Host ID with us in the database.
And more questions... I will setup a call for tomorrow morning, but in the meantime can you please check on the questions, provide answers where easy by email. And maybe also share the stored procedures for all ip addresse to site related mapping?
1. There are more than one ip addresses present for one tenable asset. Comma separated ipv4 values.
a. How to find the Site details for these?
b. If different ip address falls into more than one range(in Infoblox) how do we pick the range from Infoblox?
c. Can we pick random ip address and look for range?
For 1. If you have several ip for one device, we do not support this.
We did not have the opportunity to obtain all of the data from Tenable to compare for which devices several ip addresses should occur, and for which individual ones should be used. For this reason, the code that supports these devices has not been implemented.
In my opinion it would be necessary to separate these addresses and select the site code on the basis of the first one (but the information about whether the first IP is the most important should be confirmed with the team of Tenable).
Answers from Errol
IP range/ site mapping
Charitra: The meeting with Lukasz was fruitful but couldn’t able to get through all the questions and clarifications due to many reasons. For now we have below list of questions and the approach we have finalized after discussions till date, please review. It is bit difficult to understand the code hence we have some clarifications to take final development going.
1. If a device location is empty/null and assignment group is present should we consider Location as 'All Locations' for that device?
All Location is one of the location in cmn_location table.
This applies to SNoW devices only.
If the location is empty, then it should just be empty.
2. If sitecode002 is null/empty , should we consider u_pg_site_code for Site Code?
No, you can only use u_pg_site_code002
3. We will match infoblox site to SNOW site using Site Code and pick the Location Name from SNOW.
There are duplicate site codes in SNOW, however we will pick the site code where city value is not null.
This is ok.
4. If the Site code is not present in Infoblox or the site code does not exist in SNOW , we will mark it to UNSPECIFIED location.
If Tenable IP does not fall in any range in valid Infoblox(Valid only if Site code present), the Site will be UNSPECIFIED.
Correct.
5. Site to Assignment group relation will exist only from cmdb_ci tables. This will be number of different combinations exist in all hardware devices. Let me know otherwise?
The default is that assignment groups are based on a discovery source, while for those whose discovery source is Manual upload, then the assignment group is based on the site.
6. There is a flag named InvalidFlag in Update Snow Dim Site. Is this flag is used anywhere? If used, what is the logic of this flag?
This should be a question to Lukasz because this flag is not in the

## HW-81 BU leader dashboard
Mockup

## General Navigation
Group Genies define pre-filtering (data) and configuration
| IT Asset Admin | all assets - devices and apps charts/ metrics/ filters/ details separated by tab?
| SSLs | site assignment group content (devices) - all on one tab?
| Owning Org Leaders and Delegates | owning-org content (apps) - all on one tab? |  | Confirm all details tables content similar between stakeholders, define only exceptions!
| Integrators | type assignment group content (devices) - all on one tab?
-> already pre-set after login
In addition, all P&Gers can see their own (application) asset with compliance status and documentation gaps
View Requirements defined
View: All
| View: IT Asset Admin |  | individual stakeholder areas?
View: Site
View: OwningOrg
View: Integrators
View: Individual
Application Metrics
| Base: Registration/ Classification | confirmed
| Targeted: iRisk | confirmed
| Targeted: Validation | confirmed
| Targeted: Enterprise Architecture | confirmed
| Targeted: IT Continuity | removed
| Targeted: GDPR/ Legal | removed
Device Metrics

## Vulnerability metrics 2019 (hidden)
Richard/ EY email exchange
All tracking should be rolling 12 months as data gets available – we will develop suitable graphic format for that purpose (rather changes to the existing than development from scratches)
Limit number of slides as much as possible while keeping them useful / readable. – unnecessary slide will be removed; considering suggestion below we could get rid of the following slides: Agents and compliance scans, Vulnerabilities across regions , Vulnerabilities across infrastructure
Drastic changes up or down in the tracking should be explained in foot notes. – no problem with that but comments in foot notes may be not visible enough; our proposition is to keep the explanation related to the current month on slide while keeping the previous comments in foot notes; Richard please share your feedback on this [RE: “Like”]
1) Tenable.IO tracking. Counts should reflect completed scan month.
· Number of IP’s scanned – as I understand it correctly, we already have this data named as “Assets Scanned”; those numbers refers to the IPs listed within the range of scans so basically the IPs/devices we try to scan [RE: Agree, this is more of getting to use different terminology]
· Number of unique assets scanned one time or more (responding IP’s)
Not sure how to do this. Possibly need to use similar functionality as Excel Power Pivot count unique. QUID works for assets which has agents. Others, might have to look for combination of IP, device name – probably already covered as well, named as “Assets Discovered” – those are basically successfully scanned assets/IPs [RE: Agree}
· Critical Exploitable
· Number of unique assets with critical exploitable vulnerabilities (total open at the end of the month) – ok, we already have such data in repository
· Number of critical exploitable vulnerabilities (total open at the end of the month) – ok, same as above
· Number of new critical exploitable vulnerabilities first seen during the scan month – this is something that we were not tracking previously but looks like there will be no problem with extracting such data from tenable.io by using appropriate filter
· Number of remediated critical exploitable vulnerabilities during the scan month – see comment above, but in this case we need more time to verify whether the tenable filter works in the way we expect
· High Exploitable
· Same tracking as for Critical (asset numbers will overlap with the critical counts)
All vulnerabilities (do not count informational only records)
· Same tracking as for Critical – please confirm that for “All vulnerabilities” we also want to show only exploitable vulnerabilities (as described for Critical); in fact presenting only exploitable may impact the general overview as those are only ~20% of overall count; for the reference please see table below where I presented comparison between all and exploitable only vulnerabilities from last 30 days: [RE: Sorry, was not clear, I intended to say all, including not exploitable]
| Vulnerabilities: | Critical | High | Medium | Low | Sum
| All | 227 212 | 3 247 536 | 1 177 635 | 109 797 | 4 762 180
| Exploitable only | 25 481 | 1 059 694 | 126 208 | 2 694 | 1 214 077
| Exploitable only [%] | 10.08% | 24.6% | 9.68% | 2.39% | 20.32%
2) Remediation management tracking based on the SharePoint tracking list:
1) Number of open remediation activities (at end of scan month)
2) Number of vulnerabilities in open remediation requests (at end of scan month)
3) Number of vulnerabilities addressed as part of open / completed remediation requests during the scan month
4) Number of completed / closed remediation requests during the scan month
3) Additional tracking slides would be helpful for key remediation contacts / asset groups such as Open&Go, DXC Servers, Cloud environments. This would be a subset of #2 above, possibly broken down per main vulnerability, e.g., Adobe Reader, ILO, System Management Homepage ….. – needs to be confirmed with Genelle; changes to the remediation tracking on SharePoint might be necessary [RE: This was intended as tenable only tracking, using appropriate filters (in tenable or outside in SQL etc). This data should then correlate with the #2 noted SharePoint tracking
removed from NumeRITA scope