## Overview
| GDPR Dashboard | GDPR Compliance Cockpit | GDPR Application Tracker
RITA CR | 27 -> 114 | 15 -> 108 | 53 -> 140
Req. Owner | Evgeny Popov | Alessio Gatti | Luca Marotta
STATUS | Requirements started | Requirements 80% done, Design and Implementation started | Waiting for UAT
Purpose | Analysis of content and status of a certain scope. Enable flexible data analysis of raw data from OneTrust, for Cluster Team Members potentially on a daily basis during certain times of the year Enrich OneTrust data with additional calculations (e.g. Calculation status - exmpl tbc compliance control in scope status) that do not come out the box Filter for a certain data scope to share with action owners or in case of an event (e.g. Audit), export into Excel Everytime sb needs to look at a subset of data vs individual records Covering all organizations - SMO and GBS and GBUs | Regular compliance reporting, drive closure of open items across all organizations See metrics and be able to drill down into the gaps Covering ROPAS (OT) and tbc. When Data Assets (Mega - Group 1 and 2 apps only tbc) | Regular compliance reporting, drive closure of open items across all organizations See metrics and be able to drill down into the gaps Covering ROPAS (OT) and tbc. When Data Assets (Mega - Group 1 and 2 apps only tbc)
Audience | GDPR Lawyers, GDPR Core Team, Cluster Team Members and all other GDPR Stakeholders | Cluster Leads and Team Members, GBU And GBS SPOCs, GDPR Core Team, GDPR Lawyers | GBS Service Line SPOCs and GDPR Core Team
| Details | Details | Details
OUT OF SCOPE |  | DPIA: potential interface from Archer to RITA | Infosec logic on assessment completed/ control remediated (will be coming from Rastkos file) Phase 2: all system owners and ROPA owners tbc. - offer also for SMOs and GBUs ROPA Quality Checks - Alessios report
ASSUMPTION | OT API stabilized cluster/ suborganization data model and naming confirmed | OT API stabilized cluster/ suborganization data model and naming confirmed | Owning Organization assignment ready for use
Note on B3: Wojdyno, Tanja: get EA perspective on naming (consider future broader use of OT)

## Data Extracts - Evgeny
GDPR Dashboard
Data Sources | OneTrust | Mega
Data Objects | OT: Processing Activities (Mega Data Asset attributes would be maintained on "new" GBS ROPA record level) | Mega: Data Assets
Data Model
Attributes (incoming) | Cockpit Attributes
Attributes (visible) | Cockpit Attributes
Calculated Attributes (formula) | Cockpit Attributes
Filters, initially applied | OT: None | Mega: Data Assets which are... Application Nature != (“Platform”,”XOPlatform”) and Lifecycle Status != (“Decomissioned”, “Exception Use”, “not_used”, “Undecided”) tbd: ownership filter also RITA manual overwrite fields GDPR Relevant Flag = “Y” and VP != “Non GBS” must be applied | We need capability to filter within the table (search in freetext).
Views/ Pages | One Page for Processing Activities | One Page for Data Assets
Filter options | Category | PII Handled | Owning Org | Country | Vendor Qualification | Compliance Priority | Data Source | Asset Type | Asset Sub-Type | X-Border | EU Volume | Volume All | Inventory Status | Lawful Basis Status | Data Retention Status | Minimization Status | InfoSec Status | DBR Status | DSR Status | Vendor Status | DPIA Status | Notices Status | PII Data Type File | R&D Consumer Data Asset | XLS Template ID
Reference to existing RITA report | Complete Data asset and ROPA
Desired update frequency | daily (business days)
New requirements, not implemented in Excel
Additional/ current open questions | Security Controls are partially linked to ROPAS and partially to Data Assets. ROPAs missing Data Assets. Data Assets missing ROPAs today. Some attributes/ Links are not coming from one unified list. | capability of filtering by all other columns (not only using slicers)
Later anticipated changes (what/ when) | Art.30 - last updated

## Data Extracts - Attributes
GDPR Dashboard | Filters/ Slicer | Piority/ Grouping for Slicer? | Visible Attributes | Incoming Attributes OT | Incoming Attributes Mega | Incoming attributes Other Sources | Calculated Attributes (Formulas) | Translated Attributes
|  |  | Inventory Id | Inventory Id | MEGA Id
| Slicer |  | Data Subject Type - P&G | Data Subject Type - P&G | Data Category
| Slicer |  | Owning Organization | Owning Organization | Owning Organization
|  |  | Processing Activity | Name
|  |  | Business Process Owner | Business Process Owner
|  |  | Managing Organization | Managing Organization | P&G Business Contact Name/E-Mail
|  |  | SAP Vendor Number | SAP Vendor Number | SAP Vendor(s) Number
|  |  | SAP Vendor Name | SAP Vendor Name | SAP Vendor(s) Name
|  |  | Description | Description | Business Process/Service Description
| Slicer |  | Country Collected | Country Collected | In Which Country Are You Collecting PII?
| Slicer |  | PII Handled | PII Handled
|  |  | Contractual Data - LEs | Contractual data - LEs | LE(s) receiving the services?
|  |  | Business Process / Service | Business Process / Service | P&G Business Process
| Slicer |  | Processing Activity - Repository Type | Processing Activity - Repository Type | Application Nature
| Slicer |  | Processing Activity - Repository Sub-Type | Processing Activity - Repository Sub-Type
|  |  | Processing Activity Linked to P&G System | Processing Activity Linked to P&G System
|  |  | Purchasing Contact | Purchasing Contact
|  |  | Business Contact | Business Contact
|  |  | Third Party Contact | Third Party Contact
| Slicer |  | Vendor Qualification | Vendor Qualification
|  |  | Scope Number | Scope Number | SCOPE Doc Name |  | for Mega, if entry is xxxx.docx, then truncate and just provide xxxx. If the name is different, then please keep the name exacly as coming from the source
|  |  | Trans-border Data Transfer | Trans-border Data Transfer | x - Border
| Slicer |  | # of Data Stakeholders from EU | # of Data Stakeholders from EU | Volume Of Records - EU Countries
| Slicer |  | Volumes of Records - All Countries | Volumes of Records - All Countries | Volume Of Records - ALL Countries
|  |  | PG Users | PG Users | Number Of P&G Users With Access
|  |  | Third-party Users | Third-party Users | Number Of 3rd Party Users With Access
|  |  | Data Elements Collected - P&G | Data Elements Collected - P&G
|  |  | Data From Children | Data From Children
|  |  | ADM | ADM | Automated Decision Making
|  |  | Reason for Collection | Reason for Collection | Reason for Data Collection
|  |  | Data Retention | Data Retention | Data Retention Period
|  |  | Processing Activity Life Cycle Status | Processing Activity Life Cycle Status | 'OneTrust Complete GDPR Records'[Application Lifecycle Status]
|  |  | Retired Date | Retired Date | Retired Date(Decommission)
|  |  | Additional Information | Additional Information
|  |  | Custom Field #1 | Custom Field #1 | Comments / Other Information About The Application
|  |  | Custom Field #2 | Custom Field #2
|  |  | Custom Field #3 | Custom Field #3
|  |  | Custom Field #4 | Custom Field #4
|  |  | Custom Field #5 | Custom Field #5
|  |  | Custom Field #6 | Custom Field #6
|  |  | Custom Field #7 | Custom Field #7
|  |  | Custom Field #8 | Custom Field #8
|  |  | Custom Field #9 | Custom Field #9
|  |  | Custom Field #10 | Custom Field #10
|  |  | Remediation: GUV Number | Remediation: GUV Number
|  |  | Remediation iContract | Remediation iContract
|  |  | Remediation TPRM | Remediation TPRM
|  |  | Remediation Required | Remediation Required
| Slicer |  | XLS Template ID | XLS Template ID
|  |  | SPO Record ID | SPO Record ID
|  |  | MEGA Record ID | MEGA Record ID
|  |  | TISL Primary | TISL Primary
|  |  | TISL Backup | TISL Backup
|  |  | Inventory: Criteria | Inventory: Criteria | InventoryStatus
|  |  | Inventory: Evidence | Inventory: Evidence | InventoryKeptUptoDate
| Slicer |  | Inventory: Status | Inventory: Status | InventoryEvidence |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Inventory: In Scope |  |  |  | IF('PII Handled' = "No", FALSE, TRUE)
|  |  | Lawfulness Basis: Criteria | Lawfulness Basis: Criteria | LawfulnessBasisStatus
|  |  | Lawfulness Basis: Evidence | Lawfulness Basis: Evidence | LawfulnessBasisEvidence
| Slicer |  | Lawfulness Basis: Status | Lawfulness Basis: Status | LawfulnessBasisProcessing |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Lawfulness Basis: In Scope |  |  |  | IF('PII Handled' = "No", FALSE, TRUE)
|  |  | Notice: Criteria | Notice: Criteria | NoticeStatus
|  |  | Notice: Evidence | Notice: Evidence | NoticeProcessing
| Slicer |  | Notice: Status | Notice: Status | NoticeEvidence |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Notice: In Scope |  |  |  | IF('PII Handled' = "No" OR ("Vendor Qualification" = "Data Controller" AND 'SAP Vendor Number' <> "NO VENDOR" ), FALSE, TRUE)
|  |  | Minimization: Criteria | Minimization: Criteria | MinimizationStatus
|  |  | Minimization: Evidence | Minimization: Evidence | Minimization
| Slicer |  | Minimization: Status | Minimization: Status | MinimizationEvidence |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Minimization: In Scope |  |  |  | IF('PII Handled' = "No" OR ("Vendor Qualification" = "Data Controller" AND 'SAP Vendor Number' <> "NO VENDOR" ), FALSE, TRUE)
|  |  | Data retention: Criteria | Data retention: Criteria | DataRetentionStatus
|  |  | Data retention: Evidence | Data retention: Evidence | DataRetentionDefImplemented
| Slicer |  | Data retention: Status | Data retention: Status | DataRetentionEvidence |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Data retention: In Scope |  |  |  | IF('PII Handled' = "No" OR ("Vendor Qualification" = "Data Controller" AND 'SAP Vendor Number' <> "NO VENDOR" ), FALSE, TRUE)
|  |  | Reasonable InfoSec: Criteria | Reasonable InfoSec: Criteria | ReasonInfosecUctrlStatus
|  |  | Reasonable InfoSec: Evidence | Reasonable InfoSec: Evidence | ReasonInfosecUctrl
| Slicer |  | Reasonable InfoSec: Status | Reasonable InfoSec: Status | ReasonInfosecUctrlEvidence |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Reasonable InfoSec: In Scope |  |  |  | IF('PII Handled' = "No" OR 'Processing Activity - Repository Sub-Type' <> "Application" OR ('Processing Activity - Repository Sub-Type' = "Application" AND 'Compliance Prioritization2' <> "A"), FALSE, TRUE)
|  |  | Data breach response: Criteria | Data breach response: Criteria
|  |  | Data breach response: Evidence | Data breach response: Evidence
| Slicer |  | Data breach response: Status | Data breach response: Status |  |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Data breach response: In Scope |  |  |  | =FALSE
|  |  | Data Subject Rights: Criteria | Data Subject Rights: Criteria | DataSubjRightsStatus
|  |  | Data Subject Rights: Evidence | Data Subject Rights: Evidence | DataSubjRightsCentralTeam
| Slicer |  | Data Subject Rights: Status | Data Subject Rights: Status | DataSubjRightsEvidence |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Data Subject Rights: In Scope |  |  |  | IF('PII Handled' = "No" OR ("Vendor Qualification" = "Data Controller" AND 'SAP Vendor Number' <> "NO VENDOR" ), FALSE, TRUE)
|  |  | Vendors: Criteria | Vendors: Criteria | VendorsStatus
|  |  | Vendors: Evidence | Vendors: Evidence | VendorsPrivacyInfosecUpdated
| Slicer |  | Vendors: Status | Vendors: Status | VendorsEvidence |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | Vendors: In Scope |  |  |  | IF('PII Handled' = "No" OR 'SAP Vendor Number' <> "NO VENDOR", FALSE, TRUE)
|  |  | DPIA: Criteria | DPIA: Criteria | DataProImpactAssessStatus
|  |  | DPIA: Evidence | DPIA: Evidence | DpiaDonebyLegal
| Slicer |  | DPIA: Status | DPIA: Status | DpiaEvidence |  |  | Status Translation: "Aligned with Central SCOPE" = "Aligned", "Deviation from Central SCOPE" = "Deviation", "Work In Progress" = "In Progress", other statuses are not translated
|  |  | DPIA: In Scope |  |  |  | IF('PII Handled' = "No" OR ("Vendor Qualification" = "Data Controller" AND 'SAP Vendor Number' <> "NO VENDOR" ), FALSE, TRUE)
|  |  | Government ID, government-issued ID | Data Elements Collected P&G | Government ID, Government-Issued ID
|  |  | Credit card numbers | Data Elements Collected P&G | Credit Card Numbers
|  |  | Financial account number | Data Elements Collected P&G | Financial Account Number |  |  | Data Elements Collected - P&G
|  |  | Genetic data | Data Elements Collected P&G | Genetic Data |  |  | Data Elements Collected - P&G
|  |  | Biometric data | Data Elements Collected P&G | Biometric Data |  |  | Data Elements Collected - P&G
|  |  | Sex life, sexual orientation questions | Data Elements Collected P&G | Sexlife, Sexual Orientation Questions |  |  | Data Elements Collected - P&G
|  |  | Data about children under 13 | Data Elements Collected P&G | Data About Children Under 13 |  |  | Data Elements Collected - P&G
|  |  | Criminal or judicial records | Data Elements Collected P&G | Criminal Or Judicial Records |  |  | Data Elements Collected - P&G
|  |  | Precise geo location data | Data Elements Collected P&G | Precise Geo Location Data |  |  | Data Elements Collected - P&G
|  |  | Racial or ethnic origin | Data Elements Collected P&G | Racial Or Ethnic Origin |  |  | Data Elements Collected - P&G
|  |  | Political opinions, political party affiliation | Data Elements Collected P&G | Political Opinions, Political Party Affiliation |  |  | Data Elements Collected - P&G
|  |  | Trade union membership | Data Elements Collected P&G | Trade Union Membership |  |  | Data Elements Collected - P&G
|  |  | Protected Health Information (“PHI”) as defined by HIPAA | Data Elements Collected P&G | Protected Health Information |  |  | Data Elements Collected - P&G
|  |  | Other health or medical data | Data Elements Collected P&G | Other Health Or Medical Data |  |  | Data Elements Collected - P&G
|  |  | Digital signature data | Data Elements Collected P&G | Digital Signature Data |  |  | Data Elements Collected - P&G
|  |  | Data about teens between 13-15 years old | Data Elements Collected P&G | Data About Teens Between 13-15 Years Old |  |  | Data Elements Collected - P&G
|  |  | Consumer account username and password | Data Elements Collected P&G | Consumer Account UserName And Password |  |  | Data Elements Collected - P&G
|  |  | Adverse event information | Data Elements Collected P&G | Adverse Event Information |  |  | Data Elements Collected - P&G
|  |  | Identification Data | Data Elements Collected P&G | Identification Data |  |  | Data Elements Collected - P&G
|  |  | Electronic identification data | Data Elements Collected P&G | Electronic Identification Data |  |  | Data Elements Collected - P&G
|  |  | Personal characteristics | Data Elements Collected P&G | Personal Characteristics |  |  | Data Elements Collected - P&G
|  |  | Family composition | Data Elements Collected P&G | Family Composition |  |  | Data Elements Collected - P&G
|  |  | Profession | Data Elements Collected P&G | Profession |  |  | Data Elements Collected - P&G
|  |  | Image/sound recordings | Data Elements Collected P&G | Image/Sound Recordings |  |  | Data Elements Collected - P&G
|  |  | Religious or philosophical beliefs | Data Elements Collected P&G |  |  |  | Data Elements Collected - P&G
| Slicer |  | PII Data Type - SP formula |  |  |  | IF( OR('Government ID, government-issued ID'=TRUE,'Credit card numbers'=TRUE,'Financial account number'=TRUE,'Genetic data'=TRUE,'Biometric data'=TRUE,'Sex life, sexual orientation questions'=TRUE,'Data about children under 13'=TRUE,'Criminal or judicial records'=TRUE), "High", IF( OR('Precise geo location data'=TRUE,'Racial or ethnic origin'=TRUE,'Political opinions, political party affiliation'=TRUE,'Trade union membership'=TRUE,'Protected Health Information (“PHI”) as defined by HIPAA'=TRUE,'Other health or medical data'=TRUE,'Digital signature data'=TRUE,'Data about teens between 13-15 years old'=TRUE,'Consumer account username and password'=TRUE,'Adverse event information'=TRUE), "Medium", IF(OR('Identification Data'=TRUE,'Electronic identification data'=TRUE,'Personal characteristics'=TRUE,'Family composition'=TRUE,'Profession'=TRUE,'Image/sound recordings'=TRUE,'Religious or philosophical beliefs'=TRUE),"Regular","Not Scored") ) )
|  |  | PII Data Type Final - SP formula |  |  |  | IF('PII Handled' = "" OR 'PII Handled' = "Yes",IF('Vendor Qualification'="Data Controller","N/A",'PII Data Type - SP formula'),"N/A")
|  |  | Volume Risk Level |  |  |  | IF('# of Data Stakeholders from EU'=">= 20,000" OR 'Volumes of Records - All Countries'=">= 1,000,000","HIGH",IF('# of Data Stakeholders from EU'=">= 1,000 - < 20,000","MEDIUM","LOW"))
| Slicer |  | Compliance Prioritization2 |  |  |  | IF('Volume Risk Level'="HIGH" AND 'PII Data Type Final - SP formula'="HIGH","A",IF('PII Data Type Final - SP formula'="HIGH","B",IF('PII Data Type Final - SP formula'="Medium","C","D")))
| Slicer |  | R&D Consumer Data Asset |  |  |  | IF(('Custom Field #1' CONTAINS "IC" AND NOT('Custom Field #1' CONTAINS "Nordic") AND 'Managing Organization'="409-NE Cluster") OR('Custom Field #10' CONTAINS "GIC" AND 'Managing Organization ="406-DACH Cluster") OR 'XLS Template ID' CONTAINS "verbi"
|  |  | Transfer to 3rd countries - details | Transfer to 3rd countries - details
|  |  | P&G Sites / Departments | P&G Sites / Departments
|  |  | Recipients of the data | Recipients of the data
|  |  | Scope Normalized | Scope Number
Application Name
Other PII - Please specify
MegaCreationDate
MegaUpdateDate
PII Data Handled By Vendor For Specific Business Process/Service
| Slicer |  | Source |  |  |  | OneTrust or Mega
Note on D2: Wojdyno, Tanja: see on sheet "Dashboard - Evgeny"

## Data Extracts - R&D wish list
Dashboard: metrics with be drilled down in reports.
For each view there would be a hover that provides detail and one click that opens to the details.
R&D - ALL and capability to select site/ country/ cluster. Need to know:
total no. of PA
PA status – in discovery, new, discovered….pie chart
Vendor status (controller, processor…..)
Visual on data fields NOT completed – or late for completion (when available) - would drill down to a file that shows gaps. Represent as a % to help drive activity.
No. apps plus status
A view that captures the relative importance/risk profile of a PA - A, B, C, D.

## Compliance - Paging (hidden)
Owning Organization | Page | Ref CR15_addChangeView.doc
201-GBS My P&G Services | 3
205-GBS Consumer Services | 3
301-Baby Care | 2
302-Braun and Shave Care | 2
303-Fabric Care | 2
304-Hair Care | 2
305-Home Care | 2
306-PGT | 2
310-Fem Care | 2
312-Oral Care | 2
316-Skin and Personal Care | 2
404-CE Cluster | 1
405-Europe Cluster | 1
406-DACH Cluster | 1
407-FBNL Cluster | 1
408-Israel Cluster | 1
409-NE Cluster | 1
410-SE Cluster | 1
411-SEE Cluster | 1
415-TCAU Cluster | 1
unknown categorization | 4
Others to be added as appropriate
what about other GBS? Data Asset based?

## Compliance- Alessio
GDPR Compliance Cockpit
Data Sources | OneTrust | Mega (to be confirmed if Mega will be relevant or not; pending EA questions with Troy: where do we maintain Privacy data on MEGA Assets, Do we need to instantiate uses of MEGA Assets in OneTrust? <-- if yes, then we don't need MEGA at all)
Data Objects | ROPA Compliance Controls | Data Asset Compliance Controls
Attributes (incoming) | Inventory Id | Name | Managing Organization | Description - not used | Business Process Owner | Categories of Data Subjects | Categories of Data | Data Elements | Data Subjects Region | Data Subjects Volume | Purpose of Processing - not used | Data Source - not used | Source Asset - not used | Primary Storage Asset - not used | Transfer Method (From Sources) - not used | Destinations - not used | Destination Asset - not used | Transfer Method (To Destinations) - not used | Parties who Access/Use Data - not used | Locations of Parties (Access/Use) - not used | Data Retention - not used | Risk Level | Volumes of Records - All Countries | SPO Record ID | Minimization: Evidence | Remediation TPRM | # of Data Stakeholders from EU | Business Contact | Lawfulness Basis: Criteria | Transfer to 3rd countries - details | Vendors: Criteria | Inventory: Evidence | Custom Field #6 | Custom Field #10 | Lawfulness Basis: Evidence | SAP Vendor Name | Data retention: Criteria | XLS Template ID | Vendors: Evidence | MEGA Record ID | Notice: Evidence | TISL Primary | Vendors: Status | P&G Sites / Departments | Custom Field #7 | Trans-border Data Transfer | Data Elements Collected - P&G | Scope Number New | Minimization: Criteria | Data retention: Evidence | Notice: Status | Custom Field #4 | Processing Activity - Repository Sub-Type | Inventory: Status | Inventory: Criteria | DPIA: Criteria | DPIA: Status | Third-party Users | Vendor Qualification | Data breach response: Evidence | Third Party Contact | Reasonable InfoSec: Status | PII Handled | Scope Number | Additional Information | Reasonable InfoSec: Criteria | Custom Field #3 | Reason for Collection | Data Subject Rights: Evidence | Country Collected | Custom Field #2 | Data Subject Type - P&G | Remediation: GUV Number | Description | Contractual data - LEs | Data Retention | Recipients of the data | Data From Children | Remediation iContract | Custom Field #5 | PG Users | Custom Field #9 | Lawfulness Basis: Status | Purchasing Contact | Custom Field #1 | Processing Activity - Repository Type | TISL Backup | Owning Organization | Data breach response: Status | Data retention: Status | SAP Vendor Number | Data Subject Rights: Status | DPIA: Evidence | Custom Field #8 | ADM | Data Subject Rights: Criteria | Business Process / Service | Minimization: Status | Remediation Required | Data breach response: Criteria | Reasonable InfoSec: Evidence | Retired Date | Notice: Criteria | Processing Activity Life Cycle Status | Processing Activity Linked to P&G System | Add all attributes of Art. 30 Download
Attributes (visible) | Inventory Id | Name | Managing Organization | Categories of Data Subjects | Vendors: Status | Notice: Status | Inventory: Status | DPIA: Status | Reasonable InfoSec: Status | PII Handled | Lawfulness Basis: Status | Owning Organization | Data breach response: Status | Data retention: Status | Data Subject Rights: Status | Minimization: Status | Processing Activity Life Cycle Status
Calculated Attributes (formula) | Average Compliance Percentage across RoPAs/ Data Assets per Control Type and Cluster* {I donot think this is a caluclated measure at all; it's rather coming as a result of the compliant sum / total in analysis scope!} | Average Compliance Percentage across RoPAs/ Data Assets per Control Type and Cluster* 3 months ago {I donot think this is a caluclated measure at all; it's rather coming as a result of the compliant sum / total in analysis scope!} | RoPA ID + Compliance Control combination: this is generating a key for each compliance control within a RoPA, combining the [Inventory Id] field with teh following names: Inventory Lawfulness Basis Notice Minimization Data retention Reasonable InfoSec Data breach response Data Subject Rights Vendors DPIA | 1 Compliant boolean status per each of the 10 following: Vendors: Status Notice: Status Inventory: Status DPIA: Status Reasonable InfoSec: Status Lawfulness Basis: Status Data breach response: Status Data retention: Status Data Subject Rights: Status Minimization: Status Resulting in: - TRUE when [In Scope]= True and Status in ("Aligned with SCOPE", "Deviation from SCOPE", "Not Applicable", "Not needed") - FALSE when [In Scope]=True and Status in ("In Progress", "Not Started") - N/A when [In Scope] = False | 1 In scope flag per each of the 10 following: Vendors Notice Inventory DPIA Reasonable InfoSec Lawfulness Basis Data breach response Data retention Data Subject Rights Minimization For Rules on the "In scope flags" refer to "in scope calculation" tab. | [Older than 3 months] boolean flag associated with each RoPA, calculated as follows: - When Today - [RoPA Creation date as per Art. 30 download] > 90 days --> TRUE, else FALSE | Rastko will send the file with formulas
Filters, initially applied | exclude [In Scope] = FALSE controls - - for Customer report, but keep it for the "All" report | Mega: Data Assets which are... Application Nature != (“Platform”,”XOPlatform”) and Lifecycle Status != (“Decomissioned”, “Exception Use”, “not_used”, “Undecided”) tbd: ownership filter also RITA manual overwrite fields GDPR Relevant Flag = “Y” and VP != “Non GBS” must be applied" | Exclude controls connected to RoPA where the [Processing Activity Life Cycle Status] is different from "Live in Market", "Innovation" - for Customer report, but keep it for the "All" report
Views/ Pages | Pages grouped based on criterium listed in "Paging" Tab and extra Word document - consider filter instead
Filter options | Status | Inventory ID | Record Name | Managing Organization | Categories of Data Subjects | PII Handled | Owning Organization | SCOPE Document | ROPA Lifecycle Status | ROPA Age | Compliance Control Name | In scope y/n for "All" Report | Lifecycle Status ... For "All" Report
Reference to existing RITA report | Compliance (Remediation) Report | an enhanced version in currently in our Dev environment
Desired update frequency | at least weekly
New requirements, not implemented in Excel | Absolute numbers next to Percentages |  | Category - Team Organization mapping | Owning Organization: do not show the sorting numbers, but continue to group GBU/SMO/GBS and sequence in a custom way
Additional/ current open questions | Sustainable, consistent structure for Managing and Owning Organization would be recommended. Otherwise there is a risk of creating gap and overlapping areas. | To be confirmed how to handle "not applicable" controls - i.e. How to identifiy and exclude from denominator. "not applicable" may be marked with this status or implicit according to ROPA/ Data Assest risk level! | Configuration Table for Compliance Control Levels: Target System, where we maintain the desired level of compliance controls "Okness" and the tresholds for red, yellow and green | Attributes naming -aligned and consistent across reports! | Search for parts of text string | Scope selections (filters) can be saved, and shared across users | Status filter grouping (compliant/ not compliant with subselection) | R&D needs a tab which shows Controls by Innovation Center (Proces Owner - Innovation Center - manual table mapping) | Dashboard may be useful going forward | We need to show gaps explicitly. | Ability to filter/ search ofr lower level organizations - countries
Later anticipated changes (what/ when)
Note on H7: Wojdyno, Tanja: the creation data informaiton is available in the famous "Art.30" table, this information is not available in the main table

## Compliance - In Scope Calc
Conditions per Compliance Control for [In Scope] to be true
(when conditions not met, [in scope] flag is false)
Inventory | [PII Handled] = TRUE
Lawfulness Basis | [PII Handled] = TRUE |  | ROPAs | Processing Activities
Notice | [PII Handled] = TRUE AND ([Vendor Qualification] <> 'Data Controller' OR ([Vendor Qualification] = 'Data Controller' AND [SAP Vendor Number] = 'No Vendor'))
Minimization | [PII Handled] = TRUE AND ([Vendor Qualification] <> 'Data Controller' OR ([Vendor Qualification] = 'Data Controller' AND [SAP Vendor Number] = 'No Vendor'))
Data retention | [PII Handled] = TRUE AND ([Vendor Qualification] <> 'Data Controller' OR ([Vendor Qualification] = 'Data Controller' AND [SAP Vendor Number] = 'No Vendor'))
Reasonable InfoSec | [PII Handled] = TRUE AND [Processing Activity - Repository Sub-Type] = 'Application' AND [Compliance Prioritization2] = 'A'
Data breach response | 1=0 (always FALSE --> [In scope]= False
Data Subject Rights | [PII Handled] = TRUE AND ([Vendor Qualification] <> 'Data Controller' OR ([Vendor Qualification] = 'Data Controller' AND [SAP Vendor Number] = 'No Vendor'))
Vendors | [PII Handled] = TRUE AND [SAP Vendor Number] <> 'No Vendor'
DPIA | [PII Handled] = TRUE AND ([Vendor Qualification] <> 'Data Controller' OR ([Vendor Qualification] = 'Data Controller' AND [SAP Vendor Number] = 'No Vendor'))
"OK" vs "Not OK" SuperStatus
Orig Data | Result | Super Status
Not Applicable | Not Applicable | Not OK
Not Started | Not Started | Not OK
Work In Progress | In Progress | Not OK
Not Needed | Not Needed | OK
Deviation from Central SCOPE | Deviation | OK
Aligned with Central SCOPE | Aligned | OK
Age Class: Compliance > 3 months
Age Class
A | created last 30 days
B | created last 60 days
C | created more than 60 days ago = in scope for "> 3 months % compliance calculation"

## Details Infosec - Luca
All of this may be fully covered by the iRisk process and reporting going forward
Infosec Group 2/3/4
Dashboard like shown on the right, with drill-down capability
# of Apps: from filtered VP tracker exlcuding additional ones (lifecycle status Sunset/retired), then looking for # Assessemnts completed
# of Assessments Completed: GDPR Sharepoint - GBS IT - Infosec - files with the name of a MegaHexID (does the file exist or not - Rough Cut); also some exception flag (no assessment needed e.g in case recent iRISK done) also inspect content of files to assess status of details
|  | RITA will receive a file from GDPR project which includes this logic (weekly) |  |  | also allow to see those which are not complete:
Infosec Group 1
| GDPR Execution Tracking and Reporting GBS v3.xls (Infosec SP) |  |  | (was a one-off project FY1718 with 6 applications left over (3 in GBS))
We need a report with the following information per Group 1 app:
|  | Rough Cut Complete - Assessment Done |  |  | drill down:
Evidence Collection
AD Approal and sign-off - Risk Assessment
Verification of Remediation (TISL confirms compliance)
Watchout: short-term vs mid-term data source
Data Sources is tbd (Luca/ Hans)
Ongoing process (iRisk) tbc, but currently it's a manually maintained Excel file
TBc: what about non-GBS applications?
What is required for Group 1 reporting out of RITA
Select all group 1 applications out of VP tracker (ie the apps scope for the report)
Apply same logic as for group 2-3-4 on further filtering on lifecycle (ie exclude discovery, sunset, decommissioned etc…see email to Rasko for confirmation)
For each group 1 application (column B,C in attachment) report the following columns (as in attached xls, but simplified):
“Controls Rough Cut Check” (ie “CSC assessment status”): complete/wip/not started/not applicable (column “R”)
“Evidence collection & Review”: complete/wip/not started/not applicable (column “T”) – nice to have
“Non-Remediation Acceptance”: complete/wip/not started/not applicable (column “AG”)
“Verification of Remediation” (ie CSC compliance status): complete/wip/not started/not applicable (column “AI”)
Additionally, RITA must be able to aggregate the apps by service line/VP and report % of “complete” status for each of the 4 measures above (similar cockpit as Rastko’s one for Group 2-3-4 apps InfoSec report)
How to provide the raw data to RITA:
One-off: do a one-off load of the 88 applications that were in the scope of last FY CF infosec project (using the attached xls report)
Ongoing: for new group 1 apps (which will come up in the VP tracker report).
Short term solution: define a standard template for ongoing upload into RITA and set up a process with
SL SPOCs: to check the iRisk completion status of the new apps
Rastko: to get the standard template populated
Short term process on a regular frequency (weekly or up to monthly, based on how often we have new group 1 apps tbd)
Plan for later: Work with iRisk team to create the interface to get the same raw data for RITA as per above tracker. Involve also Troy for architecture decisions (example pre-filter the GDPR relevant apps in iRisk or in RITA? Prefilter the relevant lifestages in iRisk or Rita?) – Luca for now. New PM as it comes

## Details Inventory - Luca
GBS Details Report
Data Sources | Mega | InfoSec Report | RITA custom tables
Data Objects | Data Assets
Attributes (incoming) | GBS Details Attributes
Attributes (visible) | GBS Details Attributes
Calculated Attributes (formula) | GBS Details Attributes
Filters, initially applied | Report level filter - from Mega: Data Assets which are... Application Nature = one of [Application/ Application Ext. Owned/ Non-Digital/ Component] Lifecycle Status not = (“Decomissioned”, “Exception Use”, “not_used”, “Undecided”) GDPR Relevant Flag = “Y” (calc and overwrite) | GBS/IT Project Team view: show everything, following report level filter and exclude everything that is not on the GBS/IT owning organization whitelist (UNLESS unknown/ empty - must be shown as well!) PLUS add overwritten GDPR relevance flags, | GBS/IT VP page: show everything following report level filter, BUT exclude everything that is not on the following whitelist for GBS/IT L1 owning orgs**: Information Security IT Consumer Solutions IT Customer Solutions & Delivery IT Data & Analytics Organization IT IT Development Organization IT IT Innovation Organization IT Solutions Consumer Services FSS IDQ MANAGEMENT SERVICES Master Data Organization MY PG SERVICES PS Shared Services & Technology Operations PTW exclude also lifecylce status = discovery exclude also items which only showed up last 14 days (grace period*) | Other VP page: show everything , following report level filter, BUT exclude the witelisted GBS/IT organizations (show all lifecycle status and do not limit through grace period) |  | *grace period: Day x +14; where x is the day when an item first met all of the following criteria: Application Nature = one of [Application/ Application Ext. Owned/ Non-Digital/ Component] AND Lifecycle Status not = (“Decomissioned”, “Exception Use”, “not_used”, “Undecided”) AND GDPR Relevant Flag = “Y” (calc and overwrite) AND L1 owning org = part of whitelist | ** GBS/IT orgs = check from PGV_ORG_ITAM_GBS.csv source file - every L1 org where L0 org name is "Corporate Function - IT (CF-IT)" or "Global Business Services Organization (GBS)"
Views/ Pages | One Page should show table by Service Line, # of apps % inventory compliance, % infosec compliance, # of apps per group | One view (details table) for Inventory details with applied on-top filters (excl. Discovery non-relevant recent 8 weeks) - purpose is to share with VP. | One view which is more wholistic and shows ON TOP data assets in Discovery, flagged as Non-relevant and just recently (8 weeks) showing up. Filtering to allow show e.g. Discovery only, or only the one which will soon be reported to VP, or the non-relevant flagged (with NEW comments) | One pivot view for Group 1 Data Assets showing compliance status for Inventory and InfoSec per GBS VP | Cluster accountability / visibility for controls to be addressed | More than one dedicated link to Data Controller, App Owner and Owning Organization must be flagged as gap.
Filter options | None
Reference to existing RITA report | GBS VP Analysis
Desired update frequency | at least weekly
New requirements, not implemented in Excel | Start with VP Tracker/ VP Gap Tracker existing report pages | Grouping Calculation: based on Organization mapping (vs previous manual VP assignment) | Add comment field to "non relevant" flagging: who, why, when | make sure that one out missing out of multiple available vendor codes gets flagged accordingly | Consistentcy of Owning Organization Assignment across all reports
Additional/ current open questions | Rentention, Vendor etc. Controls shall be reported through Compliance Dashboard (no detailed tracking in here) | Details table should highlight gaps in the tracker (red cells) | Export table details with highlighted gap cells - not possible | Export summary table (which is not really a table) into Excel - not possible, use full screen/ zoom in - jpeg screenshot instead | Add totals of the summary columns (light blue section) | Grace Period: consolidate apps that are already in the VP Details under one "date" e.g. Call it "reported already" | Infosec Group 1: align simplified version - mockup to be provided by Luca | Infosec Grp 2,3,4 should rely on Excel input only, not consolidate with the data from Mega (keep it simple) . To allow for drilldown, total calculation will be column F from Rastkos file) | Grouping Logic - continued changes - last confirmed on October 25 | We must keep a grouping logic check column - which would indicate in case an application is eligible for more than one grouping, due to a logic gap. | Keep "Unknown" line item in Project Team tab - for those apps which are NOT assgined to any org at all.
Later anticipated changes (what/ when)
Other | Owning Org sources, display and usage: From Mega we are getting the following fields - AD (reporting line auto derived from ED) - Dir (reporting line auto derived from ED) - VP (reporting line auto derived from ED) - Owning Organization (lowest level) - AD (Owning Org manual assignment) - Dir (Owning Org manual assignment) - VP (Owning Org manual assignment) which we translate into one high-level GBS/IT organization name - VP name must be at the same level. The high-level GBS/IT organization name is used in slicers and it the summary visuals and in the Grouping formula calculation. The VP name is displayyed in the summary visual. For Reference, documentation CR85 Org Hierarchy (Level 1 = VP, Level 2 = Director, Level 3 = AD). By the way the high-level Owning org name is also used in the Compliance Report - so it makes sense to have one general translation table which we can also use to organize grouping and sorting and removing the leading numbers from OT for owning organization.

## Grace Period Example
Item | Date Created/ Edited | Nature | Lifeycle Status | GDPR Relevant Result | L1 Owning Org | Show in GBS/IT VP view on same day | Show in Project Team View on same day
App1 | 1.1. | Application | Leverage | y | Information Security | N | Y
App2 | 1.1. | Platform | Leverage | y | Information Security | N | N
App3 | 1.1. | Application | Leverage | N | Information Security | N | N
App4 | 1.1. | Application | Leverage | N | SMO DACH | N | N
App1 | 15.1. | Application | Leverage | y | Information Security | Y | Y
App2 | 15.1. | Application | Leverage | y | Information Security | N | Y
App3 | 15.1. | Application | Leverage | N | Information Security | N | N
App4 | 15.1. | Application | Leverage | N | SMO DACH | N | N
App1 | 29.1. | Application | Leverage | y | Information Security | Y | y
App2 | 29.1. | Application | Leverage | y | Information Security | Y | y
App3 | 29.1. | Application | Leverage | N | Information Security | N | N
App4 | 29.1. | Application | Leverage | N | SMO DACH | N | N
App1 | 30.1. | Application | Discovery | y | Information Security | N | N
App2 | 30.1. | Application | Leverage | y | Information Security | Y | y
App3 | 30.1. | Application | Leverage | N | Information Security | N | N
App4 | 30.1. | Application | Leverage | N | SMO DACH | N | N
Relevant date is the ETL date

## email conv
Notes taken during last implementation changes
November 14, 2018
(Infosec tab!)
We still need corrections on the “Non-Remediation acceptance”.
Bear with me on that, as I realized I gave you wrong specs on this, pointing you to column “AG” (“non-remediation acceptance required” field) of the InfoSec tracker vs the “non-remediation acceptance status” field, which you have now considered. However the mapping requires still a small correction.
Here is the correct mapping of RITA statuses vs column “AH” of the InfoSec tracker:
1. RITA “Complete” = InfoSec tracker “NP1 + Central Acceptance” or InfoSec tracker “completed” (68 in total)-> it seems you have this logic OK.
2. RITA “Work in Progress” = “In progress” (2 in total) -> This one is merged with next one in RITA at the moment
3. RITA “Not Applicable” = “No Acceptance Required” (18 in total) -> This one is merged with previous one in RITA at the moment
That logic is reported in the InfoSec Tracker also in column AH as of row 146.
November 9, 2018
1. I selected “GDPR relevant Flag” to ”yes”, and I exported the data.
In the extracted file I also had the following app which has “GDPR Relevant Flag Calculated” to N and “GDPR Grouping Overrode” to No. shouldn’t this app be excluded from this extract and hence related count on the reporting? [TW] I believe in this case we had a calculated No, but an overwritten Yes. So it would be correct to display this. I don’t remember how this looks in the tables, but if we have two columns one for calculated and one for overwritten, I would recommend to add both into the details table visual. If it is more complex, I would suggest to leave it for now and wait for migration to Numerify.
which fields are you looking at to decide if an app if “GDPR relevant = yes” or “no”? [TW] according to documentation : [GDPR Relevent Flag] = IIF([VolumeOfRecords-For Data Stakeholders from EU countries] = '0' OR nullif([VolumeOfRecords-For Data Stakeholders from EU countries],'') is null,'N','Y')
2. Naming: following fields: “GDPR Grouping Overrode” and “GDPR Grouping Overrode Reason” wouldn’t it make more sense to call them “GDPR Grouping Overwritten” and “GDPR Grouping Overwritten Reason”? [TW]I agree
3. when I select entries in the drop-down “Application Lifecycle Status” and then I close it and reopen, I get an empty screen (I am using chrome), which is annoying as I need to refresh the page to get the list in the drop down again. Do you experience similar issue? Why? (same happens on other picklists…see second screenshot as well about GDPR Grace period) [TW]I have similar issues and sometimes it’s a like frozen. I assume this is related to underlying data selections which are complex. I am sure there is room for improvement = tuning on data level, but we need to discuss whether it makes sense to fix here or also wait for Numerify implementation.
4. Grace Period selection. We said we were going to group the dates into weeks in the drop down (to avoid the issue of having a long list overtime). Moreover it should only show two entries related to the last two weeks. That will allow to select
previous week (say if today is Nov 5 this would be the week of Oct 29) to see the apps that will enter the VP tracker the following week (Nov 12)
previous previous-week (say if if today is Nov 5 this would be the week of Oct 22) this is to see the apps that will enter the VP tracker in two week time (Nov 19)
I still see the pick list “by day”. When are you changing that? [TW]Unfortunately I didn’t take notes when we discussed this ☹, but I didn’t we agree to allow daily selection for the last two weeks OR everything which is already included? This would result in a list of max 11 entries, counting business days only.
November 8, 2018
Inventory details (GBS/IT VP) & Inventory details (Project team)
Trisha to fix the red-highlight. Currently on all cells, it has to be only ion the mandatory fields we reviewed today from VP tracker
Trisha to add the “*” in the extract and online for all mandatory GDPR fields
Trisha to add “owning org level 1” (on top of “owning org level 1 leader) in the extract file
Inventory details other
Not for now. Should be hidden in production until ready
Tanja to show the “cluster” SMOs (DACH, NE, SE, SEE…) vs Europe SMO as “Owning org level 1”
InfoSec (gr 1) & InfoSec (gr 2-3-4)
Numbers shown do not resonate: total gr 1 apps 67 (vs 88) - Trisha to upload latest reports (for both gr 1 and gr 2-3-4) and confirm to Luca when done for testing (including sharing of uploaded files for apple-to-apple comparison)
Red-cell background on both reports is not needed for empty cells (actually confusing). Trisha to remove

## Inventory Details Attributes
GBS Details Reprot | Visible Attributes Inventory Details | Visible Attributes Group 1 Pivot | Incoming Attributes Mega | Incoming Attributes InfoSec Report | Incoming Attributes Other Sources | Calculated Attributes (Formulas)
Data Asset Name
Mega ID
Description Details
Application Nature
Data Asset Type [translated from Nature]
Data Asset Lifecycle Status
Hosting Type
P&G Asset Owner
Owning Organization
AD (Asset Owner reporting line auto derived from ED)
Dir (Asset Owner reporting line auto derived from ED)
VP (Asset Owner reporting line auto derived from ED)
L1 Owning Organization
L1 Owning Organization Leader (VP)
L2 Owning Organization
L2 Owning Organization Leader (Dir)
L3 Owning Organization
L3 Owning Organization Leader (AD)
Vendor Application Manager
Vendor Qualification [Data Controller]
Service Operations Supplier
Service Operations Supplier SAP Code
Software Supplier
Software Supplier SAP Code
Technology Supplier
Technology Supplier SAP Code
Implementation Supplier
Implementation Supplier SAP Code
Other Suppliers
Other Suppliers SAP Code
PII data handled by vendor for specific Business Process / Service
Data Category
In which country are you collecting PII?
Business Process / Service - P&G Hierarchy
Contractual Data: What are the LE(s) receiving the services?
Is the PII data accessed, processed, viewed outside of EU?
Reason for Data Collection
Data Retention Period (Actual policy which is in place)*
Number of P&G Users with Access*
Number of 3rd Party Users with Access*
Volume of Records - for data stakeholders from EU
Volume of Records - for data stakeholders from ALL countries
Government ID, government-issued ID
Credit card numbers*
Financial account number*
Genetic data*
Biometric data*
Sex life, sexual orientation questions*
Data about children under 13*
Criminal or judicial records*
Precise geo location data*
Racial or ethnic origin*
Political opinions, political party affiliation*
Trade union membership*
Protected Health Information (“PHI”) as defined by HIPAA*
Other health or medical data*
Digital signature data*
Data about teens between 13-15 years old*
Consumer account username and password*
Adverse event information*
Identification Data*
Electronic identification data*
Personal characteristics*
Family composition*
Profession*
Image/sound recordings*
Automated Decision Making*
PII for authentication/ authorization only
PII Risk Level
Data Classification
Last Reviewed Date
iRisk Last Performed
App Management CSA Last Performed
[6 empty] | InfoSec Classification | [InfoSec Classification] = IIF([DataType-PrivacyRisk] = 'High' OR [DataType-PrivacyRisk] ='Medium','Highly Restricted','Business Use')
[6 empty] | GDPR Relevant Flag (manual/ RITA) | [GDPR Relevent Flag] = Unless keyword "ITAM - GDPR: Relevance: xxx" is set, calculate this: IIF([VolumeOfRecords-For Data Stakeholders from EU countries] = '0' OR nullif([VolumeOfRecords-For Data Stakeholders from EU countries],'') is null,'N','Y')
[6 empty] | COMPLETENESS % | Checks number of nulls in 50 fields in Mega. Check these 50 fields in the first table in ‘VP Gap Tracker’ tab in GDPR VP Analysis report. Completeness% = (1-count/50)*100 Here's the list of fields [for SAP Codes, also "-" count as gap!] *Description Details *Application Nature *Data Asset Lifecycle Status *Owning Org Leader Level 1 *Owning Organization *P&G Asset Owner *Vendor Qualification [Data Controller] *Service Operations Supplier SAP Code *Software Supplier SAP Code *Technology Supplier SAP Code *Implementation Supplier SAP Code *Other Suppliers SAP Code *PII data handled by vendor for specific Business Process / Service *Data Category *In which country are you collecting PII? *Business Process / Service - P&G Hierarchy *Contractual Data: What are the LE(s) receiving the services? *Is the PII data accessed, processed, viewed outside of EU? *Reason for Data Collection Data Retention Period (Actual policy which is in place)* Number of P&G Users with Access* Number of 3rd Party Users with Access* *Volume of Records - for data stakeholders from EU *Volume of Records - for data stakeholders from ALL countries *Government ID, government-issued ID *Credit card numbers* *Financial account number* *Genetic data* *Biometric data* *Sex life, sexual orientation questions* *Data about children under 13* *Criminal or judicial records* *Precise geo location data* *Racial or ethnic origin* *Political opinions, political party affiliation* *Trade union membership* *Protected Health Information (“PHI”) as defined by HIPAA* *Other health or medical data* *Digital signature data* *Data about teens between 13-15 years old* *Consumer account username and password* *Adverse event information* *Identification Data* *Electronic identification data* *Personal characteristics* *Family composition* *Profession* *Image/sound recordings* *Automated Decision Making* *PII Risk Level | In case more than one supplier is mapped, we need the code for ALL suppliers - otherwise it counts as a gap and will affect % completeness
[6 empty] | GDPR Grouping | [GDPR Relevent Flag] = Unless keyword "ITAM - GDPR: Grouping: xxx" is set, calculate following these instructions: | https://pgone.sharepoint.com/:p:/r/sites/PG-ITAM/ITAM%20Internal%20Documents/ITAM%20e-Documents/SR20%20-%20Reporting%20IT%20Assets%20(RITA)/SR208e%20NumeRITA/RequTest/GDPR/CR53_77_GDPR%20GBS-IT%20grouping%20logic-2018-10-23.pptx?d=wfa5b986f7fb54f2c873d3f5b81e3a3cf&csf=1&e=N501np
[6 empty] | Service Line | WILL BE USED TO calculate grouping instead of VP
App Mgr Email
ease Hyperlink
[6 empty] | GDPR Group Overrode | It is flagged to be ‘Yes’ when the GDPR Grouping of the application has been overridden in Mega (you will get this through PGB_APP_KEYWORD.csv), the “overwritten” value will take precedence over the calculated.
[6 empty] | GDPR Relevance Overrode | It is flagged to be ‘Yes’ when the GDPR Relevance of the application has been overridden in Mega (you will get this through PGB_APP_KEYWORD.csv), the “overwritten” value will take precedence over the calculated.
Decommission Date
[6 empty] | Date Added to this Report (Grace Period) | lifecycle status, VP name/SL, Appnature, GDPR Relevance, Privacy Risk -> if any of those change so that the Application gets in scope of GDPR, then we put a "Start date"
[5 empty] | GDPR Group Overrode Reason |  | (who/ when/ why)
[5 empty] | GDPR Grouping Calculated |  | value before Overrode took place
Note on H11: Wojdyno, Tanja: using translation table in case Mega name is too complex or too detailed - this org name sould be on VP level
Note on E15: Wojdyno, Tanja: whitelist!
Note on H76: Wojdyno, Tanja: for Infosec not GDPR
Note on H77: Wojdyno, Tanja: may be calculated by input from "PII... Business process" and "# of EU stakeholders " - check in RITA
Note on H78: Wojdyno, Tanja: counting the columns where names starts with "*"
Note on H79: Wojdyno, Tanja: simplified
Note on H80: Wojdyno, Tanja: derived from new field "owning organization"

## DESIGN
Owner | Current XLS Report Name | New RITA Report | Page | Timeline | Comment
Luca | GDPR VP Tracker/ GBS VP Analysis | GDPR Application Tracker | Inventory Details (GBS/IT VP) | Jan | for VPs
Luca | GDPR VP Tracker/ GBS VP Analysis | GDPR Application Tracker | Inventory Details - In process (Proj Team) | Jan | for Project team (visibility to new items and those which have been manually flagged as "not relevant"
Luca | GDPR VP Tracker/ GBS VP Analysis | GDPR Application Tracker | Infosec Compliance - #(GBS/IT VP) | tbc | mid-term sourcing from iRisk (Q3)
Luca | GDPR VP Tracker/ GBS VP Analysis | GDPR Application Tracker | Infosec Compliance - % (GBS/IT VP) | tbc
|  | GDPR Application Tracker | Privacy Compliance (GBS/IT VP) |  | tbc Application or PA Compliance
|  | GDPR Application Tracker | Inventory Details (non GBS/IT VP) | tbc
|  | GDPR Application Tracker | Infosec Compliance - # (non GBS/IT VP) | tbc
|  | GDPR Application Tracker | Infosec Compliance - % (non GBS/IT VP) | tbc
|  | GDPR Application Tracker | Privacy Compliance (non GBS/IT VP) |  | tbc Application or PA Compliance
|  | GDPR Application Tracker | Infosec Dashboard (all) | tbc
Alessio | Compliance... | Compliance Dashboard | Owning Orgs | Jan
Alessio | Compliance... | Compliance Dashboard | GDPR Core Team | Jan
Alessio | Compliance... | Compliance Dashboard | Lawyers | Jan
Alessio | Compliance... | Compliance Dashboard | R&D Owning Org | Jan
|  | Compliance Dashboard | GAP AREAS ONLY | Jan | tbc. whether included in base views (slicer for gap areas) or as a separate view
Evgeny | Complete... | Dashboard/ Data Extracts | Data Assets | Jan
Evgeny | Complete... | Dashboard/ Data Extracts | Processing Activities | Jan

## Design Inventory Details GBSIT
INVENTORY DETAILS
[11 empty] | ... | build on existing VP Tracker report page!
Any click on an area in the upper visual will result in selected scope display in the lower visual (details table)
All scope: default and easy to acces (click on total)
Columns in details table: see sequence below
Highlight gaps (as reflected in % completeness) in red
Update Oct 24
|  |  | Total Applications | Average Completeness of Records [Numer of Apps ¦ % Data Field Completeness] |  | ... | ... |  | Inventory Gaps
| Owning Org* | Owning Org Leader | # | % | # | % | … | … | # | %
| FSS | Laura Becker | 132 | 15.6% | 124 | 98.6% |  |  | 8 | 6.1%
| … | … | … | … | … | … | … | … | … | …
* | whitelisted which to filter + Unknown = where empty in Mega!
Details Table - Column Sorting/ Grouping:
Data Asset Name
Mega ID
| COMPLETENESS % | important classifications
L1 Organization Leader
Owning Organization
GDPR GROUPING
| Description Details | inventory information mostly used to assess % completeness
Application Nature
Data Asset Type [translated from Nature]
Data Asset Lifecycle Status
Hosting Type
P&G Asset Owner
Vendor Application Manager
Vendor Qualification [Data Controller]
Service Operations Supplier
Service Operations Supplier SAP Code
Software Supplier
Software Supplier SAP Code
Technology Supplier
Technology Supplier SAP Code
Implementation Supplier
Implementation Supplier SAP Code
Other Suppliers
Other Suppliers SAP Code
PII data handled by vendor for specific Business Process / Service
Data Category
In which country are you collecting PII?
Business Process / Service - P&G Hierarchy
Contractual Data: What are the LE(s) receiving the services?
Is the PII data accessed, processed, viewed outside of EU?
Reason for Data Collection
Data Retention Period (Actual policy which is in place)
Number of P&G Users with Access
Number of 3rd Party Users with Access
Volume of Records - for data stakeholders from EU
Volume of Records - for data stakeholders from ALL countries
Government ID, government-issued ID
Credit card numbers
Financial account number
Genetic data
Biometric data
Sex life, sexual orienation questions
Data about children under 13
Criminal or judicial records
Precise geo location data
Racial or ethnic origin
Political opinions, political party affiliation
Trade union membership
Protected Health Information (“PHI”) as defined by HIPAA
Other health or medical data
Digital signature data
Data about teens between 13-15 years old
Consumer account username and password
Adverse event information
Identification Data
Electronic identification data
Personal characteristics
Family composition
Profession
Image/sound recordings
Automated Decision Making
PII for authentication/ authorization only
PII Risk Level
iRisk Last Performed
| L3 Owning Organization | not super important but helpful
L3 Owning Organization Leader (AD)
L2 Owning Organization
L2 Owning Organization Leader (Dir)
AD (Asset Owner reporting line auto derived from ED)
Dir (Asset Owner reporting line auto derived from ED)
VP (Asset Owner reporting line auto derived from ED)
Decommission Date
Last Reviewed Date
Data Classification
App Management CSA Last Performed
InfoSec Classification
App Mgr Email
ease Hyperlink

## Design Inventory Details - In p
INVENTORY DETAILS - IN PROCESS
Same as Inventory Details but with less filtering and additional slicers: include all lifecycle status, include all MANUALLY flagged as "not relevant", all within Grace Period
GDPR Relevance | Lifecycle Status | Grace Period - Visibility Date
Y [DEFAULT] | All [DEFAULT] | All [DEFAULT]
Overwritten to "N" | All except Discovery | <dates>
|  |  |  | ... | build on existing VP Tracker report page!
Any click on an area in the upper visual will result in selected scope display in the lower visual (details table)
All scope: default and easy to acces (click on total)
Columns in details table: see sequence below
Highlight gaps (as reflected in % completeness) in red
Same details columns as in "Inventory Details" but in addition 5 columns that reflect those out of scope and why
Data Asset Name
Mega ID
COMPLETENESS %
L1 Organization Leader
Owning Organization
GDPR GROUPING
GDPR Relevant Flag Calculated
GDPR Group Overrode
GDPR Group Overrode Reason
GDPR Grouping Calculated
Date Added to this Report (Grace Period)
...
Note on D7: Wojdyno, Tanja: All excludes initially filtered out decommissioned, not used etc.

## Design Inventory Details nonGBS
INVENTORY DETAILS non GBS/IT
Exactly the same as Inventory Details for GBS/IT, except:
Owning Org Level 1 - show only what is NOT whitelisted for GBS/IT
do NOT use grace period to filter out
Lifecylcle status?
App. Nature?

## General Requirements
Data Dictionary | consistent naming of attributes
Grace Period | aligned Grace Periods (ROPAs, Data Assets)
Owning Organization | consistent naming/ consolidation across all reports esp. GBS - see file "https://pgone.sharepoint.com/:x:/r/sites/PG-ITAM/ITAM%20Internal%20Documents/ITAM%20e-Documents/SR20%20-%20Reporting%20IT%20Assets%20(RITA)/SR208e%20NumeRITA/RequTest/GDPR/PGV_ORG_ITAM_GBS%20mapping%20OT.xlsx?d=w6a4ddfb24dc44668b8548b8e014ccc7b&csf=1&e=Tz7DXj"
Easy Data Extracts in Excel | details table, but also visuals

## Legend
Legend
tab colors indicate which report the information belongs to
Flag priorities using color coding [critical - black, nice to have - blue]
Open design items in yellow