## Test Case Templates (hidden)
INDEX
Test Scripts
TC_No | Test Scenario | Test Description | Test Steps | Expected Result | Actual Result | Priority | Status
TC_01 | To Verify the Attributes in MSTR ITSA_Incident_C Cube. | To verify and validate the Incident Attributes in ITSA_Incident_C Cube | Prerequisite | Login to Prod dev 5.1 Upgrade MSTR Web application | User should be able to login to the respective application. | 1-High | Completed. Complete Attribute validaiton screen shots are attached in below document.
|  |  | Step1 | Login to Gilead Tenant and Navigate to the ITSA_Incident_C Cube. | User should be able to navigate to the ITSA_Incident_C cube.
|  |  | Step2 | Verify the all the respective attribute are available. | All the Attributes should be available in Prod dev instance,compaired to Prod instance.
|  |  | Step3 | Verify the Values respective to DB
|  |  | Step4 | Verify the below aspects in the Incident cube: 1.Validate the format. 2.Validated the ascending and descending orders. 3.Validated the filter options. 4.Validated the Apps 5.0 Upgrade Changes both OOTB and Customization Changes. | All the below should be validated: 1.Validate the format. 2.Validated the ascending and descending orders. 3.Validated the filter options. 4.Validated the Apps 5.0 Upgrade Changes both OOTB and Customization Changes.
TC_02 | To Verify the Metrics in MSTR ITSA_Incident_C Cube. | To verify and validate the Incident Metrics in ITSA_Incident_C Cube | Prerequisite | Login to Prod dev 5.1 Upgrade MSTR Web application | User should be able to login to the respective application. | 1-High | Completed. Complete Metric validaiton screen shots are attached in below document.
|  |  | Step1 | Login to Gilead Tenant and Navigate to the ITSA_Incident_C Cube. | User should be able to navigate to the ITSA_Incident_C cube.
|  |  | Step2 | Verify the all the respective Metrics are available. | All the Metrics should be available in Prod dev instance,compaired to Prod instance.
|  |  | Step3 | Verify the Values respective to DB
|  |  | Step4 | Verify the below aspects in the Incident cube: 1.Validate the format. 2.Validated the ascending and descending orders. 3.Validated the filter options. 4.Validated the Apps 5.0 Upgrade Changes both OOTB and Customization Changes. | All the below should be validated: 1.Validate the format. 2.Validated the ascending and descending orders. 3.Validated the filter options. 4.Validated the Apps 5.0 Upgrade Changes both OOTB and Customization Changes.

## INDEX
SL No | INDEX
1 | Environment and Statistics
2 | Test Cases - Funtional
3 | Test Results - Functional
4 | Test Cases - ETL
5 | Test Results - ETL
6 | Test Cases - Cube Count
7 | Test Results - Cube Count
8 | Test Cases - MSTR
9 | Test Results - MSTR
10 | Regression Results
11 | References

## Cubes & DD Details (hidden)
INDEX
S no | CUBE | Cube | Place | path | Teant | Instance | QA Cube Query | Remark
1 | PUBLISH INTELLIGENT CUBE | ITSM_Incident_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
2 | PUBLISH INTELLIGENT CUBE | ITSM_Request Item | IN FOLDER | Public Objects\Reports\ITSA\iCubes | Numerify_BI_Gilead. | PROD | OOTB
3 | PUBLISH INTELLIGENT CUBE | ITSM_TASK FSS_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
4 | PUBLISH INTELLIGENT CUBE | ITSM_Request Task_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
5 | PUBLISH INTELLIGENT CUBE | ITSM_Survey C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
6 | PUBLISH INTELLIGENT CUBE | ITSM_Request Item_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | No Updates required | No count drops
7 | PUBLISH INTELLIGENT CUBE | ITSM_Request Task Keyword | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
8 | PUBLISH INTELLIGENT CUBE | ITSM_TASK_FSS_C Keyword | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
9 | PUBLISH INTELLIGENT CUBE | CMDB CI Weekly Trend_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead. | PROD | Updated | No count drops
10 | PUBLISH INTELLIGENT CUBE | ITSM_Reassignment_C | IN FOLDER | Public Objects\Reports\ITSA\Customizations\Icubes | Numerify_BI_Gilead | PROD | Updated | Count drops in ldb.d_incident and ldb.d_incident_state : Marking it has a known issues
S no | Customized Cube | Path | QA Status | Remark | Open JIRA
1 | ITSA_ Incident _C | Shared Insight-> ITSA->iCubes | Completed | Working fine | DELV-6582
2 | ITSA_ Request Task _C | Shared Insight-> ITSA->iCubes | Completed | Working fine
3 | CMDB CI Weekly Trend _C | Shared Insight-> ITSA->iCubes | Completed | Working fine
4 | ITSA_ Survey C | Shared Insight-> ITSA->iCubes | Completed | Working fine
5 | ITSA_Reassignment_C | Shared Insight-> ITSA->iCubes | Completed | Working fine
6 | ITSM_ Request Item _C | Shared Insight-> ITSA->iCubes | Completed | Working fine
7 | ITSM_ Request Task Keyword | Shared Insight-> ITSA->iCubes | Not Yet Started
8 | ITSM_TASK FSS_C | Shared Insight-> ITSA->iCubes | Not Yet Started
9 | ITSM_TASK_FSS_C Keyword | Shared Insight-> ITSA->iCubes | Not Yet Started
S no | Dashboard | Path | QA Status | Remark
1 | Request item Overview | Landing Page | Not Yet Started
2 | Opened Overview | Landing Page | Not Yet Started
3 | Backlog Trend Analysis | Landing Page | Not Yet Started
4 | Open Work by Assignee | Landing Page | Not Yet Started
5 | Resolved-Overview | Landing Page | Not Yet Started
6 | Incident Keyword Overview | Landing Page | Not Yet Started
7 | Incident Keyword Analysis | Landing Page | Not Yet Started
8 | CI Incident Analysis | Landing Page | Not Yet Started
9 | P1 & P2 Incident Analysis | Landing Page | Not Yet Started
10 | FSS Overview | Landing Page | Not Yet Started
11 | SLA Overivew | Landing Page | Not Yet Started
12 | Survey Overview | Landing Page | Not Yet Started
13 | Incident Analysis | Landing Page | Not Yet Started
14 | Request Item Analysis | Landing Page | Not Yet Started
15 | Catalog Task Analysis | Landing Page | Not Yet Started
16 | FSS Analysis | Landing Page | Not Yet Started
17 | SLA Analysis | Landing Page | Not Yet Started
18 | Survey Analysis | Landing Page | Not Yet Started
19 | Browse Dashbaorad | Landing Page | Not Yet Started
Sno | Dashboard Name | Dashboard Path | Total Job Count | QA Status | Remark
1 | Completeness | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevCMDBCompleteness | 8663 | Not Yet Started
2 | Customer Satisfaction Survey | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardCustomer Satisfaction Survey | 4569 | Not Yet Started
3 | OLDSPARC Ops FSS - TASK0243845 | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDecommissionedOLDSPARC Ops FSS - TASK0243845 | 3426 | Not Yet Started
4 | MisRouted Tickets | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASOMisRouted Tickets | 3207 | Not Yet Started
5 | New Dashboard | IS:\Numerify_BI_Gilead\Object Templates\Analysis | 2289 | Not Yet Started
6 | RITM0226543 - Customer Satisfaction Survey | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASORITM0226543 - Customer Satisfaction Survey | 1314 | Not Yet Started
7 | Vendor Management Dashboard | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevStandardVendor Management Dashboard | 1279 | Not Yet Started
8 | Standard SLA | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardStandard SLA | 1196 | Not Yet Started
9 | Customer Satisfaction Survey | IS:\Numerify_BI_Gilead\Public Objects\Reports\ITSA\Gilead\Production\Standard | 985 | Not Yet Started
10 | CMDB Application | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevCMDBCMDB Application | 872 | Not Yet Started
11 | Landing Page_Gilead_JB | Numerify_BI_GileadPublic ObjectsReportsCommonLanding Page_Gilead_JB | 812 | Not Yet Started
12 | Standard SLA | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardStandard SLA (Monthly) | 805 | Not Yet Started
13 | Backlog Trend Analysis | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardBacklog Trend Analysis | 798 | Not Yet Started
14 | Incident Reassignment | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardIncident Reassignment | 790 | Not Yet Started
15 | Ageing Incidents & Requests | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardAgeing Incidents & Requests | 782 | Not Yet Started
16 | RITM0149553 - Resource productivity | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDecommissionedRITM0149553 - Resource productivity | 713 | Not Yet Started
17 | SPARC Ops FSS - TASK0243845 | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevFSSSPARC Ops FSS - TASK0243845 | 660 | Not Yet Started
18 | MisRouted Incidents | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionStandardMisRouted Incidents | 654 | Not Yet Started
19 | Weekly Open & Closed Trend Analysis | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASOWeekly Open & Closed Trend Analysis | 608 | Not Yet Started
20 | Landing Page_Gilead_JB | IS:\Numerify_BI_Gilead\Public Objects\Reports\Common | 554 | Not Yet Started
21 | SPARC Ops FSS - TASK0243845 | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionFSSSPARC Ops FSS - TASK0243845 | 532 | Not Yet Started
22 | RITM0149547 Ageing Incidents & Requests | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASORITM0149547 Ageing Incidents & Requests | 516 | Not Yet Started
23 | RITM0149549 - Monthly Open & Closed Trend Analysis | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASORITM0149549 - Monthly Open & Closed Trend Analysis | 485 | Not Yet Started
24 | Completeness – TESMify | Numerify_BI_GileadPublic ObjectsReportsITSAGileadDevTMICompleteness – TESMify | 482 | Not Yet Started
25 | RITM0149550 - Reopened and Reassigned | Numerify_BI_GileadPublic ObjectsReportsITSAGileadProductionASORITM0149550 - Reopened and Reassigned | 447 | Not Yet Started

## Environment and Statistics
INDEX
Environment Details
PROD DEV POD details
Prod Dev MSTR Link
PROD POD details
Prod MSTR Link
SL No | Date | Task details | Environment | Remarks
1 |  | Full load/data patch
2
3
Total Deployments/loads
Total QA Defects
Total Retests

## Test Cases - Funtional
INDEX
TC_No | Test Case | Test Description | Expected Result | Actual Result | Result | Defect JIRA # | Comments
1 | DELV-18473 | P&G: CMDB data to come from Snow instead of MEGA | All the Rita Appliction from the CSV file should be intergated to Service Now.

## RITA Application_C
S No | Attribute | Prod Dev | Source | Prod
1 | *# of 3rd Party Resources With Access | Only Unknowns are displaying | Mega
2 | *# of P&G Users With Access | Only Unknowns are displaying
3 | *Adverse Medical Event Information | Only Having N Values |  | N and Y values
4 | *Application Description | Completed and working fine
5 | *Application Lifecycle Status
6 | *Application Nature
7 | *Application Nature (Internal)
8 | *Automated Decision Making | Working fine
9 | *Biometric Data | Only N
10 | *Consumer Account Username And Password | Only N
11 | *Credit Card Numbers | Only N
12 | *Criminal Or Judicial Records | Only N
13 | *Data About Children Under 13 | Only N
14 | *Data About Teens Between 13-15 Years Old | Only N
15 | *Data Category | UNSPECIFED is not handled
16 | *Data Retention Period In Days | Blank
17 | *Digital Signature Data | Only N
18 | *Electronic Identification Data | Only N
19 | *Family Composition | Only N
20 | *Financial Account Number | Only N
21 | *Genetic Data | Only N
22 | *Government ID ,Government-issued ID | Only N
23 | *Identification Data | Only N
24 | *Image/Sound Recordings | Only N
25 | *Implementation Supplier Name | Both Values are same as per the New codes
26 | *Implementation Supplier SAP Code
27 | *In Which Country Are You Collecting PII? | Working fine
28 | *Is The PII Data Accessed, Processed, Viewed Outside Of The EU? | Blank
29 | *L3 Business Processes | Working fine
30 | *LE(s) receiving the services? | Working fine
31 | *Other Health Or Medical Data | Only N
32 | *Other Supplier Name | Unspecified and Blank
33 | *Other Supplier SAP Code
34 | *Owning Org Level 1 Leader | Working fine
35 | *Owning Organization | Working fine
36 | *P&G Asset Owner | Working fine
37 | *Personal Characteristics | Only N
38 | *PII Data Handled For Specific Business Process | only UNSPECIFED
39 | *Political Opinions, Political Party Affiliation | Only N
40 | *Precise Geo Location Data | Only N
41 | *Privacy Risk | UNSPECIFED
42 | *Profession | Only N
43 | *Protected Health Information as Defined By HIPAA | Only N
44 | *Racial Or Ethnic Origin | Only N
45 | *Reason For Data Collection | Null
46 | *SAP Vendor(s) Name | Both Values are same as per the New codes
47 | *SAP Vendor(s) Number
48 | *Service Operation Supplier Name | Both Values are same as per the New codes
49 | *Service Operation Supplier SAP Code
50 | *Sex Life, Sexual Orientation Questions | Only N
51 | *Software Supplier Name | Both Values are same as per the New codes
52 | *Software Supplier SAP Code
53 | *Technology Supplier Name | Working fine
54 | *Technology Supplier SAP Code | Working fine
55 | *Trade Union Membership | Only N
56 | *Vendor Qualification | UNKNOWN
57 | *Volume Of Records - ALL countries | Working fine
58 | *Volume of Records - EU countries | Working fine
59 | App Mgr Email | Blank
60 | App Mgr Name | Blank
61 | Application GDPR Grouping Name Calculated | N/A
62 | Application ID | Working fine
63 | Application Repository Sub Type | UNKNOWN
64 | Application Repository Type | UNKNOWN
65 | Behavioral Data | Working fine
66 | Birthdate | Working fine
67 | Browser Cookie Data | Working fine
68 | Comments / Other Information About The Application | Blank
69 | Data About Teens 16-18 | Working fine
70 | Data Asset Name | Working fine
71 | Data Classification | Have Unknow - Public Information is not avaialble
72 | Data Elements Combined Flag | Working fine
73 | Data Subject Rights Result | UNKNOWN
74 | DataRetentionDefImplemented | Blank
75 | DataRetentionEvidence | Blank
76 | DataRetentionStatus | UNKNOWN
77 | DataSubjRightsCentralTeam | Blank
78 | DataSubjRightsEvidence | Blank
79 | DPIA: Result | UNKNOWN
80 | DPIA: Status | UNKNOWN
81 | DpiaDonebyLegal | Blank
82 | DpiaEvidence | Blank
83 | Ease Hyperlink | Blank
84 | Email address | Working fine
85 | Employee Account Username and Password | Working fine
86 | Employee Band Level | Working fine
87 | Employee T# | Working fine
88 | Employee Work Location | Working fine
89 | Gap and NoGap Applications | Not working as expected
90 | GDPR Flagoverrode Flag | Not working as expected
91 | GDPR Grouping | Working fine
92 | GDPR Grouping Overrode Flag | Logic is not working as expected then compaired to PROD instance
93 | GDPR Relevant Flag
94 | GDPR Relevant Flag Calculated
95 | GDPR Sensitivity | UNSPECIFIED case is not handeled
96 | Gender | Working fine
97 | Geographic Data, Imprecise (not within 3.2187KM) | Working fine
98 | Grace Period | Not working as expected
99 | Grace Period Flag
100 | Grace Period Start Date
101 | Hosting Type | List is not matched with current PROD instance
102 | Information Which Contans Pseudonymized Data | Working fine
103 | InfoSec Classification | Blank
104 | InventoryEvidence | Blank
105 | InventoryKeptUptoDate | Blank
106 | InventoryResult | UNKNOWN
107 | InventoryStatus | UNKNOWN
108 | IP Address | Working fine
109 | IRisk Last Performed | Blank
110 | L0 Owning Organization | Working fine
111 | L1 Owning Organization | Working fine
112 | L2 Owning Organization | Working fine
113 | L2 Owning Organization Leader (Dir) | Working fine
114 | L3 Owning Organizaiton | Working fine
115 | L3 Owning Organization Leader (AD) | Working fine
116 | Last Reviewed Date | Working fine
117 | Lawful BasisResult | UNKNOWN
118 | Lawful BasisStatus | UNKNOWN
119 | LawfulnessBasisEvidence | Blank
120 | LawfulnessBasisProcessing | Blank
121 | Mac Address | Working fine
122 | Marital Status | Working fine
123 | Mega Creation Date | Working fine
124 | Mega ID | Working fine
125 | Mega Update Date | Working fine
126 | Minimization | Blank
127 | MinimizationEvidence | Blank
128 | Mobile device Ids | Working fine
129 | Mobile Phone Number | Working fine
130 | Name | Working fine
131 | NoticeEvidence | Blank
132 | NoticeProcessing | Blank
133 | NoticesResult | UNKNOWN
134 | NoticesStatus | UNKNOWN
135 | Other (e.g. customer) Account Username and Password | Working fine
136 | Other demographic and behavioral data gathered online | Working fine
137 | PG CSA Last Performed | Blank
138 | Phone Numbers (not Mobile) | Working fine
139 | PII for authentication/ authorization only | No, Yes and Unspecified |  | only No or yes
140 | Postal address | Working fine
141 | Project Team GDPR Relevant Overwritten Flag | Only N
142 | Reasonable InfoSec: Result | UNKNOWN
143 | Reasonable InfoSec: Status | UNKNOWN
144 | ReasonInfosecUctrl | Blank
145 | ReasonInfosecUctrlEvidence | Blank
146 | Retired Date(Decommission) | Working fine
147 | Salary amount or level | Working fine
148 | Salary or benefits data | Working fine
149 | Scope Doc Name | Blank
150 | Snow ID | Blank
151 | Source Type | UNKNOWN
152 | Vendor Manager | Working fine
153 | VendorsEvidence | Blank
154 | VendorsPrivacyInfosecUpdated | Blank
155 | VendorsResult | UNKNOWN
156 | VendorsStatus | UNKNOWN
157 | Zip codes | Working fine
S No | Metrics | Prod dev |  | PROD
1 | # GDPR 1 Total Application | Completed and Working fine
2 | # GDPR 2 Total Application | Completed and Working fine
3 | # GDPR 3 Total Application | Completed and Working fine
4 | # GDPR 4 Total Application | Completed and Working fine
5 | # GDPR Ungrouped Application | Completed and Working fine
6 | # Inventory Gaps | Completed and Working fine
7 | # Of Complete Applications | Completed and Working fine
8 | # Of Total Applications | Completed and Working fine
9 | % Data Field Completeness | Completed and Working fine
10 | % Inventory Gaps | Completed and Working fine
11 | % Total Application Org Level 1 | Completed and Working fine
12 | Row Count | Completed and Working fine
13 | Total Application Org Level 1 | Completed and Working fine
| PROD Dev |  |  | PROD
| # GDPR 1 Total Application | 1015 |  | # GDPR 1 Total Application | 1015
| # GDPR 2 Total Application | 307 |  | # GDPR 2 Total Application | 307
| # GDPR 3 Total Application | 1058 |  | # GDPR 3 Total Application | 1058
| # GDPR 4 Total Application | 1430 |  | # GDPR 4 Total Application | 1430
| # GDPR Ungrouped Application | 57539 |  | # GDPR Ungrouped Application | 57445
| # Inventory Gaps | 60470 |  | # Inventory Gaps | 60375
| # Of Complete Applications | 879 |  | # Of Complete Applications | 880
| # Of Total Applications | 61349 |  | # Of Total Applications | 61255
| % Data Field Completeness | 12.45% |  | % Data Field Completeness | 12.46%
| % Inventory Gaps | 98.57% |  | % Inventory Gaps | 98.56%
| % Total Application Org Level 1 | 100% |  | % Total Application Org Level 1 | 100%
| Row Count | 61349 |  | Row Count | 61255
| Total Application Org Level 1 | 61349 |  | Total Application Org Level 1 | 61255
Metric validation

## RITA_Application_Governance_C
S No | Attribute | Source | UAT Validation | PROD Instance | VI Changes
1 | Always On CBP
2 | App Owner Employee Type
3 | App Owner Validity (y/n)
4 | Application Description
5 | Application ID
6 | Application Name
7 | Application Owner Email Address
8 | Application Owner Full Name
9 | Application/Technology Nature
10 | BIA Rating for Availability
11 | BIA Rating for Confidentiality
12 | BIA Rating for Integrity
13 | Business Process
14 | Commissioning Memo Date Approved
15 | Commissioning Memo Document Link
16 | CREATIONDATE
17 | CREATOR
18 | Critical Apps
19 | Data Privacy
20 | Data Classification
21 | Data Correctness
22 | Data Currentness
23 | Data Privacy
24 | Data Retention Period (Actual policy which is in place)
25 | Database
26 | EA Data Compliance
27 | EA Missing Data
28 | Hex Ext ID (Internal)
29 | Hex ID (Internal)
30 | Hosting
31 | Implementation Supplier
32 | Instance
33 | iRisk Data Compliance
34 | iRisk Date
35 | Keyword-Subject Area
36 | L0 Owning Organization
37 | Last Reviewed Date
38 | Lead Solution Architect
39 | License
40 | Life Cycle Status
41 | Link to EASE
42 | Owning Organization
43 | Owning Organization Level 1
44 | Owning Organization Level 1 Leader
45 | Owning Organization Level 2
46 | Owning Organization Level 2 Leader
47 | Owning Organization Level 3
48 | Owning Organization Level 3 Leader
49 | P&G Application Owner
50 | RAMP Date
51 | RAMP Location
52 | Registration Data Compliance
53 | Registration Missing Data
54 | Registration Overall Compliance
55 | Regulated System
56 | Release
57 | Server
58 | Service Operations Supplier
59 | Site Name
60 | Snow ID
61 | Sox Classification
62 | Standard
63 | Technology Supplier
64 | Validation Data Compliance
65 | Validation Missing Data
66 | Vendor Software Supplier
S No | Metrics |  | Prod dev | PROD
1 | # of Data Correct Applications |  | Completed and Working fine
2 | # of Data Current Applications |  | Completed and Working fine
3 | # of Data InCorrect Applications |  | Completed and Working fine
4 | # of EA Compliant Applications |  | Completed and Working fine
5 | # of EA Non Compliant Applications |  | Completed and Working fine
6 | # of IT Risk Assessment Complete Applications |  | Completed and Working fine
7 | # of IT Risk Assessment InComplete Applications |  | Completed and Working fine
8 | # of Non Current Applications |  | Completed and Working fine
9 | # of Registration Complete Applications |  | Completed and Working fine
10 | # of Registration Compliant Applications |  | Completed and Working fine
11 | # of Registration InComplete Applications |  | Completed and Working fine
12 | # of Registration Non Compliant Applications |  | Completed and Working fine
13 | # of Validation Compliant Applications |  | Completed and Working fine
14 | # of Validation Non Compliant Applications |  | Completed and Working fine
15 | % Data Complete |  | Completed and Working fine
16 | % Data Correct |  | Completed and Working fine
17 | % Data Current |  | Completed and Working fine
18 | % EA Compliance |  | Completed and Working fine
19 | % IT Risk Assessment |  | Completed and Working fine
20 | % Legal Validation Compliance |  | Completed and Working fine
21 | % of EA Compliance Apps |  | Completed and Working fine
22 | % of Registration Compliant Apps |  | Completed and Working fine
23 | % of Registration Data Complete Apps |  | Completed and Working fine
24 | % of Registration Data Correct Apps |  | Completed and Working fine
25 | % of Registration Data Current Apps |  | Completed and Working fine
26 | % of Validation Compliance Apps |  | Completed and Working fine
27 | % Registration Compliance |  | Completed and Working fine
28 | % Risk Completeness |  | Completed and Working fine
29 | Data Correct |  | Completed and Working fine
30 | Data Current |  | Completed and Working fine
31 | Row Count |  | Completed and Working fine
32 | Total # of Apps |  | Completed and Working fine
| Prod Dev |  |  | PROD instance
| # of Data Correct Applications |  | 7135 | # of Data Correct Applications | 7029
| # of Data Current Applications |  | 4826 | # of Data Current Applications | 4866
| # of Data InCorrect Applications |  | 1737 | # of Data InCorrect Applications | 1749
| # of EA Compliant Applications |  | 730 | # of EA Compliant Applications | 729
| # of EA Non Compliant Applications |  | 8142 | # of EA Non Compliant Applications | 8049
| # of IT Risk Assessment Complete Applications |  | 1010 | # of IT Risk Assessment Complete Applications | 1007
| # of IT Risk Assessment InComplete Applications |  | 7862 | # of IT Risk Assessment InComplete Applications | 7771
| # of Non Current Applications |  | 4046 | # of Non Current Applications | 3912
| # of Registration Complete Applications |  | 4207 | # of Registration Complete Applications | 4218
| # of Registration Compliant Applications |  | 3478 | # of Registration Compliant Applications | 3485
| # of Registration InComplete Applications |  | 4665 | # of Registration InComplete Applications | 4560
| # of Registration Non Compliant Applications |  | 5394 | # of Registration Non Compliant Applications | 5293
| # of Validation Compliant Applications |  | 14 | # of Validation Compliant Applications | 14
| # of Validation Non Compliant Applications |  | 8858 | # of Validation Non Compliant Applications | 8764
| % Data Complete |  | 89.5056 | % Data Complete | 89.6757
| % Data Correct |  | 80.4216 | % Data Correct | 80.0752
| % Data Current |  | 54.3959 | % Data Current | 55.434
| % EA Compliance |  | 21.5594 | % EA Compliance | 21.4343
| % IT Risk Assessment |  | 11.3841 | % IT Risk Assessment | 11.4719
| % Legal Validation Compliance |  | 0.79745 | % Legal Validation Compliance | 0.80599
| % of EA Compliance Apps |  | 8.2281 | % of EA Compliance Apps | 8.3049
| % of Registration Compliant Apps |  | 39.202 | % of Registration Compliant Apps | 39.7015
| % of Registration Data Complete Apps |  | 47.4188 | % of Registration Data Complete Apps | 48.0519
| % of Registration Data Correct Apps |  | 80.4216 | % of Registration Data Correct Apps | 80.0752
| % of Registration Data Current Apps |  | 54.3959 | % of Registration Data Current Apps | 55.434
| % of Validation Compliance Apps |  | 0.1578 | % of Validation Compliance Apps | 0.15949
| % Registration Compliance |  | 74.7743 | % Registration Compliance | 75.0616
| % Risk Completeness |  | 11.3841 | % Risk Completeness | 11.4719
| Data Correct |  | 7135 | Data Correct | 7029
| Data Current |  | 4826 | Data Current | 4866
| Row Count |  | 8872 | Row Count | 8778
| Total # of Apps |  | 8872 | Total # of Apps | 8778
SELECT Count(distinct a.row_id) as cnt FROM ldb.f_rita_application_c_fact a JOIN ldb.d_rita_application_c b ON a.rita_application_c_key=b.row_key JOIN ldb.d_rita_application_ext_c c ON b.rita_application_ext_c_key=c.row_key JOIN ldb.d_lov_mega_data_currentness_c d ON c.data_currentness_c_key=d.row_key JOIN ldb.d_lov_mega_data_correct_c e ON c.data_correct_c_key=e.row_key JOIN ldb.d_processing_activities_managing_organization_c a12 ON a.managing_organization_c_key=a12.row_key JOIN ldb.d_lov_processing_activities_ot_life_cycle_status_c a13 ON b.application_lifecycle_status_c_key=a13.row_key JOIN ldb.d_lov_processing_activities_ot_repository_type_c a14 ON b.application_nature_c_key=a14.row_key Where (a14.cust_dimension_name_c IN ('Application','Application - Externally Owned','Application Platform','Application Platform - Externally Owned') AND a13.source_dimension_name IN ('Design/Build', 'Launch/Deploy', 'Discovery/Requ.','UNSPECIFIED','Leverage/Optimize', 'Qualify/Deliver', 'Retired', 'Sunset','Exception') ) AND a.soft_deleted_flag='N'

## Rita_Application_Infosec_C
S no | Attribute | Source | UAT Validation | PROD Instance | VI Changes
1 | Application ID | Servicenow
2 | Application Lifecycle Status | Servicenow
3 | Application Nature | Servicenow
4 | Application Repository Type | Servicenow
5 | BIA Availability | Servicenow
6 | BIA Confidentiality | Servicenow
7 | BIA Integrity | Servicenow
8 | Compliance Factor | Infosec CSV files
9 | Data Asset Name | Servicenow
10 | Exclude in InfoSec Flag | Infosec CSV files
11 | Exclusion Date | Infosec CSV files
12 | Exists in iRisk | Infosec CSV files
13 | Exists in Legacy G1 | Infosec CSV files
14 | Exists in Legacy G234 | Infosec CSV files
15 | GDPR Grouping | Servicenow
16 | Grace Period | Servicenow
17 | Infosec In Scope | Infosec CSV files
18 | Infosec Not Applicable | Infosec CSV files
19 | iRisk Assessment Status | Infosec CSV files
20 | iRisk Category (Internal) | Infosec CSV files
21 | iRisk Category Name | Infosec CSV files
22 | iRisk ID | Infosec CSV files
23 | iRisk Open Issues | Infosec CSV files
24 | iRisk Status | Infosec CSV files
25 | L0 Owning Organization | Servicenow
26 | L1 Owning Organization | Servicenow
27 | L2 Owning Organization | Servicenow
28 | L3 Owning Organization | Servicenow
29 | Mega Hex | Servicenow
30 | Owning Organization | Servicenow
31 | P&G Asset Owner | Servicenow
32 | Privacy Risk | Servicenow
33 | Project Team GDPR Relevant OverWrittenFlag | Servicenow
34 | Reason for Exclusion | Infosec CSV files
35 | SL SPOC | Infosec CSV files
prod dev
| # iRisk IS Assessment Completed (with Open Issues) |  | # of Apps InfoSec Compliant in iRIsk | % GDPR AM Completed (legacy Gr 2, 3. 4) | % GDPR TISL Completed (legacy Gr 1) | % InfoSec Compliance in iRisk | % iRisk IS Assessment Completed (With Open Issues) | % iRisk IS Assessment Completed Without Open Issues | % iRisk IS Assessment In-Progress | GDPR AM Completed (legacy Gr 2, 3. 4) | GDPR TISL Completed (legacy Gr 1) | Infosec No Count | Infosec Yes Count | iRisk Open Issues Count | Row Count | Total # Compliant | Total # Non-Compliant NO-WIP | Total # Non-Compliant WIP | Total # of Applications | Total % Compliant | Total % Non-Compliant No-WIP | Total % Non-Compliant WIP
| 29 |  | 1026.3743 | 30.79% | 5.835% | 92.13% | 2.603% | 12.3% | 24.15% | 343 | 65 | 1269 | 14864 | 232 | 1114 | 545 | 271 | 298 | 1114 | 48.92% | 24.33% | 26.75%
prod
| # iRisk IS Assessment Completed (with Open Issues) |  | # of Apps InfoSec Compliant in iRIsk | % GDPR AM Completed (legacy Gr 2, 3. 4) | % GDPR TISL Completed (legacy Gr 1) | % InfoSec Compliance in iRisk | % iRisk IS Assessment Completed (With Open Issues) | % iRisk IS Assessment Completed Without Open Issues | % iRisk IS Assessment In-Progress | GDPR AM Completed (legacy Gr 2, 3. 4) | GDPR TISL Completed (legacy Gr 1) | Infosec No Count | Infosec Yes Count | iRisk Open Issues Count | Row Count | Total # Compliant | Total # Non-Compliant NO-WIP | Total # Non-Compliant WIP | Total # of Applications | Total % Compliant | Total % Non-Compliant No-WIP | Total % Non-Compliant WIP
| 29 |  | 1026.3743 | 30.79% | 5.835% | 92.13% | 2.603% | 12.3% | 24.15% | 343 | 65 | 1269 | 14864 | 232 | 1114 | 545 | 271 | 298 | 1114 | 48.92% | 24.33% | 26.75%
| TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
| TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE

## RITAApplicationPrivacyCompli
S no | Attribute | Source | UAT Validation | PROD Instance | VI Changes
1 | Application ID
2 | Application LifeCycle Status
3 | Application Nature
4 | Application Repository Type
5 | Assessment Status
6 | BIA Availability
7 | BIA Confidentiality
8 | BIA Integrity
9 | Created Date
10 | Data Asset Name
11 | Due Date
12 | Exclude in Privacy Flag
13 | GDPR Grouping
14 | Grace Period
15 | L0 Owning Organization
16 | L1 Owning Organization
17 | L2 Owning Organization
18 | L3 Owning Organization
19 | Mega Hex
20 | Owning Organization
21 | PG Asset Owner
22 | PIA/DPIA Status
23 | Privacy Category Name
24 | Privacy Category(Internal)
25 | Privacy Compliance Factor
26 | Privacy Dashboard Flag
27 | Privacy Exclusion Date
28 | Privacy Exists in iRisk
29 | Privacy Exists in iRisk Legacy Flag
30 | Privacy Exists in Legacy Flag
31 | Privacy In Scope
32 | Privacy iRisk Status
33 | Privacy Not Applicable
34 | Privacy Reason for Exclusion
35 | Privacy Risk
36 | Privacy Submission Date
37 | Privacy Submitter
38 | PRV-0018
39 | SL SPOC

## Test Cases - Cube Count
INDEX
Pre Requisite: | Cube query has to be updated for latest changes
TC_No | Test Case | Expected Result | Actual Result | Result | Cube query name | Defect JIRA # | Comments
S No | Cube | VI | Issues | Observations
1 | RITA_Application_ Cube | Application Tracker VI | Vendor Qualification attribute is only Unknown and Unspecified | Other Supplier Name and Other Supplier SAP Code : Compelted UNSPECIFIED
|  |  | DataSubject Right Result attribute is UNKNOWN | Source Type : This is still displying Mega, Should it change to Service Now and Mega
GDPR Sensitivity - Need to Handle Unspecified
Comments/otherInformation About the Application attributes is only Blank
2 | RITA_Application_Governance_c cube | ITAM_Application_Governance VI | Database Attirbute is compeltely UNSPECIFIED | Confirmation on Data Privacy ( UNSPECIFIED and No Personal Data)
Keyword-Subject Area is compeletey UNSPECIFIED
License attribute is compeletey UNSPECIFIED
Sox Classification attirbue is compeletey UNSPECIFIED
3 | RITA_Application_Infosec_c cube. RITA_Application_privacy_c cube. | GDPR Application Infosec_privacy_VI | iRisk Open Issues Count Metric is displyaing 0
Unspecified is not handled for IRisk_ID

## References
INDEX
References - Design document, Unit test document, data lineage, Data profiling document (if any)

## QA_Efforts Estimations (hidden)
Home
| Pre Upgrade |  | Prod 003CJ_ 3.2 | prod dev006J_ 3.2
Post Upgrade
| Gilead 5.1 Upgrade |  |  |  |  | Parent Ticket: DELV-6251
S no | Task | Start Date | End Date | Time in hrs | Remark | Task Jirra's
1 | 3.2 Prod Base line |  | 2017-05-29 | 5 mins | Triggered the Delivery Test | DELV-6266
2 | 3.2 Prod Base line_QA Failure Analysis_Cuts |  | 2017-05-29 | 1 hrs | 3 Failures | DELV-6266
3 | 3.2 Prod Base line_QA Failure Analysis_Mats |  | 2017-05-29
4 | 100 % Mats Coverage |  | 2017-05-29 | 3 hrs | Worked for Incident;Reassignment;CMDB Ci Weekly treand-c cube updated and count drop validation. | DELV-6259
|  |  | 2017-05-30 | 3 Hrs | Worked on Request_task,Task_Fss_Keyword,Request_item, Survey_c.
5 | 100 % cust coverage (Datamapper provided on 09_May_2017)
6 | Actual Baseline Report |  | 2017-06-07 | 5 mins |  | DELV-6424
7 | Usage Report |  | 2017-06-07 | 5 mins |  | DELV-6423
8 | Gilead_5.1 Upgrade_ Data mapper_QA_Cust Coverage |  | 2017-06-07 | 1 hrs | Cust Coverage anlaysis and writing the required test scripts. | DELV-6429
|  |  | 2017-06-08 | 4 Hrs
9 | Gilead_5.1_Upgrade_Prod dev_QA Test Scripts and User Document |  | 2017-06-07 | 1 hrs |  | DELV-6430
10 | Cust and Mats ETL Run in Prod dev |  | 2017-06-10 | 5 mins | Tiggered the Delivery Test | DELV-6508
11 | 5.1 ETL_QA Analysis in Prod dev (ETL Issues) |  | 2017-06-12 | 2hrs | QA Failure in Prod dev instance. | DELV-6505,6506,6507
12 | 5.1 Mats_Cube Query Validations in Prod dev |  | 2017-06-12 | 4 Hrs | Validated the Cust Queries in Prod dev instance. | DELV-6509-Task Ticket.
12.1 | 5.1 Mats_Cube Query QA Analysis_Prod dev(Redshift issues) |  | 2017-06-12 |  | Cust Failure in prod dev instance. | DELV-6514,DELV-6513,DELV-6535
13 | MSTR Cube Validation |  | 2017-06-13 |  |  | DELV-6514,DELV-6513,DELV-6535
13.1 | Incident Cube |  | 13-Jun-2017 14-Jun-2017 15-Jun-2017 (Retest Incident issues). | 7 :30 Hrs |  | DELV-6593
13.2 | ITSA_Request Task_ |  | 2017-06-16 | 3:00 Hrs |  | DELV-6594
13.3 | CMDB CI Weekly Trend_C |  | 2017-06-16 | 3:00 Hrs |  | DELV-6608
13.4 | ITSA_Survey_C |  | 2017-06-19 | 3:00 Hrs |  | DELV-6625
13.5 | ITSA_Reassignment_C |  | 2017-06-19 | 3:00 Hrs |  | DELV-6626
13.6 | ITSA_Request_Item_C |  | 2017-06-19 | 3:00 Hrs |  | DELV-6637
13.7 | ITSA_Request_Task_Keyword_C
13.7 | ITSA_TASK FSS_C
13.9 | ITSA_TASK_FSS_C Keyword
14 | Dashboard
14.1